## Resource & Narrative
Year | 2021 | Area | SouthGrid
Quarter | Q1 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | All SL6 nodes have now been upgraded to CentOS 7 except the EOS head node which is in the process of being upgraded. Managed to keep site operating during the third lockdown. |  |  | Had air con issues over Christmas which are yet to be fixed. VAC support is gradually disappearing and consequently, we will start looking at switching over to ARC if we have to
Bristol | xrootd experimental VM working for xrootd--> HDFS and HTTPS --> HDFS; updated APEL accounting for new submission mechanism; enabled Mu3e.org VO; Puppet upgrade to version 6; Workaround for Cloudera CDH repos |  |  | Puppet 4 stopped working for some modules used --> forced upgrade to 6; Cloudera CDH repositories shut public access (even for the free version); major lack of time & access to Physics building to work on LCG :[
Cambridge
Oxford | A test environment has been setup to test Xcache viability as a prerequisite for Oxford going store-less site. The test environment consist of XrootD server, ARC CE/HTcondor server and two worker nodes with 112 threads. Atlas test jobs successfully ran on it. New hardware purchased for the Squid/DHCP. Now in production. Decommissioned SL6 temperature monitoring server with a replacement CentOS 7 server. Added support for Mu3e VO |  |  | 29/03/2021: After a brown out, three out of warranty worker node's raid card failed and now retired.
RAL PPD
Sussex
Risks
Type | Risk |  |  | Mitigation
Birmingham
Bristol | Shortage of human-power |  |  | Regular Ops & Southgrid meetings helpful, despite stretched resources!
Cambridge
Oxford | Storage disks failing Storage pool nodes are still on SL6 Replacement Squid/DHCP server failed Several mother board and memory module failures. |  |  | Replace disks from decommissioned servers Go Storageless site Squid/DHCP server - reverted back to old SL6 - replace the hardware. Replaced under warranty
RAL PPD
Sussex
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-03-31 | BRISTOL: progress on replacing lcgse01 with xrootd-only (io02) |  |  | can retire lcgse01 (and DMLite)
2021-03-31 | BRISTOL:New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-03-31 | BRISTOL:Continue cleaning up and labelling of network cables
2021-03-31 | BRISTOL:Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-03-31 | BRISTOL:START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | WIP
2021-03-31 | BRISTOL:START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | WIP
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-06-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | experimental xrootd VM works, now need to move lessons learnt into puppet. Next try clustered mode for production setup
2021-06-30 | New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-06-30 | Continue cleaning up and labelling of network cables
2021-06-30 | Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-06-30 | START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | WIP
2021-06-30 | START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | WIP
2020-11-20 | OXFORD: replace SL6 VOMS server with CentOS 7 version |  |  | New VOMS VM
2020-11-20 | OXFORD: replace SL6 Squid/DHCP server with CentOS 7 version |  |  | New Squid/DHCP server
2020-11-10 | OXFORD: replace the old monitoring server |  |  | New monitoring server

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 263.8% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 215.9% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 71.84% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 92.87% | MCT | Average Argo Availability - SouthGrid |  |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 93.56% | MCT | Average Argo Reliability - SouthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 22768 | 26780 | 8500 | 45682 | 55500 | 3580 | 162810 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 9466 | 7292 | 3965 | 15882 | 22851 | 2257 | 61713
% of Pledge | 240.5% | 367.3% | 214.4% | 287.6% | 242.9% | 158.6% | 263.8%
Storage Available (TB) | 1717 | 1085 |  | 910 | 3600 |  | 7312
Storage Pledged (TB) | 1040 | 0 | 0 | 301 | 2045 | 0 | 3386
% of Pledge | 165.1% | #DIV/0! | #DIV/0! | 302.3% | 176% | #DIV/0! | 215.9%
Availability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 |  | 97.87 | 98.51 |  | 98.79% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 95.52 |  | 100 | 99.84 |  | 98.45% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 |  | 99.73 | 94.61 |  | 98.11% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 98.5067 | #DIV/0! | 99.2 | 97.6533 | #DIV/0! | 98.45%
Reliability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 |  | 97.87 | 98.51 |  | 98.79% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 99.17 |  | 100 | 99.84 |  | 99.67% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 |  | 99.73 | 94.61 |  | 98.11%
% Tier-2 Total | #DIV/0! | 99.7233 | #DIV/0! | 99.2 | 97.6533 | #DIV/0! | 98.86%
CPU Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 229035840 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 2500243 | 9877127 | 3965849 | 19083480 | 35586547 |  | 71013246 | Q1: 2160/2184 (if leap year)
Month 2 | 3257294 | 8199037 | 2005753 | 16695144 | 23733056 |  | 53890284 | Q2: 2184
Month 3 | 5286110 | 10453322 | 2154172 | 3289231 | 31927215 |  | 53110050 | Q3: 2208
Total: | 11043647 | 28529486 | 8125774 | 39067855 | 91246818 | 0 | 178013580 | Q4: 2208
% Utilisation | 21.97% | 48.25% | 43.3% | 38.73% | 74.46% | 0% | 77.72%
WallClock Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 359484480 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 3938290 | 12629191 | 5824304 | 22014867 | 41475793 |  | 85882445 | Q1: 2160/2184 (if leap year)
Month 2 | 5123683 | 9993912 | 4460866 | 19714892 | 35411492 |  | 74704845 | Q2: 2184
Month 3 | 6023853 | 12236035 | 3506059 | 3625190 | 42310879 |  | 67702016 | Q3: 2208
Total: | 15085826 | 34859138 | 13791229 | 45354949 | 119198164 | 0 | 228289306 | Q4: 2208
% Utilisation | 30.01% | 58.95% | 73.48% | 44.97% | 97.27% | 0% | 63.5%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 740 | 690 | 0 | 1510 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 0 | 0 | 0 | 384 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 630 | 599 | 0 | 1309 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 0 | 0 | 0 | 325 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/UK-SouthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes