## Resource & Narrative
Year | 2021 | Area | CMS
Quarter | Q1 | Reporter | KE |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Tier 1 |  |  |  | On top of existing inefficiencies and failures, likely related to file access, there was a problem with WN xrootd containers not being re-created. This affected all VOs but particularly CMS who stream data throughout the job. T1 was put into drain for a week for CMS then brought back with a limited number of cores.
Tier 2s
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [11 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 10 |  | 5% |  | AWI | Tier-1 Data Transfer Quality | No major problems for site to site transfers. Tape pledge is still full so there have not been writes except for tests. | [5 empty] | Metric OK | MOK
2 | 11 | 5% or pledge | 5% | 7.4% | #VALUE! | Timely and efficient availability and use of resources at RAL T1 (Global %) | Some periods below pledge but compensated with periods well above pledge. Late-Feb/early March there was 10 days we were capped at pledge due to LHCb issues getting fair share. In mid-March we were put into drain for Prod due to WN gateways disappearing then brought back gradually. RAL ran 7.4% of Completed T1 jobs. | [5 empty] | Metric Clost to Target | MCT
2 | 12 | 70% | 5% | 30% | MFL | Tier-1 Average CPU Efficiency | 30% - even worse than previous quarter. This is at least 40 percentage points below any other T1 for the same period and RAL was put into drain for Prod to stop it getting worse. No progress on improving offsite reads in this period; tests show that onsite reads are just as problematic. | [5 empty] | Metric not OK | MFL
2 | 13 | 10% | 5% | 27% | MFL | Tier-1 Failure Rate | 27% which is similar to last quarter. Of these only 16% are LogCollect which fail for known reasons. The rest are a mixture of Analysis and Processing jobs. The Processing jobs almost always fail due to file access problems. Highest failure rate among T1s, similar to FNAL. | [5 empty] | Metric with no Target | MNO
2 | 14 | 97% | 5% | 100% | MOK | Site availability at the Tier-1 | "SAM 1 day availability" is 91%. WLCG site mon is 100%
2 | 15 | 5% | 5% |  | AWI | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | There is currently no way to access this information.
2 | 16 | 0% | 1% | 0% | MOK | Custodial Data Loss at Tier-1 | None
2 | 17 |  | 5% |  | AWI | Transfer rates to the UK Tier 2s | No major problems
2 | 18 | 80% | 5% | 99% | MOK | Site availability at the Tier-2s | IC - 100%, Brunel - 99%, RALPP - 98%. Source e.g.: https://monit-wlcg-sitemon.web.cern.ch/monit-wlcg-sitemon/reports/2021/202102/wlcg/WLCG_All_Sites_CMS_Feb2021.pdf
2 | 19 | 80% | 5% | 99% | MOK | Site reliability at the Tier-2s | As above
2 | 20 | 0% | 5% |  | AWI | Unique data loss at Tier-2s | None
2 | 21 | 30% | 5% | 30% | MOK | Failed analysis jobs | About 30% failure rate for analysis jobs, which is worse than last quarter
2 | 22 | 20% | 5% | 15% | MOK | Failed production jobs | About 15% failure rate for production jobs, which is the same as last quarter
2 | 23 | 5% | 5% | 4.7% | MOK | T2 sites provide an appropriate level of resource to CMS | UK sites provided CPU to complete 4.7% of CMS T2 jobs
2 | 24 | 80% | 5% |  | AWI | Job performance/efficiency using AAA data transfer | There is currently no way to access this information.
Milestones | [11 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 5 | 2020-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Achieved | MSA
2 | 6 | 2021-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Ongoing | MOG
2 | 7 | 2022-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Overdue | MOD
2 | 8 | 2023-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone not due | MSU
2 | 17 | 2020-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 18 | 2021-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 19 | 2021-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 20 | 2022-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 21 | 2022-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 22 | 2023-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 23 | 2023-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 24 | 2024-04-01 | N |  | MSU | Review of CMS AAA Efficiency
Site availability
[7 empty] | Site | Jan | Feb | Mar | Avg
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333
Site reliability
[7 empty] | Site | Jan | Feb | Mar
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes