## Resource & Narrative
Year | 2020 | Area | LHCb
Quarter | Q3 | Reporter | RN |  | Approved | AMcN
Narrative
Area | Successes |  |  | Problems
Task 1 | Outside the 4 issues mentioned, the jobs “mostly” (except for two workflows) run fine at RAL Tier-1. However, these issues show that it is an unstable equilibrium at best … |  |  | 1. Ongoing streaming issue from ECHO at RAL. Suggested timescales until now have all slipped. 2. Possible corruption of data issue at RAL. Yet to be understood. 3. Issue extracting checksums from ECHO using xrootd protocol (was supposed to just “work”) 4. Possible problems with the CEs / batch system which had large variations in number of LHCb running jobs. This has settled down for now, but the orign of the variations is not yet understood.
Task 2 | Excellent communication with the Tier-2 sites using the mailing lists and different meetings. |  |  | Issues with networking at some Tier-2 sites which will need follow up. May become an issue as LHC starts its run again next year.
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc | Networking to various university sites |  |  | Investment in networking?
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 25 | 90% | 5% | 69.6% | MFL | Tier-1 prod CPU efficiency | In line with previous numbers Note that this is jobs not including simulation |  | Metric OK | MOK
2 | 26 | 50% | 5% | 79.4% | MOK | Tier-1 user success rate |  |  | Metric Clost to Target | MCT
2 | 27 | 70% | 5% | 75.7% | MOK | Tier-1 user CPU efficiency | Good enough I suppose, considering the ongoing ECHO streaming issue |  | Metric not OK | MFL
2 | 28 | 15% | 5% | 19% | MOK | UK Tier-1 work fraction |  |  | Metric with no Target | MNO
2 | 29 | 50% | 5% | 91.7% | MOK | Tier-2A : User success rate
2 | 30 | 70% | 5% | 95.8% | MOK | Tier-2A : User CPU efficiency
2 | 31 | 90% | 5% | 94.4% | MOK | All Tier-2: Simulation success rate
2 | 32 | 90% | 5% | 98.2% | MOK | All Tier-2: Simulation CPU efficiency
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N | 2020-11-01 | MSA | Report on delivery to LHCb during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes