## Resource & Narrative
Year | 2021 | Area | Other VOs
Quarter | Q1 | Reporter | KE
Narrative
Area | Successes |  |  | Problems
Onboarding new VOs
Supporting existing VOs through major campaigns
Service improvements
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc | Communication during Covid particularly. Can lose touch with the smaller VOs.
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 33 | 90% | 40% | 64% | MCT | UK Tier-1 work fraction for ALICE as a proportion of all Tier-1s (not CERN). Normalised to 3% for GridPP6 | This seems low, RAL appears to only have run 1.9% of ALICE T1 jobs this quarter. |  | Metric OK | MOK
2 | 34 | 70% | 20% | 52% | MCT | UK T1 CPU efficiency by ALICE. | This is better than last quarter, but still more than 20 percentage points below average (RAL is worst by far). Note: this is the same as metric 1a.30 - could remove? |  | Metric Clost to Target | MCT
2 | 35 | 90% | 20% | 68% | MFL | UK T1 CPU usage by ALICE. Normalised against pledged HS06. | 10950 HS06 is the pledge for Q1, changes next Q to 14940. Note this is the same as metric 1a.18 - could remove? |  | Metric not OK | MFL
2 | 36 | 90% | 40% | 86% | MCT | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s. Normalised to 2.1% for GridPP6. | 1.8% of T2 work |  | Metric with no Target | MNO
2 | 37 | 70% | 10% | 81% | MOK | UK T2 CPU efficiency for Alice. | Similar to last quarter - https://accounting.egi.eu/tier2/cpueff/COUNTRY/VO/2021/1/2021/3/custom-alice/onlyinfrajobs/
|  | 80% | 10% | 48% |  | ALICE disk usage at T1 (on last day of the quarter?) Pledge=1.32PB | 636TB. https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-03-31.json. Also a duplicate from T1 report - 1a.19 - could remove
|  | 80% | 10% | 86% |  | ALICE tape usage at T1 (on last day of the quarter?) - 'occupied size'. Pledge=1.131PB | 968 TB. http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_31032021 - also a duplicate of 1a.20 - could remove
|  | 80% | 10% | 52% |  | ALICE disk usage at T2 (on last day of the quarter?) | From Mark Slater: capacity: 1.04PB available: 992.82 TB (note that this is lower due to slowness in fixing problems due to COVID) used: 541.51 TB (Katy - interesting this is lower than last quarter)
2 | 38 | 70% | 20% | 49% | MFL | T1 CPU Efficiency for DUNE | Improved significantly throughout the quarter. The best of those listed in EGI accounting.
2 | 39 | 70% | 20% | 47% | MFL | T2 CPU Efficiency for DUNE | Improved month-by-month, and better than other countries except Switzerland.
2 | 40 | 75% | 25% | 35% | MFL | CPU usage by DUNE in the UK relative to pledge of 2000 cores | 695 cores in total, from T1 (average 134 cores) and T2 (average 561 cores). This is down from Q4, but I'm pretty sure these numbers change after I have put them in this spreadsheet. https://accounting.egi.eu/tier2/elap_processors/COUNTRY/DATE/2021/1/2021/3/custom-dune/onlyinfrajobs/
2 | 41 | 70% | 20% | 90% | MOK | T1 CPU Efficiency for Other (non-DUNE, non-LHC)
2 | 42 | 70% | 20% | 81% | MOK | T2 CPU Efficiency for Other (non-DUNE, non-LHC)
2 | 43 | 75% | 25% | 70% | MCT | T1/T2 % pledged CPU used by Other VOs (pledge is 13% of CPU used by combined LHC exps pledge in UK, which is 533922 HS06 ~ so 13% is 69410) | T1 usage 8546608 HS06 hours = 3957 HS06; T2 usage 95650893 HS06 hours = 44283 HS06. Total sum is 48240. Slightly down on last quarter
Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments
|  | 2020-04-01 | N |  | MSU |  |  | Key - Milestones
|  | 2020-04-01 | N |  | MSU |  |  | Colour | Description | Code
[9 empty] | Milestone Achieved | MSA
[9 empty] | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes