## Resource & Narrative
Year | 2021 | Area | Security
Quarter | Q1 | Reporter | DK/DC
Narrative
Area | Successes |  |  | Problems
Operations | Usual operational security activities were carried out as required. Progress continues on integration of IRIS operational security with GridPP security team. Presented at HEPiX and ISGC, and contributed to and chaired ISGC Security Workshop. Coordination meeting held for SOC WG to set goals for 2021. |  |  | Low response to request for responses on plans for critical vulnerabilities - this could be due to the methodology used to gather this information, so this is being evaluated (this is a communciations issue, not indicative of issues at sites). 1 critical vulnerability was flagged at ECDF outside the ringfenced WLCG estate which was successfully handled by the ECDF systems team (the responsible parties)
Trust & Identity | Continued progress in REFEDS SIRTFI working group and eduGAIN security. Ongoing collaboration with policy groups in WISE, GN4-3 and IGTF. Continue to make good progress on guidance for use of Assurance frameworks |  |  | None
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 100% | MOK | % of Sites responding to security communication requests | n/a for this reporting period |  | Metric OK | MOK
3 | 3 | 95% | 5% | 66% | MFL | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | 3 applicable broadcasts in this time period; the low response rate has led to a re-evaluation of the measurement of this metric |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | n/a for this reporting period |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N | 2020-07-01 | MSA | GridPP-wide security training event | IRIS Security Workshop held at end of July 2020
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
2020-11-03 | EGI Conference, "Developing a Trust and Security Framework for IRIS", D Crooks
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes