## Resource & Narrative
Year | 2021 | Area | Federal Services
Quarter | Q1 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
GOCDB | Internal and external monitoring of the new failover continues to improve. Ensuring GOCDB is as interoperable as possible by reviving ties to the OGF Glue Working Group. Old (and now unused) hosts shutdown To meet requirements of the EOSC-hub project, a separate “view” of GOCDB was deployed: https://gocdb.eosc-portal.eu/portal/ |  |  | Ongoing issues with the RAL Tier 1 Load balancers and the underlying virtualisation platform they use result in repeated minor outages of GOCDB (20 minutes per week). This is suspected to effect all services making use of the load balancers and is being investigated with the appropriate teams in the Tier 1.
Accounting - APEL and IRIS Dashboard
Workflow Management - DIRAC | Stable running. We participate in the weekly (technical) DIRAC meetings/hackathons to ensure that up and coming DIRAC updates are compatible with our system and we continue to contribute bug fixes. Simon F is still the release manager for VMDirac (Cloud Interface).
Data Management - Rucio and FTS | Start of EGI-ACE project. Recruited new member of staff. |  |  | Bug means that Rucio can't choose the correct proxy to use when submitting transfers.
CVMFS Service | Service migrated to new hardware and OS. Onboarded service with EGI-ACE.
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
3 | 1 | 99% | 2% | 99.95% | MOK | GOCDB Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-GOCDB?start_date=2021-01-01&end_date=2021-03-31 |  | Metric OK | MOK
3 | 2 | 0.5 | 0.1 | 1.7 | MOK | GOCDB Usage | Average Number of Concurrent GOCDB sessions https://vande.gridpp.rl.ac.uk/next/d/gbuGiWHMk/gocdb-longer-term-host-metrics?orgId=1&from=1593558000000&to=1601506799000&viewPanel=6 |  | Metric Clost to Target | MCT
3 | 3 | 99% | 2% | 100% | MOK | APEL Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-APEL?start_date=2020-10-01&end_date=2020-12-31 |  | Metric not OK | MFL
3 | 4 | 1 | 0.2 | 1.2 | MOK | APEL Usage | Millions of messages processed in the quarter. |  | Metric with no Target | MNO
3 | 5 | 97% | 2% | 99% | MOK | Workflow Management (DIRAC) Availability
3 | 6 | 5 | 2 | 10 | MOK | Workflow Management (DIRAC) Usage | Measured as number of active VO (>2000 jobs in the quarter)
3 | 7 | 99% | 2% | 100% | MOK | Data Management (FTS + Rucio) Availability | Only measuring FTS service availability currently
3 | 8 | 3 | 1 | 2 | MCT | Data Management (FTS + Rucio) Usage
3 | 9 | 99% | 2% | 100% | MOK | CVMFS Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-CVMFS?start_date=2021-01-01&end_date=2021-03-31
3 | 10 |  |  | 44 | MOK | CVMFS Usage | Measured as number of active repositories
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
|  |  | N |  | MSU |  |  |  | Milestone Achieved | MSA
|  |  | N |  | MSU |  |  |  | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes