## Resource & Narrative
Year | 2021 | Area | Tier-1
Quarter | Q2 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
Tape System (Castor) | Migration to Spectra Logic Library Ccompleted
Disk (Echo)
Batch System |  |  |  | Long running problem with LHCb analysis jobs not being able to access their data correctly.
Network |  |  |  | Problems with (primarily) CMS jobs accessing offsite data through the firewall are reducing job efficiency.
Other
Risks
Type | Risk |  |  | Mitigation
General | Access to the machine room has been reduced as a result of he Covid-19 restrictions. |  |  | Organising interventions more carefully and postpone non-essential work.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-03-31 | Delivery of this years hardware procurements |  |  | Not yet deployed into production

## Metrics & Milestones
Metrics | [8 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Notes | Colour | Description | Code
1a | 1 | 100% | 5% | 97.55% | MCT | % of GridPP commitment for CPU |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric OK | MOK
1a | 2 | 100% | 5% | 92% | MFL | % of GridPP commitment for Disk | The delay in deploying this years disk procurement is not affecting our ability to deliver as many non-LHC VOs are not using their allocation. | Calculated from Allocations.xlsx using [Total Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric Clost to Target | MCT
1a | 3 | 100% | 5% | 110% | MOK | % of GridPP allocation for Tape |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. Note the Total Commitment is lower than the total request because we buy Tape when required. |  | Metric not OK | MFL
1a | 4 | 94% | 5% | 101.9% | MOK | % of GridPP6 Staff funded |  |  |  | Metric with no Target | MNO
1a | 5 | 98% | 3% | 98.3% | MOK | WLCG Service Availability for Alice |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/06-21/WLCG_Tier1_History_ALICE_Jun2021.pdf
1a | 6 | 98% | 3% | 100% | MOK | WLCG Service Availability for ATLAS |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/06-21/WLCG_Tier1_History_ATLAS_Jun2021.pdf
1a | 7 | 98% | 3% | 99.7% | MOK | WLCG Service Availability for CMS |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/06-21/WLCG_Tier1_History_CMS_Jun2021.pdf
1a | 8 | 98% | 3% | 99.67% | MOK | WLCG Service Availability for LHCB |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/06-21/WLCG_Tier1_History_LHCB_Jun2021.pdf
1a | 9 | 90% | 20% | 99.44% | MOK | % usage by ATLAS of their CPU pledge | Manual correctionhas been applied as May accounting is incorrect in APEL | ATLAS Pledge = 173160 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/4/2021/6/lhc/onlyinfrajobs/
1a | 10 | 80% | 20% | 96.47% | MOK | % usage by ATLAS of their Disk pledge |  | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-06-30.json
1a | 11 | 80% | 20% | 73.78% | MCT | % usage by ATLAS of their Tape pledge | Pledge increased in April, the VO has not had time to use it yet. | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30062021
1a | 12 | 90% | 20% | 187.9% | MOK | % usage by CMS of their CPU pledge | Manual correctionhas been applied as May accounting is incorrect in APEL | CMS Pledge = 52000HS06 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/4/2021/6/lhc/onlyinfrajobs/
1a | 13 | 80% | 20% | 94.14% | MOK | % usage by CMS of their Disk pledge |  | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-06-30.json
1a | 14 | 80% | 20% | 98.65% | MOK | % usage by CMS of their Tape pledge |  | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30062021
1a | 15 | 90% | 20% | 58.66% | MFL | % usage by LHCb of their CPU pledge | Significant increase in LHCb pledge in April, new hardware had not entered production until near end of quarter. (Manual correction needed as May accounting is incorrect in APEL) | LHCb Pledge = 135464 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/4/2021/6/lhc/onlyinfrajobs/
1a | 16 | 80% | 20% | 77.02% | MCT | % usage by LHCb of their Disk pledge | Pledge increased in April, the VO has not had time to uset it yet. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-06-30.json
1a | 17 | 80% | 20% | 73.04% | MCT | % usage by LHCb of their Tape pledge | Pledge increase in April, the VO has not had tme to use it yet. | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30062021
1a | 18 | 90% | 20% | 55.74% | MFL | % usage by ALICE of their CPU pledge | Significant increase in ALICE pledge in April, new hardware had not entered production until near end of quarter. (Manual correction needed as May accounting is incorrect in APEL) | ALICE Pledge = 14940 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/4/2021/6/lhc/onlyinfrajobs/
1a | 19 | 80% | 20% | 38.87% | MFL | % usage by ALICE of their Disk pledge | We are working with ALICE to ensure that they can make full use of their storage. There have been problems with the authentication for their Third Party Transfers. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-06-30.json
1a | 20 | 80% | 20% | 51.58% | MFL | % usage by ALICE of their Tape pledge | ALICE have not been writing to tape during the long shutdown. | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_31032021
1a | 21 | 40% | 30% | 14.99% | MCT | % usage by non-LHC VOs of their CPU allocation |  | Total Pledge * 0.13 = 48823 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/04/2021/06/custom-biomed,dune,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 22 | 80% | 20% | 95.5% | MOK | % usage by non-LHC VOs of their Disk allocation | Currently only Dune using Echo | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-06-30.json
1a | 23 | 80% | 20% | 152.9% | MOK | % usage by non-LHC VOs of their Tape allocation |  | Total Pledge * 0.1 = 7177TB Usage calculated from printTapeUsage.py
1a | 24 | 90% | 10% | 88.66% | MCT | GridPP Funded Farm Occupancy |  | https://vande.gridpp.rl.ac.uk/next/d/3NOsnhnMz/batch-system-capacity?orgId=1&from=1617231600000&to=1625093999000
1a | 25 | 80% | 10% | 90% | MOK | % Total DIsk Usage |  | ResourceUsage spreadsheet
1a | 26 | 80% | 10% | 89% | MOK | % Total Tape Usage |  | ResourceUsage spreadsheet
1a | 27 | 70% | 20% | 83% | MOK | % Job Efficiency (CPU/Wall) - ATLAS | Estimated based on a subset of total data from internal HTCondor database. | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2021/04/2021/06/lhc/onlyinfrajobs/
1a | 28 | 70% | 20% | 47.7% | MFL | % Job Efficiency (CPU/Wall) - CMS | Significantly better than previous quarter due to Firewall upgrade, however CMS are still limited by external network connectivity. Estimated based on a subset of total data from internal HTCondor database. | See Above
1a | 29 | 70% | 20% | 94% | MOK | % Job Efficiency (CPU/Wall) - LHCb | Estimated based on a subset of total data from internal HTCondor database. | See Above
1a | 30 | 70% | 20% | 73% | MOK | % Job Efficiency (CPU/Wall) - ALICE | Estimated based on a subset of total data from internal HTCondor database. | See Above
1a | 31 | 70% | 20% | 50% | MCT | % Job Efficiency (CPU/Wall) - non-LHC | Estimated based on a subset of total data from internal HTCondor database. Dominated by Dune who ran the most jobs and had an efficiency of 45% | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2021/04/2021/06/custom-biomed,dune,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 32 | 95% | 5% | 97.36% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ATLAS |  | https://accounting.egi.eu/tier1/cpueff/VO/TIER1/2021/04/2021/06/lhc/onlyinfrajobs/
1a | 33 | 95% | 5% | 68.81% | MFL | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - CMS | CMS and ALICE who both rely on off-site reads | See Above
1a | 34 | 95% | 5% | 100.5% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - LHCb |  | See Above
1a | 35 | 95% | 5% | 95.05% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ALICE |  | See Above
1a | 36 | 100% | 5% | 100% | MOK | % of GGUS Tickets Handled |  | https://ggus.eu/index.php?mode=ticket_search&show_columns_check%5B0%5D=TICKET_TYPE&show_columns_check%5B1%5D=AFFECTED_VO&show_columns_check%5B2%5D=AFFECTED_SITE&show_columns_check%5B3%5D=PRIORITY&show_columns_check%5B4%5D=RESPONSIBLE_UNIT&show_columns_check%5B5%5D=STATUS&show_columns_check%5B6%5D=DATE_OF_CHANGE&show_columns_check%5B7%5D=SHORT_DESCRIPTION&show_columns_check%5B8%5D=SCOPE&su_hierarchy=0&affectedsite=RAL-LCG2&specattrib=none&status=all&typeofproblem=all&ticket_category=all&date_type=creation+date&timeframe=lastweek&tf_radio=2&from_date=01+Apr+2020&to_date=30+Jun+2020&orderticketsby=REQUEST_ID&orderhow=desc&search_submit=GO%21&ticket_per_page=50
1a | 37 | 30 | 10 | 6 | MOK | Average number of security vunerabilities |  | https://install02.gridpp.rl.ac.uk/pakiti/ Take Average Security in gridpp.rl.ac.uk domain
Milestones | [8 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Comments | Colour | Description | Code
1a | 1 | 2020-11-01 | N |  | MSU | GridPP review of operation (biennial) |  |  |  | Milestone Achieved | MSA
1a | 2 | 2022-10-01 | N |  | MSU | GridPP review of operation (biennial) |  |  |  | Milestone Ongoing | MOG
1a | 3 | 2020-06-01 | 2020-04-01 | 2020-06-01 | MSA | Produce the purchasing plan |  |  |  | Milestone Overdue | MOD
1a | 4 | 2020-11-01 | 2020-09-01 | 2020-09-01 | MSA | FY20 Capacity order placed |  |  |  | Milestone not due | MSU
1a | 5 | 2021-04-01 | 2021-01-01 |  | MSU | FY20 Purchase in production | Expected to enter production in June 21
1a | 6 | 2021-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 7 | 2021-06-01 | N |  | MSU | Produce the purchasing plan
1a | 8 | 2021-11-01 | N |  | MSU | FY21 Capacity order placed
1a | 9 | 2022-04-01 | N |  | MSU | FY21 Purchase in production
1a | 10 | 2022-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 11 | 2022-06-01 | N |  | MSU | Produce the purchasing plan
1a | 12 | 2022-11-01 | N |  | MSU | FY22 Capacity order placed
1a | 13 | 2023-04-01 | N |  | MSU | FY22 Purchase in production
1a | 14 | 2023-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 15 | 2023-06-01 | N |  | MSU | Produce the purchasing plan
1a | 16 | 2023-11-01 | N |  | MSU | FY23 Capacity order placed
1a | 17 | 2024-04-01 | N |  | MSU | FY23 Purchase in production
1a | 18 | 2024-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes