## Resource & Narrative
Year | 2021 | Area | NorthGrid
Quarter | Q2 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | Successfully put on line much of the kit purchased using IRIS EoY cash |  |  | Some issues with new kit meant that there were delays into August for deployment.
Liverpool | Rob and John "officially" providing grid support. Campus networks generally being upgraded but still waiting on University to upgrade their hardware to support production IPv6. Annual site host certs update completed. Site backup system upgraded. General ongoing maintenance where possible. |  |  | Had to ban ILC from our ARCCE as they were requesting MCORE slots but only running SCORE wasting resources, VO works fine on HTCCE.
Manchester | Network upgrade continuing upgrade of the external link to 40Gbs in cooperation with university networking team. |  |  | This was delayed by covid and drastic changes in the network provisioning of the university.
Sheffield | Site still running |  |  | Not much admin time at the site still.
Risks
Type | Risk |  |  | Mitigation
Lancaster | Aging disk hardware being a big problem Running a little late on getting in new purchase. |  |  | Putting in new hardware, investigating CEPH Put in new purchase as soon as possible in Q3
Liverpool
Manchester
Sheffield | Low amount of staff time |  |  | All that could be done to mitigate this has been already.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Lancaster – new compute online CEPH planning started |  |  | Increased capacity A journey of a thousand miles starts with a single step.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-09-01 | Lancaster – get rest of kit online. Put in order for new kit. Progress with CEPH tests |  |  | More kit. Ready to replace DPM

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% | 215% | MOK | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% | 137% | MOK | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% | 156% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 94.3% | MCT | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 94.9% | MCT | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 91995 | 35047 | 55829 | 11918 | 182871 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 30822 | 18990 | 25443 | 9652 | 84907 | (plus 10% here for other Vos)
% of Pledge | 298.5% | 184.6% | 219.4% | 123.5% | 215.4% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 3400 | 1424 | 6820 | 0 | 11644
Storage Pledged (TB) | 2825 | 330 | 5648 | 0 | 8803
% of Pledge | 120.4% | 431.5% | 120.8% | 100% | 132.3%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 100 | 100 | 76 | 94% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 98 | 100 | 95 | 100 | 98.25% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 91 | 72 | 90.75%
% Tier-2 Averge | 99.3333 | 100 | 95.3333 | 82.6667 | 94.33%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 100 | 100 | 78 | 94.5% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 98 | 100 | 100 | 100 | 99.5% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 91 | 72 | 90.75%
% Tier-2 Total | 99.3333 | 100 | 97 | 83.3333 | 94.92%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 200917080 | 76542648 | 121930536 | 26028912 | 425419176 | https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 59475221 | 20974950 | 61294037 | 4148672 | 145892880 | Q1: 2160/2184 (if leap year)
Month 2 | 58057364 | 20665208 | 136274988 | 6269187 | 221266747 | Q2: 2184
Month 3 | 62312364 | 22458961 | 128410569 | 6237927 | 219419821 | Q3: 2208
Total: | 179844949 | 64099119 | 325979594 | 16655786 | 586579448 | Q4: 2208
% Utilisation | 89.51% | 83.74% | 267.3% | 63.99% | 137.9% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 200917080 | 76542648 | 121930536 | 26028912 | 425419176 | https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 70023691 | 23478785 | 66837927 | 4100377 | 164440780 | Q1: 2160/2184 (if leap year)
Month 2 | 74076854 | 24046226 | 148682380 | 6654056 | 253459516 | Q2: 2184
Month 3 | 79677182 | 23591066 | 137721299 | 6743548 | 247733095 | Q3: 2208
Total: | 223777727 | 71116077 | 353241606 | 17497981 | 665633391 | Q4: 2208
% Utilisation | 111.4% | 92.91% | 289.7% | 67.23% | 156.5%
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3400 | 970 | 0 | 0 | 4370 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 313 | 0 | 0 | 313
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 1060 | 0 | 0 | 0 | 1060
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 2400 | 860 | 0 | 0 | 3260 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 211 | 0 | 0 | 211
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 313 | 0 | 0 | 0 | 313
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 23.4 | 0 |  | 41.4 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 1.4 | 0.3 | 0 |  | 1.7 | https://accounting.egi.eu/tier2/federation/NorthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.5 | 0 |  | 2.5 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.1 | 0 |  | 0.1
gridpp | 0.001 | 0 | 0 |  | 0.001
lsst | 0 | 1 | 0 |  | 1
dune | 0 | 0.6 | 0 |  | 0.6
mu3e.org | 0 | 44 | 0 |  | 44
hyperk.org | 0.4 | 0 | 0 |  | 0.4
| 0 | 0 | 0 |  | 0
lsst (iris) | 91 | 0 | 0 |  | 91
dune (iris) | 42 | 0 | 0 |  | 42
vo.cta.in2p3.fr (iris) | 150 | 0 | 0 |  | 150
ska.telescope.eu (iris) | 0.04 | 0 | 0 |  | 0.04
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes