## Resource & Narrative
Year | 2021 | Area | SouthGrid
Quarter | Q2 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | Made space for the new equipment to be installed. This should be done in the next quarter now there are more people in the dept to help move the machines. |  |  | Still waiting on a fix for the aircon failure that happened at the start of the year. Can only run at 50% capacity until then.
Bristol | 6-OS to 7-OS upgrade for DICE WN 99% complete. |  |  | A few DICE WN with ++++storage took SEVERAL WEEKS to fully decommission xrootd replacement storage element has trouble authenticating with ARGUS - exploring workarounds.
Oxford | Continuing testing Xrootd Xcache for Atlas jobs. To improve performance, the Xcache server was rebuilt with direct storage for data disks. Atlas production jobs runs successfully using the Xcache, however, the CPU efficiency of these jobs are low. ARC-CE upgraded to version 6.12 Installed Entrust SSL cert on PerfSonar server. |  |  | 11/05/2021: Power outage at Begbroke datacentre after a lighting strike - lost four DPM storage pool nodes, 112,134 files were declared lost.
RAL PPD | Brought online 2PB of new disk Retired 2PB of out of support old disk Upgraded to ArcCE 6.12 |  |  | LHCONE Routing still not correct in the RAL core network, little effort in central network team to fix the problem. Current routing works but is not optimal. New Router hardware purchased but awaiting effort from networking to install it.
Sussex | No response |  |  | No response
Risks
Type | Risk |  |  | Mitigation
Birmingham | Made space for the new equipment to be installed. This should be done in the next quarter now there are more people in the dept to help move the machines. |  |  | Still waiting on a fix for the aircon failure that happened at the start of the year. Can only run at 50% capacity until then.
Bristol | Shortage of human-power |  |  | Regular Ops & Southgrid meetings helpful, despite stretched resources!
Oxford | Storage disks failing Storage pool nodes are still on SL6 A/C due for replacement soon. |  |  | Replace disks from decommissioned servers Go Storage-less site
RAL PPD
Sussex
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-06-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | experimental xrootd VM works, now need to move lessons learnt into puppet. Next try clustered mode for production setup
2021-06-30 | New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-06-30 | Continue cleaning up and labelling of network cables
2021-06-30 | Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-06-30 | START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | WIP
2021-06-30 | START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | WIP
2021-04-30 | OXFORD: The Xrootd Xcache server is configured and running production ATLAS jobs. |  |  | Running production jobs
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-07-30 | OXFORD: decommission old DPM storage servers. |  |  | Storage-less site from 1st July 2021
2021-10-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | experimental xrootd VM works, now need to move lessons learnt into puppet. Next try clustered mode for production setup
2021-10-30 | New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-10-30 | Continue cleaning up and labelling of network cables |  |  | Satisfied HPC Admin (who is badgering us to do this)
2021-08-30 | Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-10-30 | START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | wiki pages
2021-10-30 | START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | wiki pages

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 203.8% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 174.9% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 70.46% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 90.72% | MCT | Average Argo Availability - SouthGrid |  |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 90.72% | MCT | Average Argo Reliability - SouthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 22768 | 26780 | 45682 | 55500 | 3580 | 154310 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 11766 | 6195 | 18807 | 37579 | 1360 | 75707
% of Pledge | 193.5% | 432.3% | 242.9% | 147.7% | 263.2% | 203.8%
Storage Available (TB) | 1717 | 1085 | 0 | 3600 |  | 6402 | Oxford is a storage less site from 1st July 2021
Storage Pledged (TB) | 1138 | 0 | 0 | 2522 | 0 | 3660
% of Pledge | 150.9% | #DIV/0! | #DIV/0! | 142.7% | #DIV/0! | 174.9%
Availability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 | 100 | 99.94 | 58.04 | 89.5% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 97.66 | 84.35 | 90.92 | 99.97 | 93.22% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 | 92.2 | 92.42 | 73.14 | 89.44% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 99.22 | 92.1833 | 94.4267 | 77.05 | 90.72%
Reliability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 | 100 | 99.94 | 58.04 | 89.5% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 97.66 | 84.35 | 90.92 | 99.97 | 93.22% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 | 92.2 | 92.42 | 73.14 | 89.44%
% Tier-2 Total | #DIV/0! | 99.22 | 92.1833 | 94.4267 | 77.05 | 90.72%
CPU Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 49725312 | 58487520 | 99769488 | 121212000 | 7818720 | 207982320 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 6209528 | 10697923 | 13267044 | 29692818 | 141077 | 60008390 | Q1: 2160/2184 (if leap year)
Month 2 | 6255387 | 10978328 | 10692099 | 30437042 | 74525 | 58437381 | Q2: 2184
Month 3 | 5809148 | 11444305 | 20857664 | 29709222 | 1892317 | 69712656 | Q3: 2208
Total: | 18274063 | 33120556 | 44816807 | 89839082 | 2107919 | 188158427 | Q4: 2208
% Utilisation | 36.75% | 56.63% | 44.92% | 74.12% | 26.96% | 90.47%
WallClock Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 49725312 | 58487520 | 99769488 | 121212000 | 7818720 | 337013040 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 6883712 | 12464105 | 15585993 | 38853264 | 137250 | 73924324 | Q1: 2160/2184 (if leap year)
Month 2 | 7350177 | 14818248 | 14200744 | 41935762 | 71359 | 78376290 | Q2: 2184
Month 3 | 6792842 | 15797523 | 22804395 | 38089057 | 1670518 | 85154335 | Q3: 2208
Total: | 21026731 | 43079876 | 52591132 | 118878083 | 1879127 | 237454949 | Q4: 2208
% Utilisation | 42.29% | 73.66% | 52.71% | 98.07% | 24.03% | 70.46%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 |  | 690 | 0 | 770 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 0 | 0 | 384 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 |  | 599 | 0 | 679 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 0 | 0 | 325 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
| 0 | 0 | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
| 0 | 0 | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/UK-SouthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
| 0 | 0 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
| 0 | 0 | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes