## Resource & Narrative
Year | 2021 | Area | ATLAS
Quarter | Q2 | Reporter | JW |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Task 1 | Decommisioning of Storage for Oxford
Task 2
Risks
Type | Risk |  |  | Mitigation
General | Covid site access restrictions and relaed issues |  |  | Site access plans; planned resiliance
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Ongoing | To configure Third-party-copy using http for ECHO |  |  | To run successfully in DOMA smoke and stress tests
End of Quarter | To configure Third-party-copy using http for ECHO |  |  | To run successfully in DOMA smoke and stress tests
Ongoing | Chair ATLAS UK Cloud support meetings and help UK Cloud Squad.
Ongoing | Response to operational issues at RAL-Tier1.
Ongoing | To configure Third-party-copy using http for ECHO |  |  | To enable TPC via WebDev in production
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 1 | 95% | 5% | 91.2% | MCT | T1 Job success rates from ATLAS dashboard (site-only metrics) |  |  | Metric OK | MOK
2 | 2 | 98% | 5% | 99.09% | MOK | T1 Data availability from the ATLAS dashboard (from Monit-Grafana Panda) |  |  | Metric Clost to Target | MCT
2 | 3 | 98% | 5% | 94.8% | MCT | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests (from WLCG SiteMon) | QMUL shows lower availaibility and acceptance in this period |  | Metric not OK | MFL
2 | 4 | 95% | 5% | 96.42% | MOK | T1 Production job success rates (site only metrics) - from PANDA dashboard |  |  | Metric with no Target | MNO
2 | 5 | 95% | 5% | 97.92% | MOK | Data availability from the ATLAS dashboard; (from Monit-Grafana Panda)
2 | 6 | 95% | 5% | 97.22% | MOK | Data acceptance at Tier-2s (from Monit-Grafana Panda)
2 | 7 | 5% | 1% | 0.2% | MOK | Data loss at Tier-2s
2 | 8 | 95% | 5% | 93.81% | MCT | Atlas job success in production
2 | 9 | 95% | 5% | 87.2% | MFL | ATLAS job success rates in user analysis | RAL, LANCS and ECDF contribute the lower than expected success rates in the Quarter. Vector Read work for RAL will help, as will new disk servers at Lancaster.
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes