## Resource & Narrative
Year | 2021 | Area | CMS
Quarter | Q2 | Reporter | KE |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Tier 1 | Much improved job failure rate, although this is likely related to the observation that many fewer jobs are accessing data offsite. |  |  | Ongoing problems with job efficiency.
Tier 2s |  |  |  | Need to keep an eye on the reduction of CMS jobs running in Q2 compared with Q1
Risks
Type | Risk |  |  | Mitigation
General | Poor offsite read performance |  |  | New network bypassing firewall should help this.
Area Specifc | Vector read functionality being developed at RAL for the Tier 1 jobs reading from Echo disk, may never work |  |  | TBD
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [11 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 10 |  | 5% | N/A | MOK | Tier-1 Data Transfer Quality | No major problems for site to site transfers. Tape pledge was full throughout Q2 so there have not been writes there. | [5 empty] | Metric OK | MOK
2 | 11 | 5% or pledge | 5% | 9.6% | #VALUE! | Timely and efficient availability and use of resources at RAL T1 (Global %) | A short period at the start of the quarter below pledge (before coming out of drain) but compensated with periods well above pledge. RAL ran 9.6% of Completed T1 jobs. | [5 empty] | Metric Clost to Target | MCT
2 | 12 | 70% | 5% | 40.6% | MFL | Tier-1 Average CPU Efficiency | Back into the 'normal' zone. But still 25-35 percentage points below any other T1 for the same period. Mostly onsite reads during this period. | [5 empty] | Metric not OK | MFL
2 | 13 | 10% | 5% | 13% | MFL | Tier-1 Failure Rate | Much improved failure rate compared to recent quarters. Other T1s are at 10% or less, but if LogCollect are taken into account (29% of all failures this quarter) then RAL is in line with these, and this should be orange, if not nearly green. | [5 empty] | Metric with no Target | MNO
2 | 14 | 97% | 5% | 100% | MOK | Site availability at the Tier-1 | WLCG Sitemon - 99% April, 100% May, 100% June
2 | 15 | 5% | 5% |  | AWI | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | There is currently no way to access this information.
2 | 16 | 0% | 1% | 0% | MOK | Custodial Data Loss at Tier-1 | None
2 | 17 |  | 5% | N/A | MOK | Transfer rates to the UK Tier 2s | No major problems
2 | 18 | 80% | 5% | 93% | MOK | Site availability at the Tier-2s | IC - 100/100/100%, Brunel - 96% (99/99/91%), RALPP - 84% (100/83/69%). Source e.g.: https://monit-wlcg-sitemon.web.cern.ch/monit-wlcg-sitemon/reports/2021/202104/wlcg/WLCG_All_Sites_CMS_Apr2021.pdf
2 | 19 | 80% | 5% | 93% | MOK | Site reliability at the Tier-2s | As above
2 | 20 | 0% | 5% | 0% | MOK | Unique data loss at Tier-2s | None
2 | 21 | 30% | 5% | 20% | MOK | Failed analysis jobs | About 20% failure rate for analysis jobs, which is an improvement on last quarter
2 | 22 | 20% | 5% | 10% | MOK | Failed production jobs | <10% failure rate for production jobs, which is the better than last quarter
2 | 23 | 5% | 5% | 3.8% | MOK | T2 sites provide an appropriate level of resource to CMS | UK sites provided CPU to complete 3.8% of CMS T2 jobs (should this really be green?) UK number is lower than Q1, and the overall provision of T2s is a little higher due to increase at CERN.
2 | 24 | 80% | 5% |  | AWI | Job performance/efficiency using AAA data transfer | There is currently no way to access this information.
Milestones | [11 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 5 | 2020-12-01 | Y | 2020-12-01 | MSA | Report on delivery to CMS during year | [6 empty] | Milestone Achieved | MSA
2 | 6 | 2021-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Ongoing | MOG
2 | 7 | 2022-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Overdue | MOD
2 | 8 | 2023-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone not due | MSU
2 | 17 | 2020-10-01 | Y | 2020-10-01 | MSA | Review of CMS AAA Efficiency
2 | 18 | 2021-04-01 | S |  | MSU | Review of CMS AAA Efficiency | Milestone Suspended - work on Tier-1 CMS efficiency is an ongoing evalation of multiple aspects of CMS efficiency, including AAA, and depositions from the CMS reps are that it is impossible/unfeasible to measure "AAA efficiency" as a single entity. (See Metric 2:24)
2 | 19 | 2021-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 20 | 2022-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 21 | 2022-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 22 | 2023-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 23 | 2023-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 24 | 2024-04-01 | N |  | MSU | Review of CMS AAA Efficiency
Site availability
[7 empty] | Site | Jan | Feb | Mar | Avg
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333
Site reliability
[7 empty] | Site | Jan | Feb | Mar
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes