## Resource & Narrative
Year | 2021 | Area | LHCb
Quarter | Q2 | Reporter | RN |  | Approved | AMcN
Narrative
Area | Successes |  |  | Problems
Task 1 | 1. xroot v5 upgrade went smoothly. 2. Very good communication with Tier-1 staff (outside of management) |  |  | 1. Ongoing streaming issue from ECHO at RAL. Suggested timescales until now have all slipped. 2. Possible corruption of data issue at RAL. Proximate cause now understood though the cause of actual failure is still unknown. 3. Issue extracting checksums from ECHO using xrootd protocol (was supposed to just “work”) – still a Work In Progress 4. Possible problems with the CEs / batch system which had large variations in number of LHCb running jobs. This has settled down for now but the recent number of LHCb jobs is quite low.
Task 2 | Very good communication with Tier-2 sites |  |  | LHCb’s implementation of multi-core pilots started off with a few issues at many sites. Hopefully the bulk of these problems have been ironed out. No jobs were running at Vac sites. Thanks to Mark Slater picking up on supporting Vac at Birmingham and Glasgow, the Vac technology seems to have a second life now
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc | Networking to various university sites |  |  | Investment in networking?
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 25 | 90% | 5% | 81.6% | MFL | Tier-1 prod CPU efficiency | In line with previous numbers Note that this is jobs not including simulation |  | Metric OK | MOK
2 | 26 | 50% | 5% | 80.8% | MOK | Tier-1 user success rate |  |  | Metric Clost to Target | MCT
2 | 27 | 70% | 5% | 82.1% | MOK | Tier-1 user CPU efficiency |  |  | Metric not OK | MFL
2 | 28 | 15% | 5% | 19.4% | MOK | UK Tier-1 work fraction |  |  | Metric with no Target | MNO
2 | 29 | 50% | 5% | 75.6% | MOK | Tier-2A : User success rate
2 | 30 | 70% | 5% | 89.7% | MOK | Tier-2A : User CPU efficiency
2 | 31 | 90% | 5% | 82.9% | MFL | All Tier-2: Simulation success rate | LHCb operational error in early June caused MC simulation job failures across the grid. It was not helped by a new major DIRAC release at the same time which obscured the issue.
2 | 32 | 90% | 5% | 98.6% | MOK | All Tier-2: Simulation CPU efficiency
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N | 2020-11-01 | MSA | Report on delivery to LHCb during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes