## Resource & Narrative
Year | 2021 | Area | Security
Quarter | Q2 | Reporter | DK / DC
Narrative
Area | Successes |  |  | Problems
Operations | Start of EGI-ACE + EOSC Future. Review of information gathering procedure for site response to vulnerability advisories resulted in markedly improved response rates. Ongoing review of backup duty tasks to include monitoring of this status, consider rota tasks more broadly across IRIS in the future. Participation in ongoing development of global incident response. |  |  | Sussex Tier-2 not responding to requests for information on vulnerability response; flagged for follow-up Low resource use this quarter due to sick leave, expected to balance over the course of the year
Trust & Identity | Discussion of EGI Policy on the Processing of Personal Data in context of proper addressing of GDPR; decision to update old policy wording. SIG-ISM/WISE Workshop in May. EUGridPMA meeting in June, identifying future of host certificates as key dsicussion for this year. Ongoing collaboration with IRIS IAM important for assurance discussions across many infrastructures. |  |  | none
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 100% | MOK | % of Sites responding to security communication requests | n/a in this period |  | Metric OK | MOK
3 | 3 | 95% | 5% | 94% | MCT | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | 1 CRITICAL advisory; 1 Tier-2 did not respond to request for information Site flagged for follow-up to understand situation (Note for metrics: with 16 production Tier-2s, 1 site not responding makes this amber, should we consider revising the bands for this one?) |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | n/a in this period |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N | 2020-07-01 | MSA | GridPP-wide security training event | IRIS Security Workshop held at end of July 2020
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | Y | 2021-04-01 | MSA | Review WLCG security policy and procedure set | Review available on request. Milestone now completed (July 2021). This was 3 months late because of conflict with other activities.
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
2020-11-03 | EGI Conference, "Developing a Trust and Security Framework for IRIS", D Crooks
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes