## Resource & Narrative
Year | 2021 | Area | Federal Services
Quarter | Q2 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
GOCDB | Working with the relevant team at RAL, a workaround to the load balancer issues previously reported was deployed. Since then, GOCDB has not experienced the short network blips previously described. Started to add IRIS specific sites to the IRIS view of GOCDB |  |  | RAL networking problems around 22nd April led to small downtimes (4 min) of GOCDB and an at risk overnight
Accounting - APEL and IRIS Dashboard
Workflow Management - DIRAC | Stable running. We participate in the weekly (technical) DIRAC meetings/hackathons to ensure that up and coming DIRAC updates are compatible with our system and we continue to contribute bug fixes. Simon F is still the release manager for VMDirac (Cloud Interface). We have deployed the next major version of DIRAC on our preprod server and are working with the DIRAC developers to make it compatible with the GridPP setup.
Data Management - Rucio and FTS | Tim Noble has established himself as the Rucio service owner and established a prototype data lake with 6 UK sites. |  |  | Problems remain with transfers from multiple VOs using the incorrect X509 certificate when submitting transfers.
CVMFS Service | Stable running. Some improvements have been made to the Access Control Lists |  |  | Haven't managed to onboard the service with EOSC.
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-12-31 | Migrate the Stratum 1 servers off their current hardware. Ideally as VMs using S3 backend.
2021-09-30 | Upgrade the Rucio instance at RAL to 1.26

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
3 | 1 | 99% | 2% | 99.95% | MOK | GOCDB Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-GOCDB?start_date=2021-04-01&end_date=2021-06-30 |  | Metric OK | MOK
3 | 2 | 0.5 | 0.1 | 1.84 | MOK | GOCDB Usage | Average Number of Concurrent GOCDB sessions https://vande.gridpp.rl.ac.uk/next/d/Vg3-GCXMk/gocdb-longer-term-host-metrics?orgId=1&from=1617231600000&to=1625093999000 |  | Metric Clost to Target | MCT
3 | 3 | 99% | 2% | 100% | MOK | APEL Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-APEL?start_date=2021-04-01&end_date=2021-06-30 |  | Metric not OK | MFL
3 | 4 | 1 | 0.2 | 1.2 | MOK | APEL Usage | Millions of messages processed in the quarter. |  | Metric with no Target | MNO
3 | 5 | 97% | 2% | 100% | MOK | Workflow Management (DIRAC) Availability
3 | 6 | 5 | 2 | 10 | MOK | Workflow Management (DIRAC) Usage | Measured as number of active VO (>2000 jobs in the quarter)
3 | 7 | 99% | 2% | 100% | MOK | Data Management (FTS + Rucio) Availability | Only measuring FTS service availability currently
3 | 8 | 3 | 1 | 2 | MCT | Data Management (FTS + Rucio) Usage
3 | 9 | 99% | 2% | 99.95% | MOK | CVMFS Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-CVMFS?start_date=2021-04-01&end_date=2021-06-30
3 | 10 |  |  | 44 | MOK | CVMFS Usage | Measured as number of active repositories
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
|  |  | N |  | MSU |  |  |  | Milestone Achieved | MSA
|  |  | N |  | MSU |  |  |  | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes