## Resource & Narrative
Year | 2021 | Area | Tier-1
Quarter | Q3 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
Tape System (Castor) | Castor was upgraded for the (hopefully) final time. This was to allow the database to migrate to CTA. CTA cluster has been deployed and is being used for internal testing.
Disk (Echo) |  |  |  | Long running problem with LHCb claiming their analysis jobs not being able to access their data correctly.
Batch System | New hardware from 2020 procurement entered production. Ongoing software updates to batch farm. |  |  | Problems with CPU accounting since April have meant that we show a much lower efficiency than we should.
Network | Deplyoment of new network ongoing. CTA has been connected to the super spine. |  |  | Problems with (primarily) CMS jobs accessing offsite data through the firewall are reducing job efficiency.
Other
Risks
Type | Risk |  |  | Mitigation
General | Access to the machine room has been reduced as a result of he Covid-19 restrictions. |  |  | Organising interventions more carefully and postpone non-essential work.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-03-31 | Delivery of this years hardware procurements |  |  | Entered production in August
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [8 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Notes | Colour | Description | Code
1a | 1 | 100% | 5% | 131.7% | MOK | % of GridPP commitment for CPU |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric OK | MOK
1a | 2 | 100% | 5% | 92% | MFL | % of GridPP commitment for Disk | The delay in deploying this years disk procurement is not affecting our ability to deliver as many non-LHC VOs are not using their allocation. | Calculated from Allocations.xlsx using [Total Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric Clost to Target | MCT
1a | 3 | 100% | 5% | 106% | MOK | % of GridPP allocation for Tape |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. Note the Total Commitment is lower than the total request because we buy Tape when required. |  | Metric not OK | MFL
1a | 4 | 94% | 5% | 101.9% | MOK | % of GridPP6 Staff funded |  |  |  | Metric with no Target | MNO
1a | 5 | 98% | 3% | 96% | MCT | WLCG Service Availability for Alice | Consistently 96%, still investigating why. | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/09-21/WLCG_Tier1_History_ALICE_Sep2021.pdf
1a | 6 | 98% | 3% | 98.67% | MOK | WLCG Service Availability for ATLAS | 4% availability drop in August due to Site Network intervention. | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/09-21/WLCG_Tier1_History_ATLAS_Sep2021.pdf
1a | 7 | 98% | 3% | 96.33% | MCT | WLCG Service Availability for CMS | 8% availability drop in August due to Site Network intervention. | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/09-21/WLCG_Tier1_History_CMS_Sep2021.pdf
1a | 8 | 98% | 3% | 99.33% | MOK | WLCG Service Availability for LHCB | 2% availability loss in August due to Site Network intervention. | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2021/09-21/WLCG_Tier1_History_LHCB_Sep2021.pdf
1a | 9 | 90% | 20% | 73.32% | MCT | % usage by ATLAS of their CPU pledge | ATLAS have been wanting to run a large number of single core jobs when previously they wanted multi-core. Low numbers in Jul/Aug, usage ramping back up in September. | ATLAS Pledge = 173160 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/7/2021/9/lhc/onlyinfrajobs/
1a | 10 | 80% | 20% | 96.61% | MOK | % usage by ATLAS of their Disk pledge |  | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-09-30.json
1a | 11 | 80% | 20% | 87.64% | MOK | % usage by ATLAS of their Tape pledge |  | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30092021
1a | 12 | 90% | 20% | 219.3% | MOK | % usage by CMS of their CPU pledge |  | CMS Pledge = 52000HS06 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/7/2021/9/lhc/onlyinfrajobs/
1a | 13 | 80% | 20% | 95.39% | MOK | % usage by CMS of their Disk pledge |  | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-09-30.json
1a | 14 | 80% | 20% | 99.46% | MOK | % usage by CMS of their Tape pledge |  | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30092021
1a | 15 | 90% | 20% | 71.79% | MCT | % usage by LHCb of their CPU pledge | Significant increase compared to Q2. | LHCb Pledge = 135464 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/7/2021/9/lhc/onlyinfrajobs/
1a | 16 | 80% | 20% | 79.37% | MCT | % usage by LHCb of their Disk pledge | Significant increase compared to Q2. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-09-30.json
1a | 17 | 80% | 20% | 74.22% | MCT | % usage by LHCb of their Tape pledge | Significant increase compared to Q2. | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30092021
1a | 18 | 90% | 20% | 77.98% | MCT | % usage by ALICE of their CPU pledge | Significant increase compared to Q2. | ALICE Pledge = 14940 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/7/2021/9/lhc/onlyinfrajobs/
1a | 19 | 80% | 20% | 38.87% | MFL | % usage by ALICE of their Disk pledge | We are working with ALICE to ensure that they can make full use of their storage. There have been problems with the authentication for their Third Party Transfers. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-09-30.json
1a | 20 | 80% | 20% | 51.58% | MFL | % usage by ALICE of their Tape pledge | ALICE have not been writing to tape during the long shutdown. | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30092021
1a | 21 | 40% | 30% | 22.84% | MCT | % usage by non-LHC VOs of their CPU allocation |  | Total Pledge * 0.13 = 48823 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2021/07/2021/09/custom-biomed,dune,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 22 | 80% | 20% | 95.5% | MOK | % usage by non-LHC VOs of their Disk allocation | Currently only Dune using Echo | https://s3.echo.stfc.ac.uk/srr/storagesummary_2021-09-30.json
1a | 23 | 80% | 20% | 165.2% | MOK | % usage by non-LHC VOs of their Tape allocation |  | Total Pledge * 0.1 = 7177TB Usage calculated from printTapeUsage.py
1a | 24 | 90% | 10% | 90% | MOK | GridPP Funded Farm Occupancy |  | https://vande.gridpp.rl.ac.uk/next/d/3NOsnhnMz/batch-system-capacity?orgId=1&from=1625094000000&to=1633042799000&viewPanel=3
1a | 25 | 80% | 10% | 92% | MOK | % Total DIsk Usage |  | ResourceUsage spreadsheet
1a | 26 | 80% | 10% | 96% | MOK | % Total Tape Usage |  | ResourceUsage spreadsheet
1a | 27 | 70% | 20% | 88.49% | MOK | % Job Efficiency (CPU/Wall) - ATLAS | Estimated based on a subset of total data from internal HTCondor database. | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2021/07/2021/09/lhc/onlyinfrajobs/
1a | 28 | 70% | 20% | 53.03% | MCT | % Job Efficiency (CPU/Wall) - CMS | Significantly better than previous quarter. Full impact of network improvements have not yet been realised. | See Above
1a | 29 | 70% | 20% | 108% | MOK | % Job Efficiency (CPU/Wall) - LHCb |  | See Above
1a | 30 | 70% | 20% | 86.57% | MOK | % Job Efficiency (CPU/Wall) - ALICE |  | See Above
1a | 31 | 70% | 20% | 67.32% | MCT | % Job Efficiency (CPU/Wall) - non-LHC | Dune ran 76% of jobs with an efficiency of 57.11%. | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2021/07/2021/09/custom-biomed,dune,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 32 | 95% | 5% | 95.65% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ATLAS |  | https://accounting.egi.eu/tier1/cpueff/VO/TIER1/2021/07/2021/09/lhc/onlyinfrajobs/
1a | 33 | 95% | 5% | 77.54% | MFL | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - CMS | Significant improvement compared to last quarter. | See Above
1a | 34 | 95% | 5% | 108.9% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - LHCb |  | See Above
1a | 35 | 95% | 5% | 105.2% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ALICE |  | See Above
1a | 36 | 100% | 5% | 100% | MOK | % of GGUS Tickets Handled |  | https://ggus.eu/index.php?mode=ticket_search&su_hierarchy=0&status=all&affectedsite=RAL-LCG2&date_type=creation+date&timeframe=lastweek&tf_radio=2&from_date=01+Jul+2020&to_date=30+Sep+2020&ticket_category=all&typeofproblem=all&specattrib=none&orderticketsby=REQUEST_ID&orderhow=desc&ticket_per_page=50&show_columns_check%5B0%5D=TICKET_TYPE&show_columns_check%5B1%5D=AFFECTED_VO&show_columns_check%5B2%5D=AFFECTED_SITE&show_columns_check%5B3%5D=PRIORITY&show_columns_check%5B4%5D=RESPONSIBLE_UNIT&show_columns_check%5B5%5D=STATUS&show_columns_check%5B6%5D=DATE_OF_CHANGE&show_columns_check%5B7%5D=SHORT_DESCRIPTION&show_columns_check%5B8%5D=SCOPE&search_submit=Search
1a | 37 | 30 | 10 | 6 | MOK | Average number of security vunerabilities |  | https://install02.gridpp.rl.ac.uk/pakiti/ Take Average Security in gridpp.rl.ac.uk domain
Milestones | [8 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Comments | Colour | Description | Code
1a | 1 | 2020-11-01 | N |  | MSU | GridPP review of operation (biennial) | Cancelled because of Pandemic |  |  | Milestone Achieved | MSA
1a | 2 | 2022-10-01 | N |  | MSU | GridPP review of operation (biennial) |  |  |  | Milestone Ongoing | MOG
1a | 3 | 2020-06-01 | 2020-04-01 | 2020-06-01 | MSA | Produce the purchasing plan |  |  |  | Milestone Overdue | MOD
1a | 4 | 2020-11-01 | 2020-09-01 | 2020-09-01 | MSA | FY20 Capacity order placed |  |  |  | Milestone not due | MSU
1a | 5 | 2021-04-01 | 2021-01-01 | 2021-07-01 | MOD | FY20 Purchase in production | Expected to enter production in June 21
1a | 6 | 2021-04-01 | 2021-04-01 | 2021-04-01 | MSA | Tier-1 WLCG MoU commitments met
1a | 7 | 2021-06-01 | 2021-05-01 | 2021-06-01 | MSA | Produce the purchasing plan
1a | 8 | 2021-11-01 | 2021-06-01 | 2021-08-01 | MSA | FY21 Capacity order placed
1a | 9 | 2022-04-01 | N |  | MSU | FY21 Purchase in production
1a | 10 | 2022-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 11 | 2022-06-01 | N |  | MSU | Produce the purchasing plan
1a | 12 | 2022-11-01 | N |  | MSU | FY22 Capacity order placed
1a | 13 | 2023-04-01 | N |  | MSU | FY22 Purchase in production
1a | 14 | 2023-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 15 | 2023-06-01 | N |  | MSU | Produce the purchasing plan
1a | 16 | 2023-11-01 | N |  | MSU | FY23 Capacity order placed
1a | 17 | 2024-04-01 | N |  | MSU | FY23 Purchase in production
1a | 18 | 2024-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
2021-08-01 | Designing the RAL Tier-1 Network for HL-LHC and Future data lakes, https://doi.org/10.1051/epjconf/202125102074
2021-08-01 | Public Engagement in a Global Pandemic, https://doi.org/10.1051/epjconf/202125101005
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes