## Resource & Narrative
Year | 2021 | Area | LondonGrid
Quarter | Q3 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel | I've started the migration out of DOME. Plan: (0) Build a CEPHFS system - Concluded in a couple of weeks, when we'll have the last hardware delivered. (1) Build an XrootD gateway. - Work plan for December. We have 1500 cores to add to Compute nodes. 25G network for them should available before end of the year. Those are node bought with Brunnel's money. No GridPP funding.
Imperial | Working on upgrading dCache to CentOS8 from CentOS7 Backfilling IRIS Openstack cluster with grid jobs
QMUL | Put 8 GPU nodes online (16 Nvidia A100 GPUa) and available for use. In contact with DUNE/Atlas etc.. to get them integrated into their systems. Put online another 30 nodes (40,000 HepSpec), now have over 9000 job slots. Almost finished Tender process for new Storage, awaiting official approval from Procurement to announce winner, Should be able to buy approx 10PB online storage. Updated the storage accounting to use Project Lustre quotas, Online storage reporting is now accurate to within 20mins https://se03.esc.qmul.ac.uk:8443/info/report.json Have agreed a plan for the refurbishment for the Data Centre and have obtained funding to provide 390KW of cooling to the room. This will enable future growth beyond the 260 KW of Equipment already in the room Tender documents are being drawn up.
RHUL | Migration to C7 almost done. Only one service left (argus) System security patches applied in August. Problem with master02 disk. Mounted FS for argus was missing for a short time. |  |  | Some intermittent problems with switches. Intermittent problems with httpd services in DPM data nodes
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL
RHUL | WAN connection to Janet, currently 10 Gb/s, is insufficient for site to operate effectively as non-storage site
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 315.6% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 203% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 76.63% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 98.98% | MOK | Average Argo Availability - LondonGrid | Excellent availability |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 98.98% | MOK | Average Argo Reliability - LondonGrid | Excellent reliability

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 52831 | 114000 | 112500 | 56000 | 335331 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 20152 | 29377 | 22055 | 34668 | 106252 | (plus 10% here for Other Vos)
% of Pledge | 262.2% | 388.1% | 510.1% | 161.5% | 315.6%
Storage Available (TB) | 1200 | 12000 | 5100 | 1300 | 19600
Storage Pledged (TB) | 1016 | 3412 | 5225 | 0 | 9653
% of Pledge | 118.1% | 351.7% | 97.61% | #DIV/0! | 203%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 98.55 | 99.76 | 97.31 | 100 | 98.91% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 99.57 | 94.48 | 100 | 98.51% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 99.17 | 99.72 | 99.18 | 99.52%
% Tier-2 Averge | 99.5167 | 99.5 | 97.17 | 99.7267 | 98.98%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 98.55 | 99.76 | 97.31 | 100 | 98.91% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 99.57 | 94.48 | 100 | 98.51% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 99.17 | 99.72 | 99.18 | 99.52%
% Tier-2 Total | 99.5167 | 99.5 | 97.17 | 99.7267 | 98.98%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 116650848 | 251712000 | 248400000 | 123648000 | 740410848 | https://accounting.egi.eu/tier2/federation/London Tier 2/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 18217013.98 | 59722405.9311 | 49880155.294 | 29812638.9112 | 157632214.1163 | Q1: 2160/2184 (if leap year)
Month 2 | 17321974.0618 | 60729086.853 | 65807361.0066 | 28687620.0388 | 172546041.9602 | Q2: 2184
Month 3 | 19119335.8189 | 50558412.5054 | 61082034.7504 | 32396948.7641 | 163156731.8388 | Q3: 2208
Total: | 54658323.8607 | 171009905.2895 | 176769551.051 | 90897207.7141 | 493334987.9153 | Q4: 2208
% Utilisation | 46.86% | 67.94% | 71.16% | 73.51% | 66.63%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 116650848 | 251712000 | 248400000 | 123648000 | 740410848 | https://accounting.egi.eu/tier2/federation/London Tier 2/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 25397094.303 | 73965388.9063 | 47804101.1287 | 32967788.2918 | 180134372.6298 | Q1: 2160/2184 (if leap year)
Month 2 | 24228919.6305 | 78744706.5668 | 63493454.8375 | 31563142.1943 | 198030223.2291 | Q2: 2184
Month 3 | 27119590.6109 | 64759497.5724 | 62920041.6064 | 34398557.4167 | 189197687.2064 | Q3: 2208
Total: | 76745604.5444 | 217469593.0455 | 174217597.5726 | 98929487.9028 | 567362283.0653 | Q4: 2208
% Utilisation | 65.79% | 86.4% | 70.14% | 80.01% | 76.63%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 32.98 | 0 | 4400 | 1055 | 5487.98 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1429.36 | 5379.498 | 0 | 2.2 | 6811.058 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0.053 | 614.915 | 300 | 0 | 914.968
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1204 | 0 | 0 | 1204
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 32 | 0 | 3570 | 784.36 | 4386.36 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 1230 | 3055.731 | 0 | 1.57 | 4287.301 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 454 | 221 | 0 | 675
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 673.6 | 0 | 0 | 673.6
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0.35 | 0 | 0 | 0 | 0.35 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 39.355 | 0 | 0 | 39.355 | https://accounting.egi.eu/tier2/federation/London Tier 2/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
dune | 0 | 0 | 11 | 0 | 11 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0.5 | 0 | 0.069 | 0.006 | 0.575 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.811 | 0.169 | 0 | 77.98
lz | 0 | 1411.185 | 0 | 0 | 1411.185
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.009 | 0.02 | 0.037
skatelescope.eu | 0 | 0.05 | 0.219 | 0 | 0.269
snoplus.snolab.ca | 0 | 0 | 10.4 | 0 | 10.4
solidexperiment.org | 0 | 567.887 | 0 | 0 | 567.887
t2k.org | 0 | 46.437 | 188.7 | 0 | 235.137
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0.25 | 0 | 0 | 0 | 0.25
mice | 9.6 | 0 | 0 | 0 | 9.6
vo.moedal.org | 0 | 0 | 1.35 | 0 | 1.35
fusion | 0 | 0 | 0 | 0.009 | 0.009
cernatschool.org | 0 | 0 | 0.072 | 0 | 0.072
hyperk.org | 0 | 0 | 0.595 | 0 | 0.595
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes