## Resource & Narrative
Year | 2021 | Area | NorthGrid
Quarter | Q2 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | Procured Equipment Steven joined the team Great strides made in CEPH experience |  |  | Delays in electrical work have meant delays in fully commissioning CEPH
Liverpool | Accounting publishing brought up to date on all Ces/SE. Kernel security updates applied during shutdown. All condor nodes and servers upgraded to latest 8.8 release. HTCondor CE upgraded to latest 3.4 release. ARC CE updated to 6.13, REST interface enabled. Node queues rationalised on all CEs to provide 4GB queue for LHCb. |  |  | Site emergency shutdown due to cooling failure in July, interruption less than a day Lots of disk failure replacements, all out of warranty. Older storage servers will be gradually drained and retired according to age/reliability.
Manchester
Sheffield | Mitch on leave at time report was requested, but Sheffield is working steadily and keeping up to date.
Risks
Type | Risk |  |  | Mitigation
Lancaster | DPM reliability is still a problem, made worse by a change of tack where we are not adding to it. Machine room work delayed, so new racks don’t have power. |  |  | Push CEPH deployment Continue gaining experience with test systems to hit the ground running.
Liverpool | Disk failure rate with aging kit |  |  | Shrinking storage to adapt, targetted retirements of faulty servers
Manchester
Sheffield
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-09-30 | Lancaster – New kit ordered and delivered. |  |  | More capacity, key CEPH infrastructure
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-12-14 | Lancaster - New CEPH cluster online and ready for testing. |  |  | Prepared to start testing and transitioning to CEPH

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% | 215% | MOK | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% | 130% | MOK | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% | 137% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 99% | MOK | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 99% | MOK | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 91995 | 35047 | 55829 | 11918 | 182871 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 30822 | 18990 | 25443 | 9652 | 84907 | (plus 10% here for other Vos)
% of Pledge | 298.5% | 184.6% | 219.4% | 123.5% | 215.4% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 3210 | 1424 | 6820 | 0 | 11454
Storage Pledged (TB) | 2825 | 330 | 5648 | 0 | 8803
% of Pledge | 113.6% | 431.5% | 120.8% | 100% | 130.1%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 98 | 99 | 100 | 100 | 99.25% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 98 | 100 | 100 | 93 | 97.75% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 100 | 96 | 99%
% Tier-2 Averge | 98.6667 | 99.6667 | 100 | 96.3333 | 98.67%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 98 | 99 | 100 | 100 | 99.25% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 98 | 100 | 100 | 93 | 97.75% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 100 | 100 | 100%
% Tier-2 Total | 98.6667 | 99.6667 | 100 | 97.6667 | 99%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 203124960 | 77383776 | 123270432 | 26314944 | 430094112 | https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 63329512 | 22162490 | 80644155 | 5067637 | 171203794 | Q1: 2160/2184 (if leap year)
Month 2 | 57568238 | 21180552 | 82787915 | 6704061 | 168240766 | Q2: 2184
Month 3 | 69179797 | 12727231 | 84771269 | 5637571 | 172315868 | Q3: 2208
Total: | 190077547 | 56070273 | 248203339 | 17409269 | 511760428 | Q4: 2208
% Utilisation | 93.58% | 72.46% | 201.3% | 66.16% | 119% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 203124960 | 77383776 | 123270432 | 26314944 | 430094112 | https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 83403063 | 24339151 | 88432269 | 6268539 | 202443022 | Q1: 2160/2184 (if leap year)
Month 2 | 78171171 | 22434556 | 86615432 | 7014340 | 194235499 | Q2: 2184
Month 3 | 84675840 | 13314736 | 87726607 | 5888275 | 191605458 | Q3: 2208
Total: | 246250074 | 60088443 | 262774308 | 19171154 | 588283979 | Q4: 2208
% Utilisation | 121.2% | 77.65% | 213.2% | 72.85% | 136.8%
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3160 | 970 |  |  | 4130 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 |  |  | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 313 |  |  | 313
Alice | 0 | 0 |  |  | 0
IRIS | 1060 | 0 | 0 | 0 | 1060
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 1750 | 860 |  |  | 2610 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 |  |  | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 224 |  |  | 224
Alice | 0 | 0 |  |  | 0
IRIS | 313 | 0 | 0 | 0 | 313
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 23.4 | 0 |  | 41.4 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 1.4 | 0.3 | 0 |  | 1.7 | https://accounting.egi.eu/tier2/federation/NorthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.5 | 0 |  | 2.5 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.1 | 0 |  | 0.1
gridpp | 0.001 | 0 | 0 |  | 0.001
lsst | 0 | 1 | 0 |  | 1
dune | 0 | 0.6 | 0 |  | 0.6
mu3e.org | 0 | 64 | 0 |  | 64
hyperk.org | 18 | 0 | 0 |  | 18
| 0 | 0 | 0 |  | 0
lsst (iris) | 91 | 0 | 0 |  | 91
dune (iris) | 48 | 0 | 0 |  | 48
vo.cta.in2p3.fr (iris) | 150 | 0 | 0 |  | 150
ska.telescope.eu (iris) | 0.04 | 0 | 0 |  | 0.04
0
0
0
0
0
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes