## Resource & Narrative
Year | 2021 | Area | ScotGrid
Quarter | Q2 | Reporter | SS
Narrative
Area | Successes |  |  | Problems
Durham | Nagios will "self-build" from puppet facts via exported resources. Puppet can retrieve the "Physical Rack" from Netbox, ensuring SNMP Locations are correct. For VM is marks it as a VM. |  |  | Nodes continue to go Read Only due to failing hard disks, repaired as they happen but they have caused issues to site reliability.
Edinburgh | Internal site XCache continues to surprise in reducing the traffic and load on the site storage significantly. Load on site storage has also been re-balanced using new site-specific tools. |  |  | Site A/R continues to be impacted by various outages within the university infrastructure. Mitigations have been applied to improve site availability as best possible.
Glasgow | Gordon Stewart assumed the post of ScotGrid Technical Co-ordinator on 1st August.
Risks
Type | Risk |  |  | Mitigation
Durham | Local COVID restrictions means 2 man working is advised against. Some issues may not be resolved if it requires a 2 man team. General access is also restricted and so issues may take longer to resolve. |  |  | Just be patient.
Edinburgh | Additional loss of expertise due to staff leaving. Some work now has a bus factor of <=1 due to Covid. No clear picture of networking at site. |  |  | More documentation needed across the site to avoid missing knowledge gaps building up. Have comissioned additional services to supplement this to avoid A/R falling too low. Aim to work closer with university admins to better understand current systems better.
Glasgow | COVID and other delays mean migration to new DC is delayed. |  |  | Focus on running both batch farms and storage pools for as long as possible.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Durham: Shared Fail2Ban Production Ready |  |  | Waiting on Durham COSMA/DiRAC HPC and Durham ARC for our first "production" installs to finalise documentation.
| Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | Only need a el8 build which is on hold until an el8 solution is finalised.
| Durham: Join monitoring systems together, rebuild nagios. Make puppet maintain it. |  |  | Successfull, some minor changes required for service definitinons.
Glasgow: provision and commission new storage hardware in data centre
Glasgow: make progress with tranche procurement
| Edinburgh: Setup RUCIO inside Kubernetes at Edinburgh which supports GridPP. |  |  | This was delayed due to problems discovered in attempting to migrate from kubernetes "proof-of-concept" to "production" specifically with container networking.
| Edinburgh: Migrate Tier2 CO8 resources to Alma Linux |  |  | CO8 installs will be supported beyond Q4-2021. Stalled due to other issues/outages.
| Edinburgh: Navigate coming university security policy changes for remote access. |  |  | Still be able to access GridPP reources for administration remotely as university changes security policy and firewall configs.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Durham: Shared Fail2Ban Production Ready |  |  | Waiting on Durham COSMA/DiRAC HPC and Durham ARC for our first "production" installs to finalise documentation.
| Durham: Continue to replace node hard drives as they fail. |  |  | No more read only nodes due to failed hard drives.
| Edinburgh: Further improve site service monitoring by improving FluentD usage. |  |  | Documentation on using OpenSearch and FluentD for site monitoring
| Edinburgh: Finish CentOS8 migration |  |  | CO8 installs will be supported beyond Q4-2021.
| Edinburgh: Make/provide additional documentation of XCache setup |  |  | More resources for other sites looking to make use of XCache

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 3 | 100% | 5% | 223.1% | MOK | % of WLCG Pledged CPU Available - ScotGrid |  |  | Metric OK | MOK
1b | 7 | 100% | 5% | 0% | MFL | % of WLCG Pledged Disk Available - ScotGrid |  |  | Metric Clost to Target | MCT
1b | 11 | 50% | 5% | 149.5% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid |  |  | Metric not OK | MFL
1b | 17 | 95% | 5% | 96.07% | MOK | Average Argo Availability - ScotGrid |  |  | Metric with no Target | MNO
1b | 18 | 95% | 5% | 96.07% | MOK | Average Argo Reliability - ScotGrid

## Resources
Please fill in all fields highlighed in
Capacities | Durham | Edinburgh | Glasgow | Total | Notes
CPU Available (HS06) |  |  | 155875 | 155875 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 38034 | 5647 | 26190 | 69871 | (plus 10% for other Vos)
% of Pledge | 0% | 0% | 595.2% | 223.1%
Storage Available (TB) |  |  |  | 0
Storage Pledged (TB) | 0 | 0 | 4074 | 4074
% of Pledge | #DIV/0! | #DIV/0! | 0% | 0%
Availability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 94.03 | 99.24 | 100 | 97.76% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 99.04 | 99.83 | 73.01 | 90.63% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.9 | 99.58 | 100 | 99.83%
% Tier-2 Averge | 97.6567 | 99.55 | 91.0033 | 96.07%
Reliability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 94.03 | 99.24 | 100 | 97.76% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 99.04 | 99.83 | 73.01 | 90.63% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.9 | 99.58 | 100 | 99.83%
% Tier-2 Total | 97.6567 | 99.55 | 91.0033 | 96.07%
CPU Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 0 | 0 | 344172000 | 344172000 | https://accounting.egi.eu/tier2/federation/ScotGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 56772468 | 10576408 | 72677840 | 140026716 | Q1: 2160/2184 (if leap year)
Month 2 | 66081946 | 12858165 | 70313854 | 149253965 | Q2: 2184
Month 3 | 66208908 | 18454237 | 87491439 | 172154584 | Q3: 2208
Total: | 189063322 | 41888810 | 230483133 | 461435265 | Q4: 2208
% Utilisation | #DIV/0! | #DIV/0! | 66.97% | 134.1% | ECDF cloud reporting missing for Q2, numbers have been requested from uVic but no reply as of 01/08/21
WallClock Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 0 | 0 | 344172000 | 344172000 | https://accounting.egi.eu/tier2/federation/ScotGrid/normelap_processors/SITE/DATE/2021/1/2020/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 55812713 | 14322208 | 99714208 | 169849129 | Q1: 2160/2184 (if leap year)
Month 2 | 64470485 | 19162526 | 81213715 | 164846726 | Q2: 2184
Month 3 | 66558479 | 20907035 | 92357119 | 179822633 | Q3: 2208
Total: | 186841677 | 54391769 | 273285042 | 514518488 | Q4: 2208
% Utilisation | #DIV/0! | #DIV/0! | 79.4% | 149.5% | ECDF cloud wallclock = (1.046 * CPU hours based on historical performance)
Storage LHC & IRIS: AVAILABLE (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 265 | 750 | 4200 | 5215 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 300 | 300
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 235 | 699.14 | 1760 | 2694.14 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 1 | 1 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 72 | 72
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
biomed | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
cernatschool.org | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/ScotGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
clas12 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
comet.j-parc.jp | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dune | 0 | 0 | 0 | 0
gridpp | 0 | 1 | 2 | 3
hyperk.org | 0 | 0 | 0 | 0
ilc | 0 | 0 | 0 | 0
iris.ac.uk | 0 | 0 | 0 | 0
lhcb | 0 | 0 | 0 | 0
lsst | 0 | 0 | 0 | 0
lz | 0 | 0 | 0 | 0
magrid | 0 | 0 | 0 | 0
mice | 0 | 0 | 1.9 | 1.9
na62.vo.gridpp.ac.uk | 0 | 0 | 3.8 | 3.8
ops | 0 | 0 | 0 | 0
pheno | 66 | 0 | 7.5 | 73.5
skatelescope.eu | 0 | 0 | 0 | 0
snoplus.snolab.ca | 0 | 0 | 0 | 0
solidexperiment.org | 0 | 0 | 0 | 0
t2k.org | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 0 | 0
vo.northgrid.ac.uk | 0 | 0 | 0 | 0
vo.scotgrid.ac.uk | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Ongoing | LSST, Escape, astro | Rob assisting astro people in Edinburgh with grid usage.
Ongoing | LZ | ECDF aiding in moving some workloads to the Grid.
Ongoing | DUNE | Provided effort into DUNE RUCIO deployment and data management
Ongoing | Imaging Centre of Excellence / Glasgow Uni / NHS | Durham - Provided support to Jon Trinder to get a Shared Fail2Ban instace installed on their systems, working with Jon to improve some of the codebase and iron out pre-production bugs.
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
2021-04-12 | Gareth Roy | Gareth left the Glasgow team to become the Data Centre Manager within IT Services.
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Present | UK Members of DPM Collaboration | UK Data Storage (S. Skipsey)
Present | HTTP Deployment Working Group | S. Skipsey
Present | Member of Tier-2 Evolution Working Group | S.Skipsey
– April 2021 | WLCG Sytem Performance and Cost Modelling WG | Gareth Roy
Present | Member of WLCG SOC WG | Adam Boutcher
Present | Member of WLCG SOC WG | Paul Clark
Present | Member of the WLCG DOMA-QoS WG | Robert Currie
Date | Other Outputs and Knowledge Exchange | Notes