## Resource & Narrative
Year | 2021 | Area | SouthGrid
Quarter | Q3 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | Finally managed to install the worker nodes that arrived during lockdown. Aircon has been fixed as well so we are now operating at full capapcity for the first time this year. |  |  | There is now no real support for VAC and we are the only site using it. However, discussing with the experiments will allow us to keep running it.
Bristol |  |  |  | Storage element replacement ongoing - low effort available; Major issues with primary network link: network equipment replacements, throttled for weeks; recenlty upstream issues (university networks team talking to JISC) - no ETA
Oxford | All storage retired at Oxford, all DPM servers decommissioned. Continuing testing Xrootd Xcache for Atlas jobs. Configured Xcache server to have bonded 20G network link. Network uplink tested at 20G to University core routers. Puppet HTcondor module was simplified to use built in config file so that the latest HTCondor version 8.8.15 would be installed. Downtime to update the kernel and upgrade HTCondor to 8.8.15 on all GRID nodes. |  |  | Atlas jobs are running at ~80% CPU efficiency as storage less site - the jobs were running well above 90% as a storage site. Couple of older worker nodes died.
RAL PPD | General ArcCE, HTCondor etc updates Worker Node Kernel updates now fully automatic |  |  | Non LHCOne Traffic still incorectly routed via the site firewall
Sussex
Risks
Type | Risk |  |  | Mitigation
Birmingham
Bristol
Oxford | Xrootd Xcache running on an old hardware. Xrootd Xcache is working as a buffer server instead as a cache server - no advantage for Oxford site. |  |  | Replace the hardware.
RAL PPD
Sussex
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-07-30 | OXFORD: decommission old DPM storage servers. |  |  | Storage-less site from 1st July 2021
2021-10-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | experimental xrootd VM works, now need to move lessons learnt into puppet. Next try clustered mode for production setup
2021-10-30 | New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-10-30 | Continue cleaning up and labelling of network cables |  |  | Satisfied HPC Admin (who is badgering us to do this)
2021-08-30 | Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-10-30 | START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | wiki pages
2021-10-30 | START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | wiki pages
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Oxford: Possible getting new hardware for the Xrootd Xcache from RAL T1. Possibly permanently upgrade the uplink to core routers to 20G if initial test successful and affordable. |  |  | Replace the old hardware
2021-12-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | experimental xrootd VM works, now need to move lessons learnt into puppet. Next try clustered mode for production setup
2021-12-30 | BRISTOL: New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2022-03-30 | BRISTOL: Upgrade to HTCondor 9 |  |  | New and improved HTCondor version with new security
2022-06-30 | BRISTOL: After HTCondor upgrade, add GPUs to HTCondor cluster |  |  | GPUs will become available for local and grid (low availability) use
RALPP: Upgrade dCache to latest Golden Release Fix routing

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 203.8% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 174.9% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 75.77% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 86.47% | MFL | Average Argo Availability - SouthGrid | Brought down by Sussex (which is small) and lack of monitoring of Birmingham |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 88.55% | MFL | Average Argo Reliability - SouthGrid | Brought down by Sussex (which is small) and lack of monitoring of Birmingham

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 22768 | 26780 | 45682 | 55500 | 3580 | 154310 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 11766 | 6195 | 18807 | 37579 | 1360 | 75707
% of Pledge | 193.5% | 432.3% | 242.9% | 147.7% | 263.2% | 203.8%
Storage Available (TB) | 1717 | 1085 | 0 | 3600 |  | 6402 | Oxford is a storage less site from 1st July 2021
Storage Pledged (TB) | 1138 | 0 | 0 | 2522 | 0 | 3660
% of Pledge | 150.9% | #DIV/0! | #DIV/0! | 142.7% | #DIV/0! | 174.9%
Availability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 | 80 | 97.03 | 41.2 | 79.56% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 100 | 100 | 95.53 | 61.69 | 89.3% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 | 94.96 | 87.37 | 79.81 | 90.53% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 100 | 91.6533 | 93.31 | 60.9 | 86.47%
Reliability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 | 100 | 97.03 | 41.2 | 84.56% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 100 | 100 | 95.53 | 61.69 | 89.3% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 100 | 100 | 87.37 | 79.81 | 91.8%
% Tier-2 Total | #DIV/0! | 100 | 100 | 93.31 | 60.9 | 88.55%
CPU Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 100865856 | 122544000 | 7904640 | 210267840 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 6731760 | 10966639 | 20613849 | 31002517 | 1549388 | 70864153 | Q1: 2160/2184 (if leap year)
Month 2 | 4677780 | 8830236 | 24714079 | 31710173 | 577278 | 70509546 | Q2: 2184
Month 3 | 5756487 | 8883808 | 21858516 | 32088695 | 1504405 | 70091911 | Q3: 2208
Total: | 17166027 | 28680683 | 67186444 | 94801385 | 3631071 | 211465610 | Q4: 2208
% Utilisation | 34.15% | 48.5% | 66.61% | 77.36% | 45.94% | 100.6%
WallClock Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 100865856 | 122544000 | 7904640 | 340716480 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 7901894 | 14507469 | 24703404 | 36851855 | 1489708 | 85454330 | Q1: 2160/2184 (if leap year)
Month 2 | 5406880 | 11410406 | 28889856 | 40786308 | 614177 | 87107627 | Q2: 2184
Month 3 | 6937940 | 11404947 | 25478442 | 39909137 | 1851523 | 85581989 | Q3: 2208
Total: | 20246714 | 37322822 | 79071702 | 117547300 | 3955408 | 258143946 | Q4: 2208
% Utilisation | 40.27% | 63.12% | 78.39% | 95.92% | 50.04% | 75.77%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 |  | 690 | 0 | 770 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 0 | 0 | 384 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 |  | 599 | 0 | 679 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 0 | 0 | 325 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
[6 empty] | 0 | Active VOs at you site can be assesed from the following link:
[6 empty] | 0 | https://accounting.egi.eu/tier2/federation/UK-SouthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
[6 empty] | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
[6 empty] | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes