## Resource & Narrative
Year | 2021 | Area | CMS
Quarter | Q2 | Reporter | KE |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Tier 1 | Some improvements seen in job efficiency - more to come |  |  | CMS caused to go into drain (from production jobs) with increasing regularity - something to monitor.
Tier 2s
Risks
Type | Risk |  |  | Mitigation
General | Poor offsite read performance at T1 |  |  | New network bypassing firewall should help this.
Area Specifc | Need ability to perform vector reads efficiently at T1 |  |  | Possible development at T1 to help this
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [11 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 10 |  | 5% |  | AWI | Tier-1 Data Transfer Quality | We moved to WebDav for a couple of weeks in early October, but had to revert back to gsiftp due to the failure rate. Tape transfers restarted, but at a limited rate, as RAL offered additional space (around 3PB) to CMS. | [5 empty] | Metric OK | MOK
2 | 11 | 5% or pledge | 5% | 9.7% | #VALUE! | Timely and efficient availability and use of resources at RAL T1 (Global %) | More than pledged resources were used by CMS, RAL ran 9.7% of completed T1 jobs. | [5 empty] | Metric Clost to Target | MCT
2 | 12 | 70% | 5% | 51% | MFL | Tier-1 Average CPU Efficiency | Still in the red zone, but an improvement of 10 percentage points from last quarter. Some periods with heavy use of offsite reads still give very poor average efficiency - e.g. 20%. But some cause for optimism here. | [5 empty] | Metric not OK | MFL
2 | 13 | 10% | 5% | 15% | MFL | Tier-1 Failure Rate | Slightly higher than last quarter, but the same as FNAL and better than PIC. Still could improve, I reckon. If you subtract the LogCollect jobs, which still fail virtually all of the time at RAL (35% of failures this Q) the rate is closer to 10%. | [5 empty] | Metric with no Target | MNO
2 | 14 | 97% | 5% | 94% | MCT | Site availability at the Tier-1 | WLCG SiteMon - 97% July, 85% August, 100% September
2 | 15 | 5% | 5% |  | AWI | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | There is currently no way to access this information.
2 | 16 | 0% | 1% | 0% | MOK | Custodial Data Loss at Tier-1 | None
2 | 17 |  | 5% | 0% | MOK | Transfer rates to the UK Tier 2s | No major problems
2 | 18 | 80% | 5% | 99% | MOK | Site availability at the Tier-2s | IC - 100 (100/100/100) %, Brunel - 99 (96/100/100) %, RALPP - 99 (99/99/100) %
2 | 19 | 80% | 5% | 99% | MOK | Site reliability at the Tier-2s | As above
2 | 20 | 0% | 5% | 0% | MOK | Unique data loss at Tier-2s | None
2 | 21 | 30% | 5% | 20% | MOK | Failed analysis jobs | Same as last quarter
2 | 22 | 20% | 5% | 6% | MOK | Failed production jobs | Another improvement on last quarter
2 | 23 | 5% | 5% | 4% | MOK | T2 sites provide an appropriate level of resource to CMS | UK sites provided CPU to complete 4% of CMS T2 jobs, which is a slight improvement on Q2
2 | 24 | 80% | 5% |  | AWI | Job performance/efficiency using AAA data transfer | There is currently no way to access this information.
Milestones | [11 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments |  |  |  |  | Colour | Description | Code
2 | 5 | 2020-12-01 | Y | 2020-12-01 | MSA | Report on delivery to CMS during year | [6 empty] | Milestone Achieved | MSA
2 | 6 | 2021-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Ongoing | MOG
2 | 7 | 2022-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone Overdue | MOD
2 | 8 | 2023-12-01 | N |  | MSU | Report on delivery to CMS during year | [6 empty] | Milestone not due | MSU
2 | 17 | 2020-10-01 | Y | 2020-10-01 | MSA | Review of CMS AAA Efficiency
2 | 18 | 2021-04-01 | S |  | MSU | Review of CMS AAA Efficiency | Milestone Suspended - work on Tier-1 CMS efficiency is an ongoing evalation of multiple aspects of CMS efficiency, including AAA, and depositions from the CMS reps are that it is impossible/unfeasible to measure "AAA efficiency" as a single entity. (See Metric 2:24)
2 | 19 | 2021-10-01 | N |  | MSU | Review of CMS AAA Efficiency | KATY and DAVID - I would like to chat about this again. SAM
2 | 20 | 2022-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 21 | 2022-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 22 | 2023-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 23 | 2023-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 24 | 2024-04-01 | N |  | MSU | Review of CMS AAA Efficiency
Site availability
[7 empty] | Site | Jan | Feb | Mar | Avg
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333
Site reliability
[7 empty] | Site | Jan | Feb | Mar
[7 empty] | T1 | 100 | 100 | 100 | 100
[7 empty] | IC | 100 | 100 | 100 | 100
[7 empty] | RALPP | 99 | 100 | 96 | 98.3333
[7 empty] | Brunel | 100 | 99 | 99 | 99.3333

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes