## Resource & Narrative
Year | 2021 | Area | Other VOs
Quarter | Q3 | Reporter | KE
Narrative
Area | Successes |  |  | Problems
Onboarding new VOs
Supporting existing VOs through major campaigns
Service improvements
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc | Communication during Covid particularly. Can lose touch with the smaller VOs.
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 33 | 90% | 40% | 67.8% | MCT | UK Tier-1 work fraction for ALICE as a proportion of all Tier-1s (not CERN). Normalised to 3% for GridPP6 | Again, the last quarter has changed when I re-calculate. Taking the proportion of work by Wallclock hours (subtracting work done by CERN - T1s only). For Q3, value is 2.03% of all T1 work. |  | Metric OK | MOK
2 | 34 | 70% | 20% | 87% | MOK | UK T1 CPU efficiency by ALICE. |  |  | Metric Clost to Target | MCT
2 | 35 | 90% | 20% | 48% | MFL | UK T1 CPU usage by ALICE. Normalised against pledged HS06. | Using pledge of 14940 HS06 (multiplied by 24 and number of days in the quarter). However, the number in the previous quarter has changed massively. |  | Metric not OK | MFL
2 | 36 | 90% | 40% | 98% | MOK | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s. Normalised to 2.1% for GridPP6. | Values have been changing again in previous quarters. Currently 2.05% for Q3 |  | Metric with no Target | MNO
2 | 37 | 70% | 10% | 93% | MOK | UK T2 CPU efficiency for Alice.
|  | 80% | 10% | 62% |  | ALICE disk usage at T2 (on last day of the quarter?) | From Mark Slater: capacity: 1.02PB used: 631.95 TB
2 | 38 | 70% | 20% | 57% | MCT | T1 CPU Efficiency for DUNE | Efficiency fell throughout the quarter from 64 to 45%
2 | 39 | 70% | 20% | 40% | MFL | T2 CPU Efficiency for DUNE | Poor compared with other countries
2 | 40 | 75% | 25% | 91% | MOK | CPU usage by DUNE in the UK relative to pledge of 2000 cores | 1821 cores in total, from T1 (average 711 cores) and T2 (average 1110 cores).
2 | 41 | 70% | 20% | 94% | MOK | T1 CPU Efficiency for Other (non-DUNE, non-LHC) | High score, but fell through the quarter
2 | 42 | 70% | 20% | 58% | MCT | T2 CPU Efficiency for Other (non-DUNE, non-LHC)
2 | 43 | 75% | 25% | 47% | MFL | T1/T2 % pledged CPU used by Other VOs (pledge is 13% of CPU used by combined LHC exps pledge in UK, which I believe is 647,546 HS06 now ~ so 13% is 84181) | T1 usage 8,386,463 HS06 hours = 3798 HS06; T2 usage 78,491,650 HS06 hours = 35549 HS06. Total sum is 39347. Seems rather low this quarter?
Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments
|  | 2020-04-01 | N |  | MSU |  |  | Key - Milestones
|  | 2020-04-01 | N |  | MSU |  |  | Colour | Description | Code
[9 empty] | Milestone Achieved | MSA
[9 empty] | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes