## Resource & Narrative
Year | 2021 | Area | Security
Quarter | Q3 | Reporter | DK /DC
Narrative
Area | Successes |  |  | Problems
Operations | An EGI CSIRT F2F was held in this period along with preparation and revision of OSC Security materials. Development of EGI CSIRT SSC with help from Katy Ellis (challenge now planned for early 2022, coordinating with CMS to avoid data taking in Run3). Continued participation in Authz working group including leadership of activity on traceability and central suspension. Formal approval of STFC SOC project by EB. Presentation of security strategy at GridPP collaboration meeting |  |  | None
Trust & Identity | An EUGridPMA meeting was held in this period, notably including discussion of host certificate usage evolution. Presentation of this discussion at GridPP with contributions from CERN helping prepare for GDB presentation. |  |  | None
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 100% | MOK | % of Sites responding to security communication requests | n/a |  | Metric OK | MOK
3 | 3 | 95% | 5% | 100% | MOK | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | One CRITICAL advisory (started HIGH and was escalated) |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | 1 event reported out of abundance of caution by Sheffield; procedure well followed with no follow-up required |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N | 2020-07-01 | MSA | GridPP-wide security training event | IRIS Security Workshop held at end of July 2020
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | Y | 2021-04-01 | MSA | Review WLCG security policy and procedure set | Review available on request. Milestone now completed (July 2021). This was 3 months late because of conflict with other activities.
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes