## Summary
Ref. | Risk Description | Owner | Inherent Risk |  |  | Residual Risk
|  |  | Likelihood | Impact | Total | Likelihood | Impact | Total | RS
1 | Antares Storage System Problems | AD | 5 | 5 | 25 | 4 | 5 | 20
2 | Tier-1 Tape service replacemet | AD | 5 | 5 | 25 | 4 | 5 | 20
3 | Outage of UK T1 | AD | 4 | 6 | 24 | 3 | 5 | 15
4 | Failure of T1 to meet SLA or MoU | AD | 7 | 5 | 35 | 4 | 5 | 20
5 | Significant loss of custodial data at the T1 | AD | 6 | 8 | 48 | 3 | 5 | 15
6 | Loss or damage to hardware at T1 >£2M | AD | 1 | 10 | 10 | 1 | 10 | 10
7 | Disaster at T1 leads to prolonged outage | AD | 0.5 | 8 | 4 | 0.5 | 8 | 4
8 | Recruitment and retention problems at RAL | DK | 9 | 6 | 54 | 7 | 5 | 35
9 | Failure to procur, deploy or operate hardware | AD,SS | 6 | 7 | 42 | 7 | 6.5 | 45.5
10 | Insufficient Network Bandwidth | PC | 4 | 5 | 20 | 3 | 5 | 15
11 | Over contention for resources | DB | 4 | 5 | 20 | 3 | 5 | 15
12 | Increase non-LHC use | DB | 5 | 5 | 25 | 1 | 5 | 5
13 | Unquantfiable impact of BREXIT | DB | 6 | 6 | 36 | 5 | 6 | 30
14 | Capital vs Resource at the Tier-1 | DB | 4 | 6 | 24 | 5 | 5 | 25
15 | Insufficient funding at Tier-1 | DB | 5 | 5 | 25 | 2 | 2 | 4
16 | Technology Mismatch | DC | 6 | 7 | 42 | 4 | 5 | 20
17 | Loss of experienced personnel at T2s | RJ | 7 | 5 | 35 | 4.5 | 4.5 | 20.25
18 | Insufficient funding at T2s for h/w | RJ | 2 | 4 | 8 | 2 | 2 | 4
19 | Tier-2s are not fit for purpose | RJ | 5 | 6 | 30 | 4 | 6 | 24
20 | Expt. s/w runs poorly | SS | 7 | 6 | 42 | 3 | 4 | 12
21 | Security problem affecting reputation | DK | 8 | 8 | 64 | 5 | 7 | 35
22 | Loss of GridPP service due to security | DK | 8 | 7 | 56 | 5 | 7 | 35
23 | Insufficient VO/user support effort | SS | 7 | 5 | 35 | 3 | 5 | 15
24 | Mismatch between budget and hardware costs | DB | 9 | 7 | 63 | 4 | 6 | 24
25 | Core service funding insuffcient | DB | 5 | 4 | 20 | 4 | 2 | 8
26 | Breakdown of NGI/EGI infrastructure | SS | 3 | 3 | 9 | 3 | 3 | 9
27 | Insufficient travel funds | DK | 4 | 2.5 | 10 | 3 | 2.5 | 7.5
29 | Critical middleware no longer supported | DC | 5 | 6 | 30 | 5 | 5 | 25
30 | Unplanned infrastructure costs | SS/PG | 4 | 4 | 16 | 3 | 5 | 15
31 | Loss of EGI.eu | DK/AD | 4 | 3 | 12 | 3 | 2 | 6
32 | Financial Uncertainty | DB | 5 | 6 | 30 | 3 | 4 | 12
33 | Conflicting opinions amongst GridPP stakeholders | DB | 3 | 5 | 15 | 2 | 4 | 8

## Risk Register
[7 empty] | Total risk is product of Likelihood and Impact |  |  |  |  | Project Title: |  | GridPP6
[7 empty] | 25 - 50 | medium |  |  |  | Project Manager: |  | Samuel Skipsey
[7 empty] | 0 - 25 | low
[7 empty] | 50 - 100 | high
[14 empty] | 2022-04-28 |  | T1 | T2 | Project | Operational | Reputational | Financial
Ref. | Risk Description | Short Name | Work-package | Potential impact on project | Owner | Inherent Risk |  |  | Existing Controls | Current and proposed mitigation | Residual Risk |  |  | Action Required | Change since last review
[6 empty] | Likelihood | Impact | Total |  |  | Likelihood | Impact | Total
1 | ANTARES storage system may suffer from degraded availability or inadequate performance | Antares Storage System Problems | 1 | Experiments would be unable to keep up with data rate from CERN or other sites. Service may be unable to handle planned level of reprocessing or analysis. | AD | 5 | 5 | 25 | Reliability good but some indication of performance related problems at high transaction rates. Extensive testing of infrastructure. Close liaison with CERN. Pro-active monitoring. Change control system. Limit number of major upgrades. Close liaison with experiments. Resilient architecture. | Continue to extend testing. Pro-active approach to advanced testing of new use cases. Increase priority of ANTARES support. Impact will decline as CEPH project progresses. | 4 | 5 | 20 |  | Metric now tracks new Antares system which replaced CASTOR. Increased risk as this is a new system (same as risk inherited from retired metric below) | x |  |  | x | x
2 | Replacement Tier-1 Tape service to replace CASTOR may not be in place before CASTOR support ends. | Tier-1 Tape service replacemet | 1 | 1. CASTOR support from CERN will end with it's refocus on EOS as a storage solution. This will mean and end to software updates for the CASTOR Tape service. 2. At present no alternative has been identified so project runs a risk of hitting a software/security issue which will not be patched when support ends 3. Lack of development effort in GridPP6 may slow implementation of Tier-1 service | AD | 5 | 5 | 25 | Software development expertise held within Tier-1 that can be used to continue CASTOR support, ongoing effort in developing and deploying a new Tier-1 Tape service. | Identify and develop a new Tier-1 tape service. | 4 | 5 | 20 |  | METRIC RETIRED: Transition to new Antares system completed (entry above now tracks risk associated with the commissioned system) | x |  |  | x | x | x
3 | Outage of the UK T1 for 1 week or more (cooling failure, network failure etc) | Outage of UK T1 | 1,2 | Tier-1 would not be able to operate and would be unable to meet MoU commitments. Knock on effect on UK Tier-2s. | AD | 4 | 6 | 24 | Well tested disaster management system will initiate prompt remedial action. Staff prepared to work overtime. Resilient network connectivity and cooling system. UPS. Environment monitoring and callout system. | Some resilience is available in the International Tier-1 structure. Tier-2s could work with other Tier-1s if required. Some fall back services are provided by the Tier-2s. | 3 | 5 | 15 |  | No Change | x |  |  | x | x
4 | Failure of T1 to meet WLCG MoU service level commitments for availability/responsivness | Failure of T1 to meet SLA or MoU | 1,3 | Due to falling staff levels at the Tier-1 it becomes increasingly difficult to respond in a timely manner. In the event of a major failure (rather than a slight technical failure) experiments would be unable to carry out their full program of work at the Tier-1. We may suffer reputational damage. | AD | 7 | 5 | 35 | Production team and callout system. Disaster management system. Resilient, segmented infrastructure. Performance metrics. Change control system. Well established hardware procurement system with reserve capacity to handle short term procurement delays. | Much of the work of the team is directed towards ensuring MoU commitments are met. Production team will continue to enhance the services ability to respond rapidly and effectively to problems. Increase further the emphasis on change management and testing. Improve ability to carry out transparent interventions, by architecture, virtualisation and instancing improvements. | 4 | 5 | 20 |  | No change. (COVID stil around) | x |  |  | x | x
5 | Significant loss of custodial data at the T1 | Significant loss of custodial data at the T1 | 1 | Reputational damage. Although copies are usually held elsewhere in the world copying back to RAL may be operationally problematic or even in extreme cases impossible. | AD | 6 | 8 | 48 | Metadata catalogue backups and live off site copy. Checksums. Media recovery procedures. | Extensive disaster recovery testing. Routine data dipsticking/validation. Regular media repacking. | 3 | 5 | 15 |  | No change. | x |  |  | x | x
6 | Substantial loss of or damage to hardware at the T1 (Fire, flood, theft, flooring failure, cooling failure …) hardware damage exceeding £2m | Loss or damage to hardware at T1 >£2M | 1 | Could not meet MoU commitments. Corrective action would be impossible within existing funding and when funded may take many months to carry out. | AD | 1 | 10 | 10 | Building access control system and physical protection. Environment monitoring, automated shutdown and callout system. Fire alarm and fire suppression system. Cooling system resilience. Disaster management system. | Ensure close liaison with site services to pre-empt weaknesses when they are identified in the infrastructure. | 1 | 10 | 10 |  | No Change | x |  |  | x | x | x
7 | Significant disaster at the Tier-1, leading to prolonged outage (fire, flood, JANET unavailable for long period, etc.) | Disaster at T1 leads to prolonged outage | 1 | Very long term outage of the Tier-1: UK unable to meet its commitments to wLCG over substantial period | AD | 0.5 | 8 | 4 | Environment monitoring and callout system to stop problems becoming critical. Other wLCG Tier-1s take over services. | Resilient site network paths and infrastructure. Attempt to associate UK Tier-2s with other Tier-1s now a possibility owing to improved network infrastructure. | 0.5 | 8 | 4 |  | No Change | x |  |  | x | x | x
8 | Failure to retain or recruit key technical staff at RAL | Recruitment and retention problems at RAL | 1,3 | Inability to meet GridPP deliverables, milestones and metrics because of lack of staff | DK | 9 | 6 | 54 | Ensure that STFC management are aware of problems when/if they occur | Well documented processes & procedures for key systems are used to share essential knowledge. This allows technical staff to have the minimum knowledge required to ensure critical systems stay online and at a minimum level of operation, in the case of a loss of expertise. Staff given appropriate ownership of key systems, recognition within STFC and opportunities to share key personal successes within the GridPP community (at collaboration and other meetings). Use of apprenticeships and internship where appropriate to help fill the recruitment pipeline. | 7 | 5 | 35 |  | Increased risk, due to economic factors (cost of living, etc) worsening. | x |  |  | x
9 | Failure to procur, deploy or operate hardware at GridPP sites | Failure to procur, deploy or operate hardware | 1,2 | Problems with procurement such as late delivery or other supplier related issues. Large batches of h/w could fail acceptance testing or develop faults during production use. Significant reduction in capacity could adversly affect GridPP's abilitiy to meet the WLCG MoU commitments. | AD,SS | 6 | 7 | 42 | 1. Monitoring of available disk space/cpu utilisation. 2. Procurements take account of experiment requests. 3.Track hardware failures and observe trends. 4. Documented clear recovery procedures. 5. Throughly test new hardware prior to deployment. 6. Changes in site procurement policy 7. PMB oversight of procurement at GridPP sites. | If jobs do not require site specific data then redirect them to other sites. If data is required then replicate it elsewhere and run jobs. Run a fast procurement to increase capacity - if not a short term effect. Close liason with instituional procurements teams. | 7 | 6.5 | 45.5 |  | Increased risk due to geopolitical effects on supply chains, economies and ongoing silicon shortages | x | x |  | x
10 | Insufficient Network bandwidth delivered | Insufficient Network Bandwidth | 1,2 | Lack of bandwidth would prevent data flowing from the Tier 0, & 1 and onto the Tier 2s at a rate sufficient to process the data at required speeds. | PC | 4 | 5 | 20 | The Tier1 has a failover link for the LHCOPN. Tier-2s are liaising with JANET to upgrade links at major sites. | Exploit second OPN link if necessary, Tier-2s are generally well connected and GridPP has good communications links with JANET/JISC. Actual measured throughput should deliver as expected. | 3 | 5 | 15 |  | Residual likelihood increased (from 2 to 3) due to the delays in upgrades to bandwidth at some large Tier-2s. Tier-1 risk is reduced due to network upgrades. | x | x | x | x
11 | Over contention for Resources | Over contention for resources | 1,2 | Resources are so heaviliy used that conflicts arise between major VOs stemming from a change in experiment requirements subsequent to project proposal. | DB | 4 | 5 | 20 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Purchase more hardware and/or improve profiling and procurement.Reduce non-LHC experiment resources. Agree programme priorities through PMB and STFC. | 3 | 5 | 15 |  | No change - remain at risk, although Brexit risks mostly quantifiable. |  | x | x | x | x
12 | Unexpected resource requirements by non-LHC VOs | Increase non-LHC use | 1,2 | Mandated non-LHC VOs have increased usage requirement that cause conflict with LHC usage. | DB | 5 | 5 | 25 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Look at supporting non-LHC VOs from other funding opportunities such as IRIS fundining. | 1 | 5 | 5 |  | Reduced due to availability of IRIS etc, which cushion effects for us. |  | x | x | x | x
13 | Unquantfiable impact of BREXIT | Unquantfiable impact of BREXIT | All | 1. Exchange rate volatility 2. Loss of joint funding from EOSC 3. New, restrictive operational constraints | DB | 6 | 6 | 36 | Situation at present makes it difficult to plan strategy | Call upon project contingency | 5 | 6 | 30 |  | METRIC RETIRED: Brexit impacts are now quantifiable enough to be included across the other risks in this register. | x | x | x | x |  | x
14 | Difficulty with STFC budgets due to Capital vs Resource limitations | Capital vs Resource at the Tier-1 | 1,2 | The Split of funding between Capital and Resource, can cause problems due to the changing classification of computer equipment | DB | 4 | 6 | 24 | Quarterly review of Tier 1 spending situation. Salaries are always classed as resource, but the boundary for equipment purchases makes predicting the capital requirement difficult. | Increase communications with STFC to ensure plan is appropriate. | 5 | 5 | 25 |  | No change. | x | x | x | x |  | x
15 | Insufficient funding to meet hardware commitments at Tier-1 | Insufficient funding at Tier-1 | 2 | Less hardware available to meet international obligations and MoUs as well a suser expectations. See BREXIT risk. | DB | 5 | 5 | 25 | Detailed trends and costings based on 10 years of purchases to maximise resources procured from spends. | Encourge opportunities of sourcing funding from other streams (e.g. IRIS) | 2 | 2 | 4 |  | Increasing risk, due to increasing hardware requirements past the risk register horizon. |  | x |  |  |  | x
16 | GridPP unable to respond to (unexpected) Technology Shifts - WLCG expts exploit new technology not supported at GridPP sites. | Technology Mismatch | 1,2,4 | In the absence of significant development effort, GridPP would be unable to respond to new developments in technology cause mismatch between experiment processing requirements and available hardware. | DC | 6 | 7 | 42 | New technology directions are closely monitored by involvement in research work groups on Cloud computing, Virtualization, and HEPIX. Changes are expected by the end of the project. GridPP technology group meets regularly. | Work packages invest some small fraction of effort directly on new technologies with a view to bringing them mainstream when both mature enough and appropriate to the overall project. WLCG TEGs and WLCG TDR update. This could be mitagated by the effor tin the 110% scenario | 4 | 5 | 20 |  | No change |  | x | x | x
17 | Loss of experienced personnel or insufficient manpower at T2s | Loss of experienced personnel at T2s | 2 | Sites may not be able to diagnose and fix problems as quickly. Ability to react to changing situations or to upgrade will be compromised. | RJ | 7 | 5 | 35 | GridPP6 staffing levels predicted. Multiple Tier-2s provide resilience to the project. | Two people at main sites. Grid Operations team spreads knowledge and expertise across sites. New models of working adopted to cope with falling staff levels at smaller sites. | 4.5 | 4.5 | 20.25 |  | Increased risk due to it being a employee's market, pressures on hiring post-COVID. |  | x |  | x
18 | Insufficient funding to meet hardware commitments at T2s | Insufficient funding at T2s for h/w | 2 | Less hardware available to meet international obligations and user expectations. | RJ | 2 | 4 | 8 | Funding models are different at different sites. Not all sites would be affected the same way and some sites may be able to add resources to compensate. | Encourage opportunistic use of more central resources. Encourage experiments to prioritise and make more efficient use of resources. | 2 | 2 | 4 |  | No change – T2 sites currently overproviding, so buffered against funding issues in 6-12month view. |  | x |  |  |  | x
19 | Middleware or software at T2 sites not fit for purpose | Tier-2s are not fit for purpose | 2,3 | Lack of staffing at Tier-2 sites reducing effort to respond to poor or non-functional middleware. Complex middlware takes significant effort to plan upgrades, deploy and test. | RJ | 5 | 6 | 30 | The same middleware and software is used at T1 and T2 sites across the world. wLCG will work with experiments to solve problems. | Community effort and shared knowledge is distributed trough week operations and storage meetings. Bi-weekly technical meetings held to discuss pain points in detail | 4 | 6 | 24 |  | No change - sites actively exploring cephfs, Xcache, other solutions in 6-12month timescale. |  | x |  | x
20 | Experiment software runs inefficiently, to the detriment of UK physicists | Expt. s/w runs poorly | 3 | Workload would not be able to fully exploit the resources available. Expts would need to invest effort in improved computing model. | SS | 7 | 6 | 42 | Experiments have reviewed computing models in preparation for LHC Run 3. Special arrangements are made for certain customers. | Experiment support posts and the grid support team will be available to all sites. Good dialogue with special customers required to ensure appropriate planning. | 3 | 4 | 12 |  | Decreased risk - evidence of improved experiment software efficiencies seen at Tier-1. |  |  | x | x
21 | Reputation risk due to a serious security problem | Security problem affecting reputation | 3 | Security problems may bring down the whole of GridPP or even wLCG, given that all Sites run very similar software. A major outage is likely to attract significant outside interest and GridPP is likely to suffer damage to its reputation. Threats rising and ability to deal with is decreasing and impact on operations is rising | DK | 8 | 8 | 64 | Act on many fronts in parallel to handle vulnerabilities to avoid incidents, to contain and handle incidents quickly when they do happen and define and enforce appropriate policies to control actions of participants. Dedicated security resource part of GridPP6. | We lead the Joint Security Policy Group of wLCG/EGI, the security vulnerability group of EGI . Established experienced security team in place. Many staff have recently recieved security training. New closer relations are being developed with IRIS and JISC security teams and a stronger monitoring and reporting on patching status is being developed. | 5 | 7 | 35 |  | Residual likelihood increased due to geopolitical factors.. |  |  | x |  | x
22 | Non-availability of T1 &2 service or compromised data due to security vulnerability | Loss of GridPP service due to security | 3 | Extended service downtime, loss of data, inability to process and analyse data. | DK | 8 | 7 | 56 | Well organised operational security incident handling led by the GridPP Security Officer in collaboration with the Tier 1 and Tier 2 system managers. Vulnerabilities in the middleware are handled today by EGI to prevent incidents happening | The GridPP security effort is essential to reduce the risks from known security vulnerabilities, to handle incidents when they do occur, to train system managers, to define and encourage security best practice, e.g. timely system patching, and to continuously monitor the status. Many staff have recently recieved security training. | 5 | 7 | 35 |  | Impact increased due to the increased downtime expected for serious security issues in the present climate. (Host universities might want v extended downtimes to ensure safety). |  |  | x | x
23 | Insufficient effort to support the VOs or the users | Insufficient VO/user support effort | 3 | New user groups (VOs) or users of the main LHC VOs are not able to make use of the Grid to do their research. | SS | 7 | 5 | 35 | Dedicated experiment support post at the Tier-1 and Tier-2 s for LHC Vos however an increase in non LHC VOS could stretch resources. Extensive Web documentation. User Coordinator can liaise with the experimental users. | Tier-1 resource meeting with the User Coordinator provides a forum to discuss new user requirements. GridPP-Support mailing list setup to coordinate help to new users. | 3 | 5 | 15 |  | No change - positive changes in landscape due to IRIS. |  |  | x | x | x
24 | Mismatch between budget and hardware costs | Mismatch between budget and hardware costs | 4 | Project would not be able to deliver the pledged resources resulting in (a) political damage and eventually (b) disadvantage to the UK experiments as the level of resource falls | DB | 9 | 7 | 63 | Monitor UK purchases for last 10 years and extrapolate with comprehensive modelling. | Cross check with CERN predictions but there is a residual exchange rate uncertainty on top of the technological uncertainty. | 4 | 6 | 24 |  | No change |  |  | x |  |  | x
25 | Funding for central services that GridPP relys on insufficiently funded. | Core service funding insuffcient | 4 | Resources within the NGI on which GridPP is planning to rely are not available. For example, the Certificate Authority is not funded or has inadequate effort to meet GridPP needs. | DB | 5 | 4 | 20 | Close collaboration with STFC to ensure GridPP is aware of progress and any issues. | Call on GridPP contingency to fund extra posts to cover the core staff. | 4 | 2 | 8 |  | No change - funding assured in timescale of review. |  |  | x |  |  | x
26 | Breakdown of core operations structures - for example in the NGI/EGI infrastructure | Breakdown of NGI/EGI infrastructure | 4 | Without a central ticketing (GGUS) interface or Grid Operations database the ability to follow up on problems, inform of upcoming downtimes and general communications between sites and users is interrupted. | SS | 3 | 3 | 9 | Core services are hosted on high-availability hardware. The GOCDB has a failover capability to another region. See BREXIT risk for assocated operating risk. | NGI structure in place and the existing central instances serve as a backup. After the transition the UK instances will be placed on high resilience equipment and procedures put in place for rapid deployment of new services. | 3 | 3 | 9 |  | No change |  |  | x | x |  | x
27 | Insufficient travel funds for effective engagement and contribution to wLCG and for internal operation of GridPP. | Insufficient travel funds | 4 | GridPP would experience difficulty in keeping up with developments in operations, in updating staff skills (through attendance at technical meetings) and in keeping up to date with experiment requirements. | DK | 4 | 2.5 | 10 | Careful management of resources and prioritisation to ensure sufficient travel funds are available | Increase the use of phone and video conferencing for attending meetings (though noting such facilities are not always available and they are frequently less optimal than attendance in person). | 3 | 2.5 | 7.5 |  | No change |  |  | x | x |  | x
29 | Critical middleware no longer supported | Critical middleware no longer supported | 4 | The significant Grid middleware code base needs to be properly maintained and supported throughout the project. The development community is now reduced to a skeleton staff and maintenance problems can arise especially with data management components. | DC | 5 | 6 | 30 | Existing GGUS mechanisms enable bug reporting by sysadmins to a small number of expert developers. Data support staff enable appropriate deployment choices, workarounds and bug fixes to be made. | Culture of fully-tested code and minimal change established. Maintenance of expertise and support staff in recognised critical areas. Reductions in functionality, if necessary. Community based support model in process of being established. | 5 | 5 | 25 |  | No change over all (but risk of transition from DPM increased versus decrease in the OS transition from last time; effects cancel out at this level) |  |  | x | x
30 | Unplanned infrastructure costs | Unplanned infrastructure costs | 4 | If extra costs arise at the T1 or T2, there is the possibility that funds will not be sufficient to buy the required hardware. Risks failing to meet WLCG pledge, and reputation risk. Risk of needing to ration resources due to electricity etc costs | SS/PG | 4 | 4 | 16 | Tier-2 costs spread across sites - if one site cannot meet the price GridPP is paying, then other sites can increase their share. Increasing risk of electricity costs or networking costs. | GridPP contingency available for extra costs at the Tier-1 or systematic increases at the Tier-2s. | 3 | 5 | 15 |  | Rising risk due to increasing electricity costs and the visibility of this to host institutes. |  |  | x |  |  | x
31 | EGI does not continue or the UK does not continue to be a member. | Loss of EGI.eu | 4 | Access to services run by EGI, Loss of co funding for services run within the UK. Loss of access to future funding oportunities, such as Horizon 2020. | DK/AD | 4 | 3 | 12 | Essential posts are part of the GridPP6. Possible BREXIT implications, see BREXIT risk. | Call on GridPP contingency to fund necessary posts. Reallocate work to other staff if possible. | 3 | 2 | 6 |  | No change |  |  | x | x |  | x
32 | Financial Uncertainty | Financial Uncertainty | 4 | Uncertainties can make staff retention difficult. Lack of long term funding would result in inadequate resources and service being provided to serve the needs of the UK Particle Physics Community. | DB | 5 | 6 | 30 | GridPP6 funding approved but still longer term uncertainities with Government funding. | Raise issues with GridPP Oversight Committee and directly with STFC | 3 | 4 | 12 |  | No change |  |  | x |  |  | x
33 | Conflicting opinions amongst GridPP stakeholders | Conflicting opinions amongst GridPP stakeholders | 4 | Disatisfaction amoungst users or site administrators could result in reduced utilisation of the resources and adversly affect the quality of research carried out. | DB | 3 | 5 | 15 | 1. Weekly PMB meetings. PMB minutes widely circulated to members of the community. Operations and sites meetings held weekly, with good coomunication between the PMB and the OPS team via cross membership. Collaboration meetings held regularly. | More F2F meetings, More CB meetings, Sites visits. | 2 | 4 | 8 |  | No change |  |  | x | x | x

## OSC Format
| RISK REGISTER |  |  |  | Total risk is product of Likelihood and Impact | [7 empty] | Project Title: | GridPP6
[5 empty] | 0 - 25 | Low | [6 empty] | Project Manager: | Samuel Skipsey
[5 empty] | 25 - 50 | Medium
[5 empty] | 50 - 100 | High | [6 empty] | Last Update: | 2022-04-28
[5 empty] | 0 | Retired
Ref. | Risk Description | Potential impact on project | Owner | Inherent Risk |  |  | Existing Controls | Current/Proposed mitigation | Residual Risk |  |  | Risk Exposure |  |  | Action Required
|  |  |  | Likelihood | Impact | Total |  |  | Likelihood | Impact | Total | Change | description | Cost (£k)
1 | ANTARES storage system may suffer from degraded availability or inadequate performance | Experiments would be unable to keep up with data rate from CERN or other sites. Service may be unable to handle planned level of reprocessing or analysis. | AD | 5 | 5 | 25 | Reliability good but some indication of performance related problems at high transaction rates. Extensive testing of infrastructure. Close liaison with CERN. Pro-active monitoring. Change control system. Limit number of major upgrades. Close liaison with experiments. Resilient architecture. | Continue to extend testing. Pro-active approach to advanced testing of new use cases. Increase priority of ANTARES support. Impact will decline as CEPH project progresses. | 4 | 5 | 20 | q |  |  | 0
2 | Replacement Tier-1 Tape service to replace CASTOR may not be in place before CASTOR support ends. | 1. CASTOR support from CERN will end with it's refocus on EOS as a storage solution. This will mean and end to software updates for the CASTOR Tape service. 2. At present no alternative has been identified so project runs a risk of hitting a software/security issue which will not be patched when support ends 3. Lack of development effort in GridPP6 may slow implementation of Tier-1 service | AD | 5 | 5 | 25 | Software development expertise held within Tier-1 that can be used to continue CASTOR support, ongoing effort in developing and deploying a new Tier-1 Tape service. | Identify and develop a new Tier-1 tape service. | 4 | 5 | 20 | q |  |  | 0
3 | Outage of the UK T1 for 1 week or more (cooling failure, network failure etc) | Tier-1 would not be able to operate and would be unable to meet MoU commitments. Knock on effect on UK Tier-2s. | AD | 4 | 6 | 24 | Well tested disaster management system will initiate prompt remedial action. Staff prepared to work overtime. Resilient network connectivity and cooling system. UPS. Environment monitoring and callout system. | Some resilience is available in the International Tier-1 structure. Tier-2s could work with other Tier-1s if required. Some fall back services are provided by the Tier-2s. | 3 | 5 | 15 | q |  |  | 0
4 | Failure of T1 to meet WLCG MoU service level commitments for availability/responsivness | Due to falling staff levels at the Tier-1 it becomes increasingly difficult to respond in a timely manner. In the event of a major failure (rather than a slight technical failure) experiments would be unable to carry out their full program of work at the Tier-1. We may suffer reputational damage. | AD | 7 | 5 | 35 | Production team and callout system. Disaster management system. Resilient, segmented infrastructure. Performance metrics. Change control system. Well established hardware procurement system with reserve capacity to handle short term procurement delays. | Much of the work of the team is directed towards ensuring MoU commitments are met. Production team will continue to enhance the services ability to respond rapidly and effectively to problems. Increase further the emphasis on change management and testing. Improve ability to carry out transparent interventions, by architecture, virtualisation and instancing improvements. | 4 | 5 | 20 | q |  |  | 0
5 | Significant loss of custodial data at the T1 | Reputational damage. Although copies are usually held elsewhere in the world copying back to RAL may be operationally problematic or even in extreme cases impossible. | AD | 6 | 8 | 48 | Metadata catalogue backups and live off site copy. Checksums. Media recovery procedures. | Extensive disaster recovery testing. Routine data dipsticking/validation. Regular media repacking. | 3 | 5 | 15 | q |  |  | 0
6 | Substantial loss of or damage to hardware at the T1 (Fire, flood, theft, flooring failure, cooling failure …) hardware damage exceeding £2m | Could not meet MoU commitments. Corrective action would be impossible within existing funding and when funded may take many months to carry out. | AD | 1 | 10 | 10 | Building access control system and physical protection. Environment monitoring, automated shutdown and callout system. Fire alarm and fire suppression system. Cooling system resilience. Disaster management system. | Ensure close liaison with site services to pre-empt weaknesses when they are identified in the infrastructure. | 1 | 10 | 10 | tu |  |  | 0
7 | Significant disaster at the Tier-1, leading to prolonged outage (fire, flood, JANET unavailable for long period, etc.) | Very long term outage of the Tier-1: UK unable to meet its commitments to wLCG over substantial period | AD | 0.5 | 8 | 4 | Environment monitoring and callout system to stop problems becoming critical. Other wLCG Tier-1s take over services. | Resilient site network paths and infrastructure. Attempt to associate UK Tier-2s with other Tier-1s now a possibility owing to improved network infrastructure. | 0.5 | 8 | 4 | tu |  |  | 0
8 | Failure to retain or recruit key technical staff at RAL | Inability to meet GridPP deliverables, milestones and metrics because of lack of staff | DK | 9 | 6 | 54 | Ensure that STFC management are aware of problems when/if they occur | Well documented processes & procedures for key systems are used to share essential knowledge. This allows technical staff to have the minimum knowledge required to ensure critical systems stay online and at a minimum level of operation, in the case of a loss of expertise. Staff given appropriate ownership of key systems, recognition within STFC and opportunities to share key personal successes within the GridPP community (at collaboration and other meetings). Use of apprenticeships and internship where appropriate to help fill the recruitment pipeline. | 7 | 5 | 35 | q |  |  | 0
9 | Failure to procur, deploy or operate hardware at GridPP sites | Problems with procurement such as late delivery or other supplier related issues. Large batches of h/w could fail acceptance testing or develop faults during production use. Significant reduction in capacity could adversly affect GridPP's abilitiy to meet the WLCG MoU commitments. | AD,SS | 6 | 7 | 42 | 1. Monitoring of available disk space/cpu utilisation. 2. Procurements take account of experiment requests. 3.Track hardware failures and observe trends. 4. Documented clear recovery procedures. 5. Throughly test new hardware prior to deployment. 6. Changes in site procurement policy 7. PMB oversight of procurement at GridPP sites. | If jobs do not require site specific data then redirect them to other sites. If data is required then replicate it elsewhere and run jobs. Run a fast procurement to increase capacity - if not a short term effect. Close liason with instituional procurements teams. | 7 | 6.5 | 45.5 | p |  |  | 0
10 | Insufficient Network bandwidth delivered | Lack of bandwidth would prevent data flowing from the Tier 0, & 1 and onto the Tier 2s at a rate sufficient to process the data at required speeds. | PC | 4 | 5 | 20 | The Tier1 has a failover link for the LHCOPN. Tier-2s are liaising with JANET to upgrade links at major sites. | Exploit second OPN link if necessary, Tier-2s are generally well connected and GridPP has good communications links with JANET/JISC. Actual measured throughput should deliver as expected. | 3 | 5 | 15 | q |  |  | 0
11 | Over contention for Resources | Resources are so heaviliy used that conflicts arise between major VOs stemming from a change in experiment requirements subsequent to project proposal. | DB | 4 | 5 | 20 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Purchase more hardware and/or improve profiling and procurement.Reduce non-LHC experiment resources. Agree programme priorities through PMB and STFC. | 3 | 5 | 15 | q |  |  | 0
12 | Unexpected resource requirements by non-LHC VOs | Mandated non-LHC VOs have increased usage requirement that cause conflict with LHC usage. | DB | 5 | 5 | 25 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Look at supporting non-LHC VOs from other funding opportunities such as IRIS fundining. | 1 | 5 | 5 | q |  |  | 0
13 | Unquantfiable impact of BREXIT | 1. Exchange rate volatility 2. Loss of joint funding from EOSC 3. New, restrictive operational constraints | DB | 6 | 6 | 36 | Situation at present makes it difficult to plan strategy | Call upon project contingency | 5 | 6 | 30 | q |  |  | 0
14 | Difficulty with STFC budgets due to Capital vs Resource limitations | The Split of funding between Capital and Resource, can cause problems due to the changing classification of computer equipment | DB | 4 | 6 | 24 | Quarterly review of Tier 1 spending situation. Salaries are always classed as resource, but the boundary for equipment purchases makes predicting the capital requirement difficult. | Increase communications with STFC to ensure plan is appropriate. | 5 | 5 | 25 | p |  |  | 0
15 | Insufficient funding to meet hardware commitments at Tier-1 | Less hardware available to meet international obligations and MoUs as well a suser expectations. See BREXIT risk. | DB | 5 | 5 | 25 | Detailed trends and costings based on 10 years of purchases to maximise resources procured from spends. | Encourge opportunities of sourcing funding from other streams (e.g. IRIS) | 2 | 2 | 4 | q |  |  | 0
16 | GridPP unable to respond to (unexpected) Technology Shifts - WLCG expts exploit new technology not supported at GridPP sites. | In the absence of significant development effort, GridPP would be unable to respond to new developments in technology cause mismatch between experiment processing requirements and available hardware. | DC | 6 | 7 | 42 | New technology directions are closely monitored by involvement in research work groups on Cloud computing, Virtualization, and HEPIX. Changes are expected by the end of the project. GridPP technology group meets regularly. | Work packages invest some small fraction of effort directly on new technologies with a view to bringing them mainstream when both mature enough and appropriate to the overall project. WLCG TEGs and WLCG TDR update. This could be mitagated by the effor tin the 110% scenario | 4 | 5 | 20 | q |  |  | 0
17 | Loss of experienced personnel or insufficient manpower at T2s | Sites may not be able to diagnose and fix problems as quickly. Ability to react to changing situations or to upgrade will be compromised. | RJ | 7 | 5 | 35 | GridPP6 staffing levels predicted. Multiple Tier-2s provide resilience to the project. | Two people at main sites. Grid Operations team spreads knowledge and expertise across sites. New models of working adopted to cope with falling staff levels at smaller sites. | 4.5 | 4.5 | 20.25 | q |  |  | 0
18 | Insufficient funding to meet hardware commitments at T2s | Less hardware available to meet international obligations and user expectations. | RJ | 2 | 4 | 8 | Funding models are different at different sites. Not all sites would be affected the same way and some sites may be able to add resources to compensate. | Encourage opportunistic use of more central resources. Encourage experiments to prioritise and make more efficient use of resources. | 2 | 2 | 4 | q |  |  | 0
19 | Middleware or software at T2 sites not fit for purpose | Lack of staffing at Tier-2 sites reducing effort to respond to poor or non-functional middleware. Complex middlware takes significant effort to plan upgrades, deploy and test. | RJ | 5 | 6 | 30 | The same middleware and software is used at T1 and T2 sites across the world. wLCG will work with experiments to solve problems. | Community effort and shared knowledge is distributed trough week operations and storage meetings. Bi-weekly technical meetings held to discuss pain points in detail | 4 | 6 | 24 | q |  |  | 0
20 | Experiment software runs inefficiently, to the detriment of UK physicists | Workload would not be able to fully exploit the resources available. Expts would need to invest effort in improved computing model. | SS | 7 | 6 | 42 | Experiments have reviewed computing models in preparation for LHC Run 3. Special arrangements are made for certain customers. | Experiment support posts and the grid support team will be available to all sites. Good dialogue with special customers required to ensure appropriate planning. | 3 | 4 | 12 | q |  |  | 0
21 | Reputation risk due to a serious security problem | Security problems may bring down the whole of GridPP or even wLCG, given that all Sites run very similar software. A major outage is likely to attract significant outside interest and GridPP is likely to suffer damage to its reputation. Threats rising and ability to deal with is decreasing and impact on operations is rising | DK | 8 | 8 | 64 | Act on many fronts in parallel to handle vulnerabilities to avoid incidents, to contain and handle incidents quickly when they do happen and define and enforce appropriate policies to control actions of participants. Dedicated security resource part of GridPP6. | We lead the Joint Security Policy Group of wLCG/EGI, the security vulnerability group of EGI . Established experienced security team in place. Many staff have recently recieved security training. New closer relations are being developed with IRIS and JISC security teams and a stronger monitoring and reporting on patching status is being developed. | 5 | 7 | 35 | q |  |  | 0
22 | Non-availability of T1 &2 service or compromised data due to security vulnerability | Extended service downtime, loss of data, inability to process and analyse data. | DK | 8 | 7 | 56 | Well organised operational security incident handling led by the GridPP Security Officer in collaboration with the Tier 1 and Tier 2 system managers. Vulnerabilities in the middleware are handled today by EGI to prevent incidents happening | The GridPP security effort is essential to reduce the risks from known security vulnerabilities, to handle incidents when they do occur, to train system managers, to define and encourage security best practice, e.g. timely system patching, and to continuously monitor the status. Many staff have recently recieved security training. | 5 | 7 | 35 | q |  |  | 0
23 | Insufficient effort to support the VOs or the users | New user groups (VOs) or users of the main LHC VOs are not able to make use of the Grid to do their research. | SS | 7 | 5 | 35 | Dedicated experiment support post at the Tier-1 and Tier-2 s for LHC Vos however an increase in non LHC VOS could stretch resources. Extensive Web documentation. User Coordinator can liaise with the experimental users. | Tier-1 resource meeting with the User Coordinator provides a forum to discuss new user requirements. GridPP-Support mailing list setup to coordinate help to new users. | 3 | 5 | 15 | q |  |  | 0
24 | Mismatch between budget and hardware costs | Project would not be able to deliver the pledged resources resulting in (a) political damage and eventually (b) disadvantage to the UK experiments as the level of resource falls | DB | 9 | 7 | 63 | Monitor UK purchases for last 10 years and extrapolate with comprehensive modelling. | Cross check with CERN predictions but there is a residual exchange rate uncertainty on top of the technological uncertainty. | 4 | 6 | 24 | q |  |  | 0
25 | Funding for central services that GridPP relys on insufficiently funded. | Resources within the NGI on which GridPP is planning to rely are not available. For example, the Certificate Authority is not funded or has inadequate effort to meet GridPP needs. | DB | 5 | 4 | 20 | Close collaboration with STFC to ensure GridPP is aware of progress and any issues. | Call on GridPP contingency to fund extra posts to cover the core staff. | 4 | 2 | 8 | q |  |  | 0
26 | Breakdown of core operations structures - for example in the NGI/EGI infrastructure | Without a central ticketing (GGUS) interface or Grid Operations database the ability to follow up on problems, inform of upcoming downtimes and general communications between sites and users is interrupted. | SS | 3 | 3 | 9 | Core services are hosted on high-availability hardware. The GOCDB has a failover capability to another region. See BREXIT risk for assocated operating risk. | NGI structure in place and the existing central instances serve as a backup. After the transition the UK instances will be placed on high resilience equipment and procedures put in place for rapid deployment of new services. | 3 | 3 | 9 | tu |  |  | 0
27 | Insufficient travel funds for effective engagement and contribution to wLCG and for internal operation of GridPP. | GridPP would experience difficulty in keeping up with developments in operations, in updating staff skills (through attendance at technical meetings) and in keeping up to date with experiment requirements. | DK | 4 | 2.5 | 10 | Careful management of resources and prioritisation to ensure sufficient travel funds are available | Increase the use of phone and video conferencing for attending meetings (though noting such facilities are not always available and they are frequently less optimal than attendance in person). | 3 | 2.5 | 7.5 | q |  |  | 0
29 | Critical middleware no longer supported | The significant Grid middleware code base needs to be properly maintained and supported throughout the project. The development community is now reduced to a skeleton staff and maintenance problems can arise especially with data management components. | DC | 5 | 6 | 30 | Existing GGUS mechanisms enable bug reporting by sysadmins to a small number of expert developers. Data support staff enable appropriate deployment choices, workarounds and bug fixes to be made. | Culture of fully-tested code and minimal change established. Maintenance of expertise and support staff in recognised critical areas. Reductions in functionality, if necessary. Community based support model in process of being established. | 5 | 5 | 25 | q |  |  | 0
30 | Unplanned infrastructure costs | If extra costs arise at the T1 or T2, there is the possibility that funds will not be sufficient to buy the required hardware. Risks failing to meet WLCG pledge, and reputation risk. Risk of needing to ration resources due to electricity etc costs | SS/PG | 4 | 4 | 16 | Tier-2 costs spread across sites - if one site cannot meet the price GridPP is paying, then other sites can increase their share. Increasing risk of electricity costs or networking costs. | GridPP contingency available for extra costs at the Tier-1 or systematic increases at the Tier-2s. | 3 | 5 | 15 | q |  |  | 0
31 | EGI does not continue or the UK does not continue to be a member. | Access to services run by EGI, Loss of co funding for services run within the UK. Loss of access to future funding oportunities, such as Horizon 2020. | DK/AD | 4 | 3 | 12 | Essential posts are part of the GridPP6. Possible BREXIT implications, see BREXIT risk. | Call on GridPP contingency to fund necessary posts. Reallocate work to other staff if possible. | 3 | 2 | 6 | q |  |  | 0
32 | Financial Uncertainty | Uncertainties can make staff retention difficult. Lack of long term funding would result in inadequate resources and service being provided to serve the needs of the UK Particle Physics Community. | DB | 5 | 6 | 30 | GridPP6 funding approved but still longer term uncertainities with Government funding. | Raise issues with GridPP Oversight Committee and directly with STFC | 3 | 4 | 12 | q |  |  | 0
33 | Conflicting opinions amongst GridPP stakeholders | Disatisfaction amoungst users or site administrators could result in reduced utilisation of the resources and adversly affect the quality of research carried out. | DB | 3 | 5 | 15 | 1. Weekly PMB meetings. PMB minutes widely circulated to members of the community. Operations and sites meetings held weekly, with good coomunication between the PMB and the OPS team via cross membership. Collaboration meetings held regularly. | More F2F meetings, More CB meetings, Sites visits. | 2 | 4 | 8 | q |  |  | 0