## Resource & Narrative
Year | 2022 | Area | Tier-1
Quarter | Q2 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
Tape System (Castor, Antares)
Disk (Echo) | VOs migrate to using Webdav for TPC. |  |  | Long running problem with LHCb claiming their analysis jobs not being able to access their data correctly.
Batch System
Network | Continuing to migrate hardware to new network.
Other
Risks
Type | Risk |  |  | Mitigation
General | Delays in procurement deliery due to global supply chain issues. |  |  | We are placing orders as soon as possible.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2022-03-31 | Delivery of CPU procurement |  |  | Hardware was delivered at the start of December but was lacking NICs. We have order some replacement temporary NICs.

## Metrics & Milestones
Metrics | [8 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Notes | Colour | Description | Code
1a | 1 | 100% | 5% | 111% | MOK | % of GridPP commitment for CPU |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric OK | MOK
1a | 2 | 100% | 5% | 112% | MOK | % of GridPP commitment for Disk |  | Calculated from Allocations.xlsx using [Total Capacity] / [Total Commitment] in the final month of the quarter. |  | Metric Clost to Target | MCT
1a | 3 | 100% | 5% | 107% | MOK | % of GridPP allocation for Tape |  | Calculated from Allocations.xlsx using [Available Capacity] / [Total Commitment] in the final month of the quarter. Note the Total Commitment is lower than the total request because we buy Tape when required. |  | Metric not OK | MFL
1a | 4 | 94% | 5% | 101.9% | MOK | % of GridPP6 Staff funded |  |  |  | Metric with no Target | MNO
1a | 5 | 98% | 3% | 98.33% | MOK | WLCG Service Availability for Alice |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2022/06-22/WLCG_Tier1_History_ALICE_Jun2022.pdf
1a | 6 | 98% | 3% | 99.33% | MOK | WLCG Service Availability for ATLAS |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2022/06-22/WLCG_Tier1_History_ATLAS_Jun2022.pdf
1a | 7 | 98% | 3% | 91.33% | MFL | WLCG Service Availability for CMS | Availability is improving compared to last quarter, since new CMS test was added. | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2022/06-22/WLCG_Tier1_History_CMS_Jun2022.pdf
1a | 8 | 98% | 3% | 99.33% | MOK | WLCG Service Availability for LHCB |  | https://wlcg-docs.web.cern.ch/reporting/reliability-availability/2022/06-22/WLCG_Tier1_History_LHCB_Jun2022.pdf
1a | 9 | 90% | 20% | 83.89% | MCT | % usage by ATLAS of their CPU pledge |  | ATLAS Pledge = 192557 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 10 | 80% | 20% | 102.6% | MOK | % usage by ATLAS of their Disk pledge | There was a spike in usage when the pledges were being updated. ATLAS have subsequently run a dark data cleanup. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2022-06-30.json
1a | 11 | 80% | 20% | 93.96% | MOK | % usage by ATLAS of their Tape pledge |  | Manual Tape Accounting currently for Antares.
1a | 12 | 90% | 20% | 180.6% | MOK | % usage by CMS of their CPU pledge |  | CMS Pledge = 52000HS06 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 13 | 80% | 20% | 88.4% | MOK | % usage by CMS of their Disk pledge |  | https://s3.echo.stfc.ac.uk/srr/storagesummary_2022-06-30.json
1a | 14 | 80% | 20% | 83.32% | MOK | % usage by CMS of their Tape pledge |  | Manual Tape Accounting currently for Antares.
1a | 15 | 90% | 20% | 128.3% | MOK | % usage by LHCb of their CPU pledge |  | LHCb Pledge = 146665 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 16 | 80% | 20% | 57.17% | MFL | % usage by LHCb of their Disk pledge | Pledge increased by 3.6PB which LHCb were unable to immediately use. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2022-06-30.json
1a | 17 | 80% | 20% | 41.77% | MFL | % usage by LHCb of their Tape pledge | Pledge increased by almost 15PB which LHCb will only make use of as data is taken. | Manual Tape Accounting currently for Antares.
1a | 18 | 90% | 20% | 105.1% | MOK | % usage by ALICE of their CPU pledge |  | ALICE Pledge = 14903 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 19 | 80% | 20% | 39.57% | MFL | % usage by ALICE of their Disk pledge | ALICE have not started significantly increasing their disk usage yet. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2022-06-30.json
1a | 20 | 80% | 20% | 46.79% | MFL | % usage by ALICE of their Tape pledge | ALICE have not been writing to tape during the long shutdown. | Manual Tape Accounting currently for Antares.
1a | 21 | 40% | 30% | 13.92% | MCT | % usage by non-LHC VOs of their CPU allocation |  | Total Pledge * 0.13 = 52796 https://accounting.egi.eu/tier1/node/UK-T1-RAL/normelap_processors-quarter/VO/DATE/2022/04/2022/06/custom-biomed,dune,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 22 | 80% | 20% | 110.5% | MOK | % usage by non-LHC VOs of their Disk allocation | Currently only Dune using Echo. Dune appear to have a dark data problem which we are investigating. | https://s3.echo.stfc.ac.uk/srr/storagesummary_2022-06-30.json
1a | 23 | 80% | 20% | 137.2% | MOK | % usage by non-LHC VOs of their Tape allocation |  | Total Pledge * 0.1 = 9255TB Usage calculated from printTapeUsage.py
1a | 24 | 90% | 10% | 85.83% | MCT | GridPP Funded Farm Occupancy | Long outage of the farm during network segmentation work in June reduced overall occupancy. | https://vande.gridpp.rl.ac.uk/next/d/3NOsnhnMz/batch-system-capacity?orgId=1&from=1633042800000&to=1640995199000&viewPanel=3
1a | 25 | 80% | 10% | 78.78% | MCT | % Total Disk Usage | Pledge increase means not all capacity was used immediately. | ResourceUsage spreadsheet
1a | 26 | 80% | 10% | 90.83% | MOK | % Total Tape Usage |  | ResourceUsage spreadsheet
1a | 27 | 70% | 20% | 89.48% | MOK | % Job Efficiency (CPU/Wall) - ATLAS |  | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 28 | 70% | 20% | 85.95% | MOK | % Job Efficiency (CPU/Wall) - CMS | Significantly better than previous quarter. Full impact of network improvements have not yet been realised. | See Above
1a | 29 | 70% | 20% | 107.7% | MOK | % Job Efficiency (CPU/Wall) - LHCb |  | See Above
1a | 30 | 70% | 20% | 95.45% | MOK | % Job Efficiency (CPU/Wall) - ALICE |  | See Above
1a | 31 | 70% | 20% | 74.21% | MOK | % Job Efficiency (CPU/Wall) - non-LHC |  | https://accounting.egi.eu/tier1/node/UK-T1-RAL/cpueff/VO/DATE/2022/4/2022/6/custom-biomed,dune,enmr.eu,gridpp,hyperk.org,ilc,lsst,na62.vo.gridpp.ac.uk,ops,pheno,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo/onlyinfrajobs/
1a | 32 | 95% | 5% | 95.62% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ATLAS | CERN reported an efficiency of 156%. I have excluded them from the calculations as it completely skews the result. | https://accounting.egi.eu/tier1/cpueff/VO/TIER1/2022/04/2022/06/lhc/onlyinfrajobs/
1a | 33 | 95% | 5% | 117.4% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - CMS |  | See Above
1a | 34 | 95% | 5% | 107.6% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - LHCb |  | See Above
1a | 35 | 95% | 5% | 138% | MOK | Relative Job Efficiency RAL(CPU/Wall) / <Tier-1>(CPU/Wall) - ALICE |  | See Above
1a | 36 | 100% | 5% | 100% | MOK | % of GGUS Tickets Handled | Need to create a more useful metric | https://ggus.eu/index.php?mode=ticket_search&su_hierarchy=0&status=all&affectedsite=RAL-LCG2&date_type=creation+date&timeframe=lastweek&tf_radio=2&from_date=01+Apr+2022&to_date=30+Dec+2022&ticket_category=all&typeofproblem=all&specattrib=none&orderticketsby=REQUEST_ID&orderhow=desc&ticket_per_page=50&show_columns_check%5B0%5D=TICKET_TYPE&show_columns_check%5B1%5D=AFFECTED_VO&show_columns_check%5B2%5D=AFFECTED_SITE&show_columns_check%5B3%5D=PRIORITY&show_columns_check%5B4%5D=RESPONSIBLE_UNIT&show_columns_check%5B5%5D=STATUS&show_columns_check%5B6%5D=DATE_OF_CHANGE&show_columns_check%5B7%5D=SHORT_DESCRIPTION&show_columns_check%5B8%5D=SCOPE&search_submit=Search
1a | 37 | 30 | 10 | 0 | MOK | Average number of security vunerabilities | Major patching camapign mandated by UKRI | https://pakiti-1.gridpp.rl.ac.uk/pakiti/ Take Average Security in gridpp.rl.ac.uk domain
Milestones | [8 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Comments | Colour | Description | Code
1a | 1 | 2020-11-01 | N |  | MSU | GridPP review of operation (biennial) | Cancelled because of Pandemic |  |  | Milestone Achieved | MSA
1a | 2 | 2022-10-01 | N |  | MSU | GridPP review of operation (biennial) |  |  |  | Milestone Ongoing | MOG
1a | 3 | 2020-06-01 | 2020-04-01 | 2020-06-01 | MSA | Produce the purchasing plan |  |  |  | Milestone Overdue | MOD
1a | 4 | 2020-11-01 | 2020-09-01 | 2020-09-01 | MSA | FY20 Capacity order placed |  |  |  | Milestone not due | MSU
1a | 5 | 2021-04-01 | 2021-01-01 | 2021-07-01 | MOD | FY20 Purchase in production | Expected to enter production in June 21
1a | 6 | 2021-04-01 | 2021-04-01 | 2021-04-01 | MSA | Tier-1 WLCG MoU commitments met
1a | 7 | 2021-06-01 | 2021-05-01 | 2021-06-01 | MSA | Produce the purchasing plan
1a | 8 | 2021-11-01 | 2021-06-01 | 2021-08-01 | MSA | FY21 Capacity order placed
1a | 9 | 2022-04-01 | N |  | MSU | FY21 Purchase in production
1a | 10 | 2022-05-01 | Y | 2022-04-01 | MSA | Tier-1 WLCG MoU commitments met
1a | 11 | 2022-06-01 | Y | 2022-04-01 | MSA | Produce the purchasing plan
1a | 12 | 2022-11-01 | N |  | MSU | FY22 Capacity order placed
1a | 13 | 2023-04-01 | N |  | MSU | FY22 Purchase in production
1a | 14 | 2023-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met
1a | 15 | 2023-06-01 | N |  | MSU | Produce the purchasing plan
1a | 16 | 2023-11-01 | N |  | MSU | FY23 Capacity order placed
1a | 17 | 2024-04-01 | N |  | MSU | FY23 Purchase in production
1a | 18 | 2024-05-01 | N |  | MSU | Tier-1 WLCG MoU commitments met

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
2021-08-01 | Designing the RAL Tier-1 Network for HL-LHC and Future data lakes, https://doi.org/10.1051/epjconf/202125102074
2021-08-01 | Public Engagement in a Global Pandemic, https://doi.org/10.1051/epjconf/202125101005
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes