## Resource & Narrative
Year | 2022 | Area | LondonGrid
Quarter | Q2 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel | New CEPHFS (2PB raw) in test. It should finally go in production in Q3 New 1000 cores to go in production
Imperial | Added some GPU resources to Openstack cloud Upgraded dCache Set up tokens for ATLAS
QMUL | Terry left 1 June, had hand over of infrastructure and documentation.
RHUL | condor is updated to scitokens/GSI compatible version DPM is updated. Scitokens implemented for Atlas and CMS Nodes are being patched and rebooted 3/4 done Storages are being patched are rebooted 3/4 done. |  |  | Intermittent network problems.
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL | Continued delay in upgrading WAN to 100G |  |  | None
RHUL | Continued delay in IPV6 deployment |  |  | IT service looking for external ipv6 dns resolver
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 358.9% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 394.1% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 82.06% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 98.11% | MOK | Average Argo Availability - LondonGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 98.52% | MOK | Average Argo Reliability - LondonGrid

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 52831 | 160000 | 112500 | 56000 | 381331 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 20152 | 29377 | 22055 | 34668 | 106252 | (plus 10% here for Other Vos)
% of Pledge | 262.2% | 544.6% | 510.1% | 161.5% | 358.9%
Storage Available (TB) | 1140 | 20600 | 15000 | 1300 | 38040
Storage Pledged (TB) | 1016 | 3412 | 5225 | 0 | 9653
% of Pledge | 112.2% | 603.8% | 287.1% | #DIV/0! | 394.1%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 100 | 100 | 99.96 | 82.96 | 95.73% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 100 | 96.55 | 100 | 99.14% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 99.17 | 99.99 | 98.73 | 99.47%
% Tier-2 Averge | 100 | 99.7233 | 98.8333 | 93.8967 | 98.11%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 100 | 99.14 | 99.96 | 84.41 | 95.88% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 99.85 | 99.8 | 100 | 99.91% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 99.17 | 99.99 | 99.95 | 99.78%
% Tier-2 Total | 100 | 99.3867 | 99.9167 | 94.7867 | 98.52%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 115382904 | 349440000 | 245700000 | 122304000 | 832826904 | https://accounting.egi.eu/tier2/federation/London Tier 2/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 16517793.0355 | 85617260.831 | 40908309.8837 | 20217760.3946 | 163261124.1448 | Q1: 2160/2184 (if leap year)
Month 2 | 16339837.2617 | 88068678.3805 | 50627594.2902 | 27732892.7139 | 182769002.6463 | Q2: 2184
Month 3 | 15212271.8576 | 84023690.7191 | 38599567.5716 | 28384138.7585 | 166219668.9068 | Q3: 2208
Total: | 48069902.1548 | 257709629.9306 | 130135471.7455 | 76334791.867 | 512249795.6979 | Q4: 2208
% Utilisation | 41.66% | 73.75% | 52.97% | 62.41% | 61.51%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 115382904 | 349440000 | 245700000 | 122304000 | 832826904 | https://accounting.egi.eu/tier2/federation/London Tier 2/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 25279366.663 | 112771124.7857 | 40492457.209 | 23198425.9864 | 201741374.6441 | Q1: 2160/2184 (if leap year)
Month 2 | 24281396.7986 | 124157846.0502 | 68167424.5227 | 30147165.2915 | 246753832.663 | Q2: 2184
Month 3 | 23976143.005 | 124871781.8973 | 56521265.8143 | 29590100.0305 | 234959290.7471 | Q3: 2208
Total: | 73536906.4666 | 361800752.7332 | 165181147.546 | 82935691.3084 | 683454498.0542 | Q4: 2208
% Utilisation | 63.73% | 103.5% | 67.23% | 67.81% | 82.06%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 16 | 0 | 9500 | 905 | 10421 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1000 | 11534.424 | 0 | 2.2 | 12536.624 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0.053 | 671.122 | 300 | 0 | 971.175
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1200 | 1100 | 0 | 2300
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 14.5 | 0 | 8699 | 662 | 9375.5 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 586 | 7003.434 | 0 | 1.51 | 7590.944 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 484.046 | 251 | 0 | 735.046
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 399.6 | 679 | 0 | 1078.6
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0 | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 40 | 0 | 0 | 40 | https://accounting.egi.eu/tier2/federation/London Tier 2/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
dune | 0 | 0 | 679 | 0 | 679 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0 | 0 | 0.075 | 0.006 | 0.081 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.811 | 0.181 | 0 | 77.992
lz | 0 | 3852 | 0 | 0 | 3852
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.009 | 0.02 | 0.037
skatelescope.eu | 0 | 0.05 | 0.236 | 0 | 0.286
snoplus.snolab.ca | 0 | 0 | 11.43 | 0 | 11.43
solidexperiment.org | 0 | 634.555 | 0 | 0 | 634.555
t2k.org | 0 | 46.437 | 207.94 | 0 | 254.377
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0 | 0 | 0 | 0 | 0
mice | 0 | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 9.91 | 0 | 9.91
fusion | 0 | 0 | 0 | 0.009 | 0.009
cernatschool.org | 0 | 0 | 0.072 | 0 | 0.072
hyperk.org | 0 | 0 | 0.64 | 0 | 0.64
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes