## Resource & Narrative
Year | 2022 | Area | NorthGrid
Quarter | Q2 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | The CEPH is fully in production now (and has been since the very start of the quarter). Some cluster work and old node retirements throughout the period caused a slight reduction of CPU delivered. |  |  | Slightly off storage figures whilst DPM and CEPH coexist. A few mild teething problems.
Liverpool | Unstable DPM pool nodes drained and retired. Future network changes briefly discussed with university network team: campus hardware upgrades expected in the next 6-12months, with possible throughput upgrades and production IPv6 enabling, but with potentially lots of disruption. Site host certificates annual renewal completed.
Manchester
Sheffield | Business as usual.
Risks
Type | Risk |  |  | Mitigation
Lancaster | Still some xroot performance fears until rucio file plugin implimented AND we have redirection in place. |  |  | Speed up rolling out xrootd redirection
Liverpool
Manchester
Sheffield
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
April | Lancaster-CEPH/xroot fully commissioned |  |  | 10PB extra capacity
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
August | Lancaster - Decommission DPM for atlas and others Lancaster – impliment xroot redirection |  |  | More use of the CEPHFS, less use of the DPM Increase resilience and bandwidth

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% | 211.8% | MOK | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% | 222.8% | MOK | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% | 98.24% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid | Need to look into this – under reporting capacity? |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 99.58% | MOK | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 99.92% | MOK | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 106000 | 35047 | 95006 | 11918 | 236053 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 36671 | 11470 | 59053 | 4261 | 111455 | (plus 10% here for other Vos)
% of Pledge | 289.1% | 305.6% | 160.9% | 279.7% | 211.8% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 12000 | 900 | 6820 | 0 | 19720
Storage Pledged (TB) | 2837 | 330 | 5685 | 0 | 8852
% of Pledge | 423% | 272.7% | 120% | 100% | 222.8%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 100 | 95 | 100 | 98.75% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 100 | 100 | 100 | 100% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 100 | 100 | 100%
% Tier-2 Averge | 100 | 100 | 98.3333 | 100 | 99.58%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 100 | 99 | 100 | 99.75% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 100 | 100 | 100 | 100% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 100 | 100 | 100%
% Tier-2 Total | 100 | 100 | 99.6667 | 100 | 99.92%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 231504000 | 76542648 | 207493104 | 26028912 | 541568664 | https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 59475221 | 20974950 | 61294037 | 4148672 | 145892880 | Q1: 2160/2184 (if leap year)
Month 2 | 58057364 | 20655208 | 68137494 | 6269187 | 153119253 | Q2: 2184
Month 3 | 62312364 | 22458961 | 73348141 | 6237927 | 164357393 | Q3: 2208
Total: | 179844949 | 64089119 | 202779672 | 16655786 | 463369526 | Q4: 2208
% Utilisation | 77.69% | 83.73% | 97.73% | 63.99% | 85.56% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 231504000 | 76542648 | 207493104 | 26028912 | 541568664 | https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 70023691 | 23478785 | 66837927 | 4100377 | 164440780 | Q1: 2160/2184 (if leap year)
Month 2 | 74076854 | 24046226 | 74341190 | 6654056 | 179118326 | Q2: 2184
Month 3 | 79677182 | 23591066 | 78441273 | 6743548 | 188453069 | Q3: 2208
Total: | 223777727 | 71116077 | 219620390 | 17497981 | 532012175 | Q4: 2208
% Utilisation | 96.66% | 92.91% | 105.8% | 67.23% | 98.24%
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 6800 | 473 | 4150 | 0 | 11423 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 313 | 300 | 0 | 613
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 1060 | 0 | 980 | 0 | 2040
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3800 | 398 | 3750 | 0 | 7948 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 234 | 210 | 0 | 444
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 586 | 0 | 595 | 0 | 1181
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 25 | 0 |  | 43 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 1.4 | 0.3 | 0 |  | 1.7 | https://accounting.egi.eu/tier2/federation/NorthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.5 | 0 |  | 2.5 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.1 | 0 |  | 0.1
gridpp | 0.001 | 0 | 0 |  | 0.001
lsst | 0 | 1 | 0 |  | 1
dune | 0 | 0.6 | 0 |  | 0.6
mu3e.org | 0 | 77 | 0 |  | 77
hyperk.org | 18.6 | 0 | 0 |  | 18.6
| 0 | 0 | 0 |  | 0
lsst (iris) | 91 | 0 | 0 |  | 91
dune (iris) | 436 | 0 | 0 |  | 436
vo.cta.in2p3.fr (iris) | 150 | 0 | 0 |  | 150
ska.telescope.eu (iris) | 0.3 | 0 | 0 |  | 0.3
0
0
0
0
0
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes