## Resource & Narrative
Year | 2022 | Area | ScotGrid
Quarter | Q2 | Reporter | GS
Narrative
Area | Successes |  |  | Problems
Durham | Developed Single Sign On and Multi-Factor Auth with Keycloak and PrivacyIDEA for the IPPP, this may be applied to some Pheno grid services. |  |  | EL8 isn't being fully adopted by the grid and so we require a jump to EL9, meaning some previous work was wasted. Power issues in the Data Centre caused a major outage (~1 day) of Grid services.
Edinburgh | Brought new NFS online with ALMA9.0+SQUID+ZFS+NFS+selinux and upgraded storage to support PPE use of Tier2 cluster. Managed to update HV to CentOS8-Stream to pick up new qemu/libvirtd and security updates. |  |  | Fast communication between cluster management team and GridPP @UoE difficult during this summer due to backlog of maintenance projects from when the world went mad. Discovered undocumented settings on our immediate upstream switch indicating we need to understand our networking better. IPv6 @UoE is not quite yet a 1st class citizen.
Glasgow | New compute, GPU node and most storage commissioned. Management network introduced to simplify remote access and permit use of Dell OpenManage, simplifying support load. |  |  | IPv6 at Glasgow also not a 1st class citizen.
Risks
Type | Risk |  |  | Mitigation
Durham | Campus IT (CIS) are working to secure the IT infra better. |  |  | We're part of the CIS Dispersed IT Operations working group to mitigate knee jerk reactions that would cause issues.
Edinburgh | Old storage fails in some catasrophic way. We don't directly manage our CE. Networking at ACF is rapidly evolving. Space at ACF is in high demand and is decreasing. |  |  | Reduce capacity and increase reliability at site. Working on keeping good communication with team managing shared compute cluster.
Glasgow | Continued water ingress in old server room brings ceiling down on top of DPM. |  |  | Working to decommission remaining DPM storage ASAP.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Edinburgh: new RPM repo for Voms data |  |  | new testing signed RPM repo for updating VOMS data
| Edinburgh: fix ansible playbooks for site |  |  | site ansible playbooks are now up to date
| Edinburgh: further automate site maintenance |  |  | additional playbooks which automate general maintenance performed at site
| Edinburgh: enable https on CE |  |  | no more (harmless) https errors from CE
| Edinburgh: investigate d-RAID on ZFS |  |  | Further simplify deployment and increase reliability of unreliable storage
| Edinburgh: Test setting up a kubernetes cluster in a box |  |  | Failed to get a chance to set this up
| Edinburgh: Continue to support stashcache |  |  | A working stashcache instance to support DUNE
| Edinburgh: Invest effort in better monitoring |  |  | Have deployed OpenSearch cluster for monitoring which can be upgraded live without service downtime
| Durham: Shared Fail2Ban Production Ready |  |  | Waiting on Durham COSMA/DiRAC HPC and Durham ARC for our first "production" installs to finalise documentation.
| Durham: Migrate services to Rocky Linux 8 |  |  | Rocky Linux 8 is the base OS for grid services.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
| Durham: Shared Fail2Ban Production Ready |  |  | Waiting on Durham COSMA/DiRAC HPC and Durham ARC for our first "production" installs to finalise documentation.
| Durham: Migrate services to Rocky Linux 8/9. |  |  | Rocky Linux 8/9 is the base OS for grid services.
| Durham: 40GB/s WAN Link. |  |  | We have 40Gb/s WAN. (Pigs might fly?)
| Edinburgh: Make new signed VOMS repo under `voms.edi.scotgrid.ac.uk` |  |  | voms data will be more regularly updated in RPM format and shared from a supported secure gridpp host.
| Edinburgh: Induct new member of staff |  |  | Someone taking some of the load off whilst also contributing to XCache monitoring efforts.
| Edinburgh: Investigate selinux on more systems |  |  | After deploying selinux on shared NFS server want to investigate potential for deploying this across rest of Tier2 estate.
| Edinburgh: Contiune with StashCache/XCache monitoring developments |  |  | Produce monitoring plots showing usage and optionally ways to improve XCache use at site

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 3 | 100% | 5% | 265.5% | MOK | % of WLCG Pledged CPU Available - ScotGrid |  |  | Metric OK | MOK
1b | 7 | 100% | 5% | 124.2% | MOK | % of WLCG Pledged Disk Available - ScotGrid |  |  | Metric Clost to Target | MCT
1b | 11 | 50% | 5% | 121.3% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid |  |  | Metric not OK | MFL
1b | 17 | 95% | 5% | 97% | MOK | Average Argo Availability - ScotGrid |  |  | Metric with no Target | MNO
1b | 18 | 95% | 5% | 97.05% | MOK | Average Argo Reliability - ScotGrid

## Resources
Please fill in all fields highlighed in
Capacities | Durham | Edinburgh | Glasgow | Total | Notes
CPU Available (HS06) | 45000 | 10000 | 150000 | 205000 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 21052 | 8727 | 47422 | 77201 | (plus 10% for other Vos)
% of Pledge | 213.8% | 114.6% | 316.3% | 265.5%
Storage Available (TB) | 300 | 1000 | 5000 | 6300
Storage Pledged (TB) | 0 | 0 | 5071 | 5071
% of Pledge | #DIV/0! | #DIV/0! | 98.6% | 124.2%
Availability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 98.95 | 93.65 | 99.45 | 97.35% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 99.75 | 100 | 99.48 | 99.74% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 81.7 | 93.9%
% Tier-2 Averge | 99.5667 | 97.8833 | 93.5433 | 97%
Reliability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 99.45 | 93.65 | 99.45 | 97.52% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 99.75 | 100 | 99.48 | 99.74% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 81.7 | 93.9%
% Tier-2 Total | 99.7333 | 97.8833 | 93.5433 | 97.05%
CPU Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 98280000 | 21840000 | 327600000 | 447720000 | https://accounting.egi.eu/tier2/federation/ScotGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 50882589 | 10528101 | 71772363 | 133183053 | Q1: 2160/2184 (if leap year)
Month 2 | 56283950 | 7292980 | 84452640 | 148029570 | Q2: 2184
Month 3 | 54191405 | 7413417 | 98785131 | 160389953 | Q3: 2208
Total: | 161357944 | 25234498 | 255010134 | 441602576 | Q4: 2208
% Utilisation | 164.2% | 115.5% | 77.84% | 98.63%
WallClock Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 98280000 | 21840000 | 327600000 | 447720000 | https://accounting.egi.eu/tier2/federation/ScotGrid/normelap_processors/SITE/DATE/2021/1/2020/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 63554524 | 12204284 | 106548853 | 182307661 | Q1: 2160/2184 (if leap year)
Month 2 | 62431559 | 11678215 | 109480928 | 183590702 | Q2: 2184
Month 3 | 56787883 | 9353235 | 111090151 | 177231269 | Q3: 2208
Total: | 182773966 | 33235734 | 327119932 | 543129632 | Q4: 2208
% Utilisation | 186% | 152.2% | 99.85% | 121.3% | ECDF cloud wallclock = (1.046 * CPU hours based on historical performance)
Storage LHC & IRIS: AVAILABLE (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 265 | 750 | 4200 | 5215 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 300 | 300
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 235 | 699.14 | 1760 | 2694.14 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 1 | 1 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 72 | 72
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
biomed | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
cernatschool.org | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/ScotGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
clas12 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
comet.j-parc.jp | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dune | 0 | 0 | 0 | 0
gridpp | 0 | 1 | 2 | 3
hyperk.org | 0 | 0 | 0 | 0
ilc | 0 | 0 | 0 | 0
iris.ac.uk | 0 | 0 | 0 | 0
lhcb | 0 | 0 | 0 | 0
lsst | 0 | 0 | 0 | 0
lz | 0 | 0 | 0 | 0
magrid | 0 | 0 | 0 | 0
mice | 0 | 0 | 1.9 | 1.9
na62.vo.gridpp.ac.uk | 0 | 0 | 3.8 | 3.8
ops | 0 | 0 | 0 | 0
pheno | 66 | 0 | 7.5 | 73.5
skatelescope.eu | 0 | 0 | 0 | 0
snoplus.snolab.ca | 0 | 0 | 0 | 0
solidexperiment.org | 0 | 0 | 0 | 0
t2k.org | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 0 | 0
vo.northgrid.ac.uk | 0 | 0 | 0 | 0
vo.scotgrid.ac.uk | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Ongoing | LSST, Escape, astro | Rob assisting astro people in Edinburgh with grid usage.
Ongoing | LZ | ECDF aiding in moving some workloads to the Grid.
Ongoing | DUNE | Provided effort into DUNE RUCIO deployment and data management
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Present | UK Members of DPM Collaboration | UK Data Storage (S. Skipsey)
Present | HTTP Deployment Working Group | S. Skipsey
Present | Member of Tier-2 Evolution Working Group | S.Skipsey
Present | Member of WLCG SOC WG | Adam Boutcher
Present | Member of WLCG SOC WG | Paul Clark
Present | Durham DITO - Business Continuity WG | Adam Boutcher
Present | Durham DITO - Cyber Security WG | Paul Clark
Present | Member of the WLCG DOMA-QoS WG | Robert Currie
Date | Other Outputs and Knowledge Exchange | Notes
Present-Sept2022 | Durham Physics Award for Excellence. | Adam & Paul have been nominated & Awarded this for IPPP/Grid IT Support at Durham.