## Resource & Narrative
Year | 2022 | Area | SouthGrid
Quarter | Q2 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | Successfully setup a working HTCondor CE on a small subset of the cluster and got ATLAS to start using it. This will eventually replace VAC for ATLAS as keeping that maintaned on the Panda side was becoming problematic. |  |  | Found an issue which had meant that the new workers put in last Autumn hadn't been reporting usage properly. Had to gradually add back in these last 9 months of APEL records so as not to overwhelm the system. Had yet another aircon failure towards the end of the quarter and will be waiting on a repair for sometime. Will consider replacing the aging units to reduce these failures.
Bristol | replace lcgse01 with xrootd-only (io02). Transfers work on both xrootd and webdav, lcgse01 removed from "production" and replaced by xrootd.phy. Network performance, as monitored by perfsonar, was fixed. Issue turned out to be "dirty" optical transeivers. lcgce02 upgraded to HTCondor 9.0.12 LTS. All host certificates have been renewed June 22nd, defragmenting renewal schedule. |  |  | FTS time outs during checksum query --> breaks CMS transfers. Was not remedied by fixed network performance. Newer versions of HTCondor (>= 9.3.0) remove X.509 support. About to lose valuable SysAdmin at the end of February 2023.
Oxford | New Rocky 8 Nagios monitoring server built and running. Build a Rocky 8 Ansible server built and running. Begbroke Data Centre room RACU replacement started on 13th June. Work to be acrried out sequentially without interuption to the computer room. However there was a power outage and downtime on 29th June.
RAL PPD
Sussex
Risks
Type | Risk |  |  | Mitigation
Birmingham
Oxford | Project underway to replace all 6 datacentre Air Handling Units with more efficient and higher capacity units. Data centre shutdown to allow servicing of electric substation. BMCs reconfigured and cabled on Lenovo worker nodes to allow IPMI management. Obtain quotes for new hardware: 2 x Racks 3 x Switches (48 x SFP28) 5 x PDUs 4 x UPSs 13 x Worker nodes
30/05/2022 | BRISTOL: replace old lcgse01 (DMLite +HDFS) with xrootd (xrootd + HDFS) |  |  | transfers work for CMS and LZ, SE passing all tests
30/06/2022 | BRISTOL: Upgrade to HTCondor 9 [ongoing] |  |  | New and improved HTCondor version with new security
30/06/2022 | BRISTOL: After HTCondor upgrade, add GPUs to HTCondor cluster |  |  | GPUs will become available for local and grid (low availability) use
30/05/2022 | BRISTOL: New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
| RALPP: Upgrade dCache to latest Golden Release Fix routing |  |  | dCache running latest golden release (7.2) major changes to RAL internal network configuration, Tier 2 on interim 2x10GB connection to RAL core and 2x40GB connection to Border routers for LHCOne but not all traffic is using the bypass
Oxford
RAL PPD
Sussex
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
30/09/2022 | BRISTOL: replace old lcgse01 (DMLite +HDFS) with xrootd (xrootd + HDFS) |  |  | FTS checksum queries work
30/09/2022 | BRISTOL: Upgrade to HTCondor 9 [ongoing] |  |  | New and improved HTCondor version with new security
30/09/2022 | BRISTOL: After HTCondor upgrade, add GPUs to HTCondor cluster |  |  | GPUs will become available for local and grid (low availability) use
30/09/2022 | BRISTOL: New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
30/09/2023 | BRISTOL: Integrate Bristol T2 with UoB official Puppet |  |  | Decomissioning of custom puppet server and deployment server (stacki).
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 248.7% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 193% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 84.55% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 80.23% | MFL | Average Argo Availability - SouthGrid |  |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 81.26% | MFL | Average Argo Reliability - SouthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 26540 | 26780 | 45682 | 55500 | 3580 | 158082 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 9277 | 4250 | 18663 | 30450 | 927 | 63567
% of Pledge | 286.1% | 630.1% | 244.8% | 182.3% | 386.2% | 248.7%
Storage Available (TB) | 2036 | 2048 |  | 3010 |  | 7094 | Oxford is a storage less site from 1st July 2021
Storage Pledged (TB) | 1222 | 0 | 0 | 2454 | 0 | 3676
% of Pledge | 166.6% | #DIV/0! | #DIV/0! | 122.7% | #DIV/0! | 193%
Availability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 0 | 100 | 98.44 | 41.02 | 59.87% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 47.22 | 99.15 | 90.8 | 100 | 84.29% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 99.5 | 94.86 | 91.78 | 100 | 96.53% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 48.9067 | 98.0033 | 93.6733 | 80.34 | 80.23%
Reliability | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 0 | 100 | 98.44 | 41.02 | 59.87% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 47.22 | 99.15 | 90.8 | 100 | 84.29% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 99.55 | 100 | 98.94 | 100 | 99.62%
% Tier-2 Total | #DIV/0! | 48.9233 | 99.7167 | 96.06 | 80.34 | 81.26%
CPU Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | 2160 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 57326400 | 57844800 | 98673120 | 119880000 | 7732800 | 213844320 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 7949992 | 9972599 | 26072394 | 32676617 | 2533147 | 79204749 | Q1: 2160/2184 (if leap year)
Month 2 | 3360659 | 10024925 | 25557271 | 31507288 | 1467268 | 71917411 | Q2: 2184
Month 3 | 6914633 | 11398955 | 24459087 | 24652343 | 1766243 | 69191261 | Q3: 2208
Total: | 18225284 | 31396479 | 76088752 | 88836248 | 5766658 | 220313421 | Q4: 2208
% Utilisation | 31.79% | 54.28% | 77.11% | 74.1% | 74.57% | 103%
WallClock Hours (HS06) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | 2160 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 57326400 | 57844800 | 98673120 | 119880000 | 7732800 | 341457120 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 11576101 | 13460703 | 28171026 | 40375804 | 4889811 | 98473445 | Q1: 2160/2184 (if leap year)
Month 2 | 6297476 | 19449469 | 28970344 | 38984376 | 4637386 | 98339051 | Q2: 2184
Month 3 | 9939156 | 19376793 | 27506439 | 32177973 | 2891584 | 91891945 | Q3: 2208
Total: | 27812733 | 52286965 | 84647809 | 111538153 | 12418781 | 288704441 | Q4: 2208
% Utilisation | 48.52% | 90.39% | 85.79% | 93.04% | 160.6% | 84.55%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 850 | 0 | 930 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 1800 | 0 | 2184 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 710 | 0 | 790 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 1130 | 0 | 1455 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Oxford | RAL PPD | Sussex | Total | Notes
[6 empty] | 0 | Active VOs at you site can be assesed from the following link:
[6 empty] | 0 | https://accounting.egi.eu/tier2/federation/UK-SouthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
[6 empty] | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
[6 empty] | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes