## Map
GridPP 6 - Project Map
WP1a: Tier-1 Operations |  |  |  |  | WP1b: Tier-2 Operations |  |  |  |  | WP1c: UK Operations |  |  |  |  | WP2: Experiment Support |  |  |  |  | WP3: Federal Responsabilities |  |  |  |  | WP5: Management
Metrics |  |  |  |  | Metrics |  |  |  |  | Metrics |  |  |  |  | Metrics |  |  |  |  | Metrics |  |  |  |  | Metrics
Pledge & Allocation |  |  |  |  | Pledge & Allocation |  |  |  |  | Pledge & Allocation |  |  |  |  | ATLAS |  |  |  |  | WLCG |  |  |  |  | Management
1a.1 | 1a.2 | 1a.3 | 1a.9 | 1a.10 | 1b.1 | 1b.2 | 1b.3 | 1b.4 | 1b.5 | 1c.1 | 1c.2 | 1c.3 | 1c.4 | 1c.5 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 5.3 | 5.4 | 5.7 | 5.8 | 5.9
1a.11 | 1a.12 | 1a.13 | 1a.14 | 1a.15 | 1b.6 | 1b.7 | 1b.8 |  |  | 1c.6 | 1c.7 | 1c.8 | 1c.9 | 1c.10 | 2.6 | 2.7 | 2.8 | 2.9 |  | 3.6 | 3.7 | 3.8 | 3.9 | 3.10
1a.16 | 1a.17 | 1a.18 | 1a.19 | 1a.20 | [15 empty] | 3.11 | 3.13 |  |  |  | Reporting
1a.21 | 1a.22 | 1a.23 | [12 empty] | CMS | [9 empty] | 5.1 | 5.2 | 5.5 | 5.6
[15 empty] | 2.10 | 2.11 | 2.12 | 2.13 | 2.14 | Security
[15 empty] | 2.15 | 2.16 | 2.17 | 2.18 | 2.19 | 3.11 | 3.12
Availability & Reliability |  |  |  |  | Availability & Reliability |  |  |  |  | Availability & Reliability |  |  |  |  | 2.20 | 2.21 | 2.22 | 2.23 | 2.24
1a.5 | 1a.6 | 1a.7 | 1a.8 |  | 1b.13 | 1b.14 | 1b.15 | 1b.16 | 1b.17 | 1c.12 | 1c.13 | [8 empty] | Milestones
[5 empty] | 1b.18 | 1b.19 | 1b.20 | [7 empty] | LHCb |  |  |  |  | Security
[15 empty] | 2.25 | 2.26 | 2.27 | 2.28 | 2.29 | 3.1 | 3.2 | 3.3 | 3.4 | 3.5
[15 empty] | 2.30 | 2.31 | 2.32 |  |  | 3.6
Service Provision |  |  |  |  | Service Provision |  |  |  |  | Service Provision
1a.24 | 1a.25 | 1a.26 | 1a.27 | 1a.28 | 1b.9 | 1b.10 | 1b.11 | 1b.12 |  | 1c.11 | 1c.14 |  |  |  | ALICE
1a.29 | 1a.30 | 1a.31 | 1a.32 | [11 empty] | 2.33 | 2.34 | 2.35 | 2.36 | 2.37 | WP4: Essential Development
Resource & Security | [9 empty] | Resource & Security |  |  |  |  | Other
1a.4 | 1a.33 | [8 empty] | 1c.15 |  |  |  |  | 2.38 | 2.39 | 2.40 | 2.41 | 2.42 | Metrics
[15 empty] | 2.43 |  |  |  |  | Review Projects
[20 empty] | 4.1 | 4.2 | 4.3 | 4.4 | 4.5
4.6
Milestones |  |  |  |  | Milestones |  |  |  |  | Milestones |  |  |  |  | Milestones |  |  |  |  | Milestones |  |  |  |  | Milestones
Tier-1 Review |  |  |  |  | Pledge & Allocation |  |  |  |  | Security |  |  |  |  | ATLAS |  |  |  |  | Tape Service |  |  |  |  | Planning
1a.1 | 1a.2 |  |  |  | 1a.7 | 1a.8 | 1a.9 | 1a.10 |  | 1c.1 | 1c.2 | 1c.3 | 1c.4 | 1c.5 | 2.1 | 2.2 | 2.3 | 2.4 |  | 4.1 | 4.2 | 4.3 | 4.4 |  | 5.1 | 5.2 | 5.3 | 5.4 | 5.5
[10 empty] | 1c.6 | 1c.7 | [13 empty] | 5.6 | 5.7 | 5.8 | 5.9 | 5.10
Hardware Procurement |  |  |  |  | Hardware Procurement | [9 empty] | CMS |  |  |  |  | Networking
1a.3 | 1a.4 | 1a.5 | 1a.6 | 1a.7 | 1b.1 | 1a.2 | 1a.3 | 1a.4 | 1a.5 | [5 empty] | 2.5 | 2.6 | 2.7 | 2.8 | 2.17 | 4.5 | 4.6 | 4.7 | 4.8 | 4.9 | Pledge & Allocation
1a.8 | 1a.9 | 1a.10 | 1a.11 | 1a.12 | 1b.6 | [9 empty] | 2.18 | 2.19 | 2.20 | 2.21 | 2.22 | [5 empty] | 5.12 | 5.14 | 5.16 | 5.18
1a.13 | 1a.14 | 1a.15 | 1a.16 | 1a.17 | [10 empty] | 2.23 | 2.24 |  |  |  | Database & Data Lakes
1a.18 | [19 empty] | 4.10 | 4.11 | 4.12 | 4.13 | 4.14 | Review
[15 empty] | LHCb |  |  |  |  | 4.15 |  |  |  |  | 5.11 | 5.13 | 5.15 | 5.17 | 5.19
Key - Metrics |  |  |  |  | Key - Milestones | [9 empty] | 2.9 | 2.10 | 2.11 | 2.12
| Metric OK |  |  |  |  | Milestone Achieved
| Metric Close to Target |  |  |  |  | Milestone Ongoing | [8 empty] | Other
| Metric not OK |  |  |  |  | Milestone Overdue | [8 empty] | 2.13 | 2.14 | 2.15 | 2.16
| Metric with no Target |  |  |  |  | Milestone not Due

## Overview
Year | 2022 | Key - Metrics |  |  |  | Metric | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Quarter | Q2 | Colour | Description | Code | # | WP1a | MOK | MOK | MOK | MOK | MOK | MOK | MFL | MOK | MCT | MOK | MOK | MOK | MOK | MOK | MOK | MFL | MFL | MOK | MFL | MFL | MCT | MOK | MOK | MCT | MCT | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK
|  |  | Metric OK | MOK | 107 | WP1b | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MFL | MFL
|  |  | Metric Clost to Target | MCT | 14 | WP1c | MOK | MOK | MOK | MOK | MOK | MFL | MOK | MOK | MFL | MOK | MOK | MOK | MOK | MNO | MOK
|  |  | Metric not OK | MFL | 14 | WP2 | MCT | MCT | MOK | MCT | MOK | MOK | MOK | MCT | MCT | MOK | MOK | MOK | MCT | MFL | MNO | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MNO | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MFL | MFL | MFL | MOK | MCT | MCT
|  |  | Metric with no Target | MNO | 4 | WP3 | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MOK | MCT | MOK | MOK | MOK | MNO
[5 empty] | 139 | WP4 | MOK | MOK | MOK | MOK | MOK | mok
[6 empty] | WP5 | MOK | MFL | MOK | MOK | MCT | MOK | MOK | mok | moK
|  | Key - Milestones |  |  |  | Milestone | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  | Colour | Description | Code | # | WP1a | MSU | MSU | MSA | MSA | MSA | MSA | MSA | MSA | MSU | MSA | MSA | MSU | MSU | MSU | MSU | MSU | MSU | MSU
|  |  | Milestone Achieved | MSA | 45 | WP1b | MOK 1: MSA; MFL 2: MSA; MOK 3: MSA; MOK 4: MSA; MCT 5: MSU; MOK 6: MSU; MOK 7: MSA; mok 8: MSA; moK 9: MSU; moK 10: MSU
|  |  | Milestone Ongoing | MOG | 9 | WP1c | MOK 1: MSA; MFL 2: MSA; MOK 3: MSU; MOK 4: MSU; MCT 5: MSA; MOK 6: MSU; MOK 7: MSU
|  |  | Milestone Overdue | MOD | 1 | WP2 | MSA | MSA | MSU | MSU | MSA | MSA | MSU | MSU | MSA | MSA | MSU | MSU | MSA | MSA | MSU | MSU | MSA | MSU | MSU | MSU | MSU | MSU | MSU | MSU
|  |  | Milestone not due | MSU | 44 | WP3 | MOK 1: MSA; MFL 2: MSA; MOK 3: MSU; MOK 4: MSU; MCT 5: MSU; MOK 6: MSU
[6 empty] | WP4 | MSA | MSA | MOG | MOG | MOG | MOG | MSA | MOD | MOG | MSA | MOG | MOG | MOG | MOG | MSA
[6 empty] | WP5 | MSA | MSA | MSA | MSA | MSA | MSA | MSA | MSA | MSU | MSU | MSU | MSA | MSA | MSA | MSA | MSU | MSU | MSU | MSU
Key - Other
|  | Colour | Description | Code | #
|  |  | Suspended | SUS | 0
|  |  | Awaiting Input | AWI | 0
|  |  | No Metric/Milestone | - | 0

## WP1a
Workpackage |  |  | 1a | Title | Tier-1 Operations
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 100% | 5% | 111% | MOK | % of GridPP commitment for CPU | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
2 | 100% | 5% | 112% | MOK | % of GridPP commitment for Disk | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
3 | 100% | 5% | 107% | MOK | % of GridPP allocation for Tape | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
4 | 94% | 5% | 101.9% | MOK | % of GridPP6 Staff funded | Tier-1 Quarterly Report, Project Allocations | Direct | Quarterly | Resource | AD
5 | 98% | 3% | 98.33% | MOK | WLCG Service Availability for Alice | Argo Monitoring | Direct | Monthly | Availability & Reliability | AD
6 | 98% | 3% | 99.33% | MOK | WLCG Service Availability for ATLAS | Argo Monitoring | Direct | Monthly | Availability & Reliability | AD
7 | 98% | 3% | 91.33% | MFL | WLCG Service Availability for CMS | Argo Monitoring | Direct | Monthly | Availability & Reliability | AD | Availability is improving compared to last quarter, since new CMS test was added.
8 | 98% | 3% | 99.33% | MOK | WLCG Service Availability for LHCB | Argo Monitoring | Direct | Monthly | Availability & Reliability | AD
9 | 90% | 10% | 83.89% | MCT | % usage by ATLAS of their CPU pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
10 | 80% | 10% | 102.6% | MOK | % usage by ATLAS of their Disk pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | There was a spike in usage when the pledges were being updated. ATLAS have subsequently run a dark data cleanup.
11 | 80% | 10% | 93.96% | MOK | % usage by ATLAS of their Tape pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
12 | 90% | 10% | 180.6% | MOK | % usage by CMS of their CPU pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
13 | 80% | 10% | 88.4% | MOK | % usage by CMS of their Disk pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
14 | 80% | 10% | 83.32% | MOK | % usage by CMS of their Tape pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
15 | 90% | 10% | 128.3% | MOK | % usage by LHCb of their CPU pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
16 | 80% | 10% | 57.17% | MFL | % usage by LHCb of their Disk pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | Pledge increased by 3.6PB which LHCb were unable to immediately use.
17 | 80% | 10% | 41.77% | MFL | % usage by LHCb of their Tape pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | Pledge increased by almost 15PB which LHCb will only make use of as data is taken.
18 | 90% | 20% | 105.1% | MOK | % usage by ALICE of their CPU pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
19 | 80% | 20% | 39.57% | MFL | % usage by ALICE of their Disk pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | ALICE have not started significantly increasing their disk usage yet.
20 | 80% | 20% | 46.79% | MFL | % usage by ALICE of their Tape pledge | Pledge, CRIC, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | ALICE have not been writing to tape during the long shutdown.
21 | 40% | 30% | 13.92% | MCT | % usage by non-LHC VOs of their CPU allocation | Pledge, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
22 | 80% | 20% | 110.5% | MOK | % usage by non-LHC VOs of their Disk allocation | Pledge, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD | Currently only Dune using Echo. Dune appear to have a dark data problem which we are investigating.
23 | 80% | 20% | 137.2% | MOK | % usage by non-LHC VOs of their Tape allocation | Pledge, Tier1 Quarterly Report | Derived | Quarterly | Pledge & Allocation | AD
24 | 90% | 10% | 85.83% | MCT | GridPP Funded Farm Occupancy | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD | Long outage of the farm during network segmentation work in June reduced overall occupancy.
25 | 80% | 10% | 78.78% | MCT | % Total DIsk Usage | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD | Pledge increase means not all capacity was used immediately.
26 | 80% | 10% | 90.83% | MOK | % Total Tape Usage | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
27 | 70% | 20% | 89.48% | MOK | % Job Efficiency (CPU/Wall) - ATLAS | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
28 | 70% | 20% | 85.95% | MOK | % Job Efficiency (CPU/Wall) - CMS | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD | Significantly better than previous quarter. Full impact of network improvements have not yet been realised.
29 | 70% | 20% | 107.7% | MOK | % Job Efficiency (CPU/Wall) - LHCb | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
30 | 70% | 20% | 95.45% | MOK | % Job Efficiency (CPU/Wall) - ALICE | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
31 | 70% | 10% | 74.21% | MOK | % Job Efficiency (CPU/Wall) - non-LHC | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
32 | 100% | 5% | 100% | MOK | % of GGUS Tickets Handled | Tier-1 Quarterly Report | Direct | Monthly | Service Provision | AD
33 | 30 | 10 | 0 | MOK | Average number of security vunerabilities | Tier-1 Quarterly Report | Direct | Monthly | Security | AD
Milestones
ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2020-11-01 |  |  | MSU | GridPP review of operation (biennial) |  |  |  | Tier-1 Review | AD | Cancelled due to pandemic
2 | 2022-10-01 | N |  | MSU | GridPP review of operation (biennial) |  |  |  | Tier-1 Review | AD
3 | 2020-06-01 | Yes | 2020-05-01 | MSA | Produce the purchasing plan |  |  |  | Hardware Procurement | AD
4 | 2020-11-01 | Yes | 2020-07-01 | MSA | FY20 Capacity order placed |  |  |  | Hardware Procurement | AD
5 | 2021-04-01 | Yes | 2021-06-01 | MSA | FY20 Purchase in production | Done (but was overdue) |  |  | Hardware Procurement | AD | Expected to enter production in July 21, due to COVID and other delays
6 | 2021-05-01 | Yes | 2021-05-01 | MSA | Tier-1 WLCG MoU commitments met |  |  |  | Hardware Procurement | AD
7 | 2021-06-01 | Yes | 2021-06-01 | MSA | Produce the purchasing plan |  |  |  | Hardware Procurement | AD
8 | 2021-11-01 | Yes | 2021-08-01 | MSA | FY21 Capacity order placed |  |  |  | Hardware Procurement | AD
9 | 2022-04-01 | Yes |  | MSU | FY21 Purchase in production |  |  |  | Hardware Procurement | AD
10 | 2022-05-01 | Yes | 2022-04-01 | MSA | Tier-1 WLCG MoU commitments met |  |  |  | Hardware Procurement | AD
11 | 2022-06-01 | Yes | 2022-04-01 | MSA | Produce the purchasing plan |  |  |  | Hardware Procurement | AD
12 | 2022-11-01 |  |  | MSU | FY22 Capacity order placed |  |  |  | Hardware Procurement | AD
13 | 2023-04-01 |  |  | MSU | FY22 Purchase in production |  |  |  | Hardware Procurement | AD
14 | 2023-05-01 |  |  | MSU | Tier-1 WLCG MoU commitments met |  |  |  | Hardware Procurement | AD
15 | 2023-06-01 |  |  | MSU | Produce the purchasing plan |  |  |  | Hardware Procurement | AD
16 | 2023-11-01 |  |  | MSU | FY23 Capacity order placed |  |  |  | Hardware Procurement | AD
17 | 2024-04-01 |  |  | MSU | FY23 Purchase in production |  |  |  | Hardware Procurement | AD
18 | 2024-05-01 |  |  | MSU | Tier-1 WLCG MoU commitments met |  |  |  | Hardware Procurement | AD

## WP1b
Workpackage |  |  | 1b | Title | Tier-2 Operations
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 100% | 5% | 359% | MOK | % of WLCG Pledged CPU Available - LondonGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | DR
2 | 100% | 5% | 212% | MOK | % of WLCG Pledged CPU Available - NorthGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
3 | 100% | 5% | 194% | MOK | % of WLCG Pledged CPU Available - ScotGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | GS
4 | 100% | 5% | 249% | MOK | % of WLCG Pledged CPU Available - SouthGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | PG
5 | 100% | 5% | 394% | MOK | % of WLCG Pledged Disk Available - LondonGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | DR
6 | 100% | 5% | 223% | MOK | % of WLCG Pledged Disk Available - NorthGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
7 | 100% | 5% | 124% | MOK | % of WLCG Pledged Disk Available - ScotGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | GS
8 | 100% | 5% | 193% | MOK | % of WLCG Pledged Disk Available - SouthGrid | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | PG
9 | 50% | 5% | 82% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid | Quarterly Report, accounting.egi.eu | Derived | Quarterly | Service Provision | DR
10 | 50% | 5% | 98% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid | Quarterly Report, accounting.egi.eu | Derived | Quarterly | Service Provision | MD
11 | 50% | 5% | 166% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid | Quarterly Report, accounting.egi.eu | Derived | Quarterly | Service Provision | GS
12 | 50% | 5% | 85% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid | Quarterly Report, accounting.egi.eu | Derived | Quarterly | Service Provision | PG
13 | 95% | 5% | 98% | MOK | Average Argo Availability - LondonGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | DR
14 | 95% | 5% | 99% | MOK | Average Argo Reliability - LondonGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | DR
15 | 95% | 5% | 100% | MOK | Average Argo Availability - NorthGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | MD
16 | 95% | 5% | 100% | MOK | Average Argo Reliability - NorthGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | MD
17 | 95% | 5% | 97% | MOK | Average Argo Availability - ScotGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | GS
18 | 95% | 5% | 97% | MOK | Average Argo Reliability - ScotGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | GS
19 | 95% | 5% | 80% | MFL | Average Argo Availability - SouthGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | PG | Bristol
20 | 95% | 5% | 81% | MFL | Average Argo Reliability - SouthGrid | Argo Monitoring | Direct | Monthy | Availability & Reliability | PG | Bristol
Milestones
ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2020-06-01 | Yes | 2020-04-01 | MSA | Allocate Tier-2 funds based on performance/utilisation |  |  |  | Hardware Procurement | GR
2 | 2021-10-01 | Yes | 2021-10-01 | MSA | FY21/22 Pocurements commence |  |  |  | Hardware Procurement | GR | Most Procurements moved to FY21
3 | 2022-04-01 | Yes | 2022-04-01 | MSA | FY21/22 Procurements completed |  |  |  | Hardware Procurement | SS
4 | 2022-06-01 | Yes | 2021-12-01 | MSA | Allocate Tier-2 funds based on performance/utilisation |  |  |  | Hardware Procurement | SS
5 | 2022-10-01 |  |  | MSU | FY22/23 Pocurements commence |  |  |  | Hardware Procurement | SS
6 | 2023-04-01 |  |  | MSU | FY22/23 Procurements completed |  |  |  | Hardware Procurement | SS
7 | 2020-08-01 | Yes | 2020-08-01 | MSA | Review and set WLCG Pledges | CRIC, VO Predictions |  | Yearly | Pledge & Allocation | SS
8 | 2021-08-01 | Yes | 2021-08-01 | MSA | Review and set WLCG Pledges | CRIC, VO Predictions |  | Yearly | Pledge & Allocation | SS
9 | 2022-08-01 |  |  | MSU | Review and set WLCG Pledges | CRIC, VO Predictions |  | Yearly | Pledge & Allocation | SS
10 | 2023-08-01 |  |  | MSU | Review and set WLCG Pledges | CRIC, VO Predictions |  | Yearly | Pledge & Allocation | SS

## WP1c
| Workpackage |  |  | 1c | Title | UK Operations
Metrics
| ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
| 1 | 100% | 5% | 131% | MOK | % of GridPP CPU Pledge used by ALICE | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 2 | 100% | 5% | 173% | MOK | % of GridPP CPU Pledge used by ATLAS | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 3 | 100% | 5% | 308% | MOK | % of GridPP CPU Pledge used by CMS | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 4 | 100% | 5% | 202% | MOK | % of GridPP CPU Pledge used by LHCb | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 5 | 100% | 5% | 101% | MOK | % of GridPP CPU Pledge used by Other | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 6 | 80% | 10% | 46% | MFL | % of GridPP Disk Pledge used by ALICE | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD | Significant increase in disk pledge required by ALICE as step function, ALICE has not filled it yet
| 7 | 80% | 10% | 116% | MOK | % of GridPP Disk Pledge used by ATLAS | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 8 | 80% | 10% | 143% | MOK | % of GridPP Disk Pledge used by CMS | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 9 | 80% | 10% | 61% | MFL | % of GridPP Disk Pledge used by LHcb | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD
| 10 | 80% | 10% | 147% | MOK | % of GridPP Disk Pledge available to Other | Pledge, CRIC, Tier2 Quarterly Report | Derived | Quarterly | Pledge & Allocation | MD | I would expect this to be higher, given the CPU calculation
? | 11 | 70% | 5% | 96% | MOK | % Utilisation of available GridPP CPU Resources | Quarterly Report, accounting.egi.eu | Derived | Quarterly | Service Provision | MD
| 12 | 100% | 5% | 100% | MOK | % of GridPP Sites in certified Status | CRIC, Tier2 Quarterly Report | Direct | Monthy | Availability & Reliability | MD
| 13 | 95% | 5% | 100% | MOK | Availabilty of GridPP Dirac Job submission Framework | Federal Services | Direct | Monthy | Availability & Reliability | AD
| 14 |  |  |  | MNO | No. of unique supported on Dirac | Federal Services | Direct | Monthy | Service Provision | AD | Determined by counting unique user groups in DIRAC config
| 15 | 100% | 5% | 100% | MOK | % of Sites responding to security communication requests | Security Quarterly Report | Direct | Quarterly | Security | DC | n/a in this period
Milestones
| ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
| 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge |  |  |  | Security | DC | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved
| 2 | 2022-04-01 | Y | 2021-11-01 | MSA | GridPP-wide security communication challenge |  |  |  | Security | DC
| 3 | 2023-04-01 |  |  | MSU | GridPP-wide security communication challenge |  |  |  | Security | DC
| 4 | 2024-04-01 |  |  | MSU | GridPP-wide security communication challenge |  |  |  | Security | DC
| 5 | 2022-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security training event |  |  |  | Security | DC
| 6 | 2024-04-01 |  |  | MSU | GridPP-wide security training event |  |  |  | Security | DC
| 7 | 2022-04-01 |  |  | MSU | Review of the role of the security team |  |  |  | Security | DK

## WP2
Workpackage |  |  | 2 | Title | Experiment Support & Liasion
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 95% | 5% | 91% | MCT | T1 Job success rates from ATLAS dashboard (site-only metrics) | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier1 | RJ | Inefficient high-IO Sherpa jobs introduced a number of job failures at the site, until problem was identified and a fix (on the ATLAS side) rolled out.
2 | 98% | 5% | 97.3% | MCT | T1 Data availability from the ATLAS dashboard | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier1 | RJ
3 | 98% | 5% | 98.5% | MOK | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier1 | RJ
4 | 95% | 5% | 93.8% | MCT | T1 Production job success rates (site only metrics) - from PANDA dashboard | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
5 | 95% | 5% | 97.1% | MOK | Data availability from the ATLAS dashboard; if we can automate this reliably | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
6 | 95% | 5% | 97% | MOK | Data acceptance at Tier-2s | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
7 | 5% | 1% | 0.01% | MOK | Data loss at Tier-2s | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
8 | 95% | 5% | 90.2% | MCT | Atlas job success in production | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
9 | 95% | 5% | 90.1% | MCT | ATLAS job success rates in user analysis | ATLAS Dashboard | Direct | Quarterly | ATLAS - Tier2 | RJ
10 |  |  |  | MOK | Tier-1 Data Transfer Quality | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | Transfers via the new protocol, Webdav, suffered when load was high (e.g. from all VOs combined), but it was particularly noticeable that SAM tests failed. There was an improvement in the config and also increased hardware, and the end of the quarter appeared better.
11 | 5% | 5% | 8% | MOK | Timely and efficient availability and use of resources at RAL T1 (Global %) | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | RAL ran 7.9% of completed CMS Tier 1 jobs, which is down on last quarter but still above pledge which is 6.8%.
12 | 70% | 5% | 74% | MOK | Tier-1 Average CPU Efficiency | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | Now achieving the average Tier 1 job efficiency - great improvement in the last year.
13 | 10% | 5% | 14% | MCT | Tier-1 Failure Rate | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | Same as last quarter. However, real value closer to 11% due to LogCollect jobs continuing to fail, and not being fixed by CMS.
14 | 97% | 5% | 90% | MFL | Site availability at the Tier-1 | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | 89,91,90% from WLCG SiteMon Apr/May/Jun. As last quarter, this was strongly affected by the SAM test failures for the webdav endpoint. In addition there were issues with SAM tests on the CEs. None of these affected running prod jobs, so Katy articifially kept RAL enabled for jobs.
15 | 5% |  |  | MNO | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | There is currently no way to access this information.
16 | 0% | 1% | 0% | MOK | Custodial Data Loss at Tier-1 | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | None of note
17 |  |  |  | MOK | Transfer rates to the UK Tier 2s | CMS Dashboard | Direct | Quarterly | CMS - Tier1 | DC | Pretty serious transfer problems at Bristol (although this is generally considered a T3…and should really be labelled as one) with 1% transfer efficiency (success rate) through most of the quarter. At time of writing there is a ggus ticket and it is being updated regularly. Other sites look fine.
18 | 80% | 5% | 96% | MOK | Site availability at the Tier-2s | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | IC - 98 (98/99/97)%, RALPP - 94 (98/90/94)%, Brunel - 95 (99/88/97)%
19 | 80% | 5% | 96% | MOK | Site readiness at the Tier-2s | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | IC - 98 (98/99/97)%, RALPP - 95 (98/90/96)%, Brunel - 95 (99/88/97)%
20 | 0% | 5% | 0% | MOK | Unique data loss at Tier-2s | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | None reported
21 | 30% | 5% | 29% | MOK | Failed analysis jobs | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | A bit higher than last quarter, but still within the expected margin
22 | 20% | 5% | 7% | MOK | Failed production jobs | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | Good
23 | 5% | 5% | 5% | MOK | T2 sites provide an appropriate level of resource to CMS | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | UK T2 sites provided CPU to complete 4.7% of CMS T2 jobs.
24 | 80% |  |  | MNO | Job performance/efficiency using AAA data transfer | CMS Dashboard | Direct | Quarterly | CMS - Tier2 | DC | There is currently no way to access this information.
25 | 90% | 5% | ? | MOK | Tier-1 prod CPU efficiency | LHCb Dirac | Direct | Quarterly | LHCB - Tier1 | AM | In line with previous numbers Note that this is jobs not including simulation
26 | 50% | 5% | ? | MOK | Tier-1 user success rate | LHCb Dirac | Direct | Quarterly | LHCB - Tier1 | AM
27 | 70% | 5% | ? | MOK | Tier-1 user CPU efficiency | LHCb Dirac | Direct | Quarterly | LHCB - Tier1 | AM
28 | 15% | 5% | ? | MOK | UK Tier-1 work fraction | LHCb Dirac | Direct | Quarterly | LHCB - Tier1 | AM
29 | 50% | 5% | ? | MOK | Tier-2A : User success rate | LHCb Dirac | Direct | Quarterly | LHCB - Tier2 | AM
30 | 70% | 5% | ? | MOK | Tier-2A : User CPU efficiency | LHCb Dirac | Direct | Quarterly | LHCB - Tier2 | AM
31 | 90% | 5% | ? | MOK | All Tier-2: Simulation success rate | LHCb Dirac | Direct | Quarterly | LHCB - Tier2 | AM
32 | 90% | 5% | ? | MOK | All Tier-2: Simulation CPU efficiency | LHCb Dirac | Direct | Quarterly | LHCB - Tier2 | AM
33 | 90% | 40% | 113% | MOK | UK Tier-1 work fraction | Tier-1 Monitoring | Direct | Quarterly | ALICE - Tier1 | KE | Much better utilisation this quarter, 3.38% of ALICE work done by T1s
34 | 70% | 20% | 95% | MOK | UK T1 CPU efficiency for Alice. | Tier-1 Monitoring | Direct | Quarterly | ALICE - Tier1 | KE | Very good. Not every site does this well
35 | 90% | 20% | 104% | MOK | Fraction of CPU fair share used by Alice at UK T1 | Tier-1 Monitoring | Direct | Quarterly | ALICE - Tier1 | KE | Using pledge of 14940 HS06 (multiplied by 24 and number of days in the quarter).
36 | 95% | 40% | 151% | MOK | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s (2.1% for GridPP6). | Tier-1 Monitoring | Direct | Quarterly | ALICE - Tier2 | KE | 3.17% of T2 walltime was run in the UK, well above pledge
37 | 70% | 10% | 85% | MOK | UK T2 CPU efficiency for Alice. | Tier-1 Monitoring | Direct | Quarterly | ALICE - Tier3 | KE
38 | 70% | 20% | 46% | MFL | T1 CPU Efficiency for DUNE | Quarterly Reporting | Direct | Quarterly | OTHER - IRIS | KE | Slight improvement on last quarter. Some other sites just as bad, I think this is expected.
39 | 70% | 20% | 36% | MFL | T2 CPU Efficiency for DUNE | Quarterly Reporting | Direct | Quarterly | OTHER - IRIS | KE | Some improvement on last quarter. Many sites have low values.
40 | 75% | 25% | 48% | MFL | CPU usage by DUNE in the UK relative to pledge | Pledges, Quarterly Reporting | Direct | Quarterly | OTHER - IRIS | KE | 963 cores in total, from T1 (average 128 cores) and T2 (average 835 cores). Down on last quarter.
41 | 70% | 20% | 79% | MOK | T1 CPU Efficiency for Other (non-DUNE, non-LHC) | Pledges, Quarterly Reporting | Direct | Quarterly | OTHER - IRIS | KE
42 | 70% | 20% | 58% | MCT | T2 CPU Efficiency for Other (non-DUNE, non-LHC) | Quarterly Reporting | Direct | Quarterly | OTHER - other | KE
43 | 70% | 25% | 69% | MCT | T1/T2 % pledged CPU used by Other VOs | Quarterly Reporting | Direct | Quarterly | OTHER - other | KE | T1 usage 11,012,753 HS06 hours = 5042 HS06; T2 usage 170,692,610 HS06 hours = 78,156 HS06. Total sum is 83,198.
|  |  |  | AWI | TBC |  |  |  |  | KE
|  |  |  | AWI | TBC |  |  |  |  | KE
Milestones
ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2020-12-01 | Y | 2020-11-01 | MSA | Report on delivery to ATLAS during year |  |  |  | T1 ATLAS | RJ
2 | 2021-12-01 | Y | 2021-11-01 | MSA | Report on delivery to ATLAS during year |  |  |  | T1 ATLAS | RJ
3 | 2022-12-01 |  |  | MSU | Report on delivery to ATLAS during year |  |  |  | T1 ATLAS | RJ
4 | 2023-12-01 |  |  | MSU | Report on delivery to ATLAS during year |  |  |  | T1 ATLAS | RJ
5 | 2020-12-01 | Y | 2020-11-01 | MSA | Report on delivery to CMS during year |  |  |  | T1 CMS | DC
6 | 2021-12-01 | Y | 2020-11-01 | MSA | Report on delivery to CMS during year |  |  |  | T1 CMS | DC
7 | 2022-12-01 |  |  | MSU | Report on delivery to CMS during year |  |  |  | T1 CMS | DC
8 | 2023-12-01 |  |  | MSU | Report on delivery to CMS during year |  |  |  | T1 CMS | DC
9 | 2020-12-01 | Y | 2020-11-01 | MSA | Report on delivery to LHCb during year |  |  |  | T1 LHCb | AM
10 | 2021-12-01 | Y | 2020-11-01 | MSA | Report on delivery to LHCb during year |  |  |  | T1 LHCb | AM
11 | 2022-12-01 |  |  | MSU | Report on delivery to LHCb during year |  |  |  | T1 LHCb | AM
12 | 2023-12-01 |  |  | MSU | Report on delivery to LHCb during year |  |  |  | T1 LHCb | AM
13 | 2020-12-01 | Y | 2020-11-01 | MSA | Report on delivery to Other during year |  |  |  | T1 Other | DR
14 | 2021-12-01 | Y | 2020-11-01 | MSA | Report on delivery to Other during year |  |  |  | T1 Other | DR
15 | 2022-12-01 |  |  | MSU | Report on delivery to Other during year |  |  |  | T1 Other | DR
16 | 2023-12-01 |  |  | MSU | Report on delivery to Other during year |  |  |  | T1 Other | DR
17 | 2020-10-01 | Y | 2020-10-01 | MSA | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
18 | 2021-04-01 | S |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC | Metric Suspended; As per Metric 24, it is impossible to accurately measure AAA efficiency in the current CMS configuration. Ongoing work at the Tier-1 on CMS job efficiency provides understanding of the features this metric was intended to capture.
19 | 2021-10-01 | S |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
20 | 2022-04-01 | S |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
21 | 2022-10-01 |  |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
22 | 2023-04-01 |  |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
23 | 2023-10-01 |  |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC
24 | 2024-04-01 |  |  | MSU | Review of CMS AAA Efficiency |  |  |  | T1 CMS | DC

## WP3
Workpackage |  |  | 3 | Title | Federal Responsibilities
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 99% | 2% | 99.99% | MOK | GOCDB Availability | Federal Services Report | Direct | Monthly | WLCG | AD | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-GOCDB?start_date=2021-04-01&end_date=2021-06-30
2 | 0.5 | 0.1 | 1.09 | MOK | GOCDB Usage | Federal Services Report | Direct | Monthly | WLCG | AD | Average Number of Concurrent GOCDB sessions https://vande.gridpp.rl.ac.uk/next/d/Vg3-GCXMk/gocdb-longer-term-host-metrics?orgId=1&from=1617231600000&to=1625093999000
3 | 99% | 2% | 99.65% | MOK | APEL Availability | Federal Services Report | Direct | Monthly | WLCG | AD | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-APEL?start_date=2021-04-01&end_date=2021-06-30
4 | 1 | 0.2 | 1.3 | MOK | APEL Usage | Federal Services Report | Direct | Monthly | WLCG | AD | Millions of messages processed in the quarter.
5 | 97% | 2% | 99.99% | MOK | Workflow Management (DIRAC) Availability | Federal Services Report | Direct | Monthly | WLCG | AD
6 | 5 | 2 | 6 | MOK | Workflow Management (DIRAC) Usage | Federal Services Report | Direct | Monthly | WLCG | AD | Measured as number of active VO (>2000 jobs in the quarter)
7 | 99% | 2% | 99% | MOK | Data Management (FTS + Rucio) Availability | Federal Services Report | Direct | Monthly | WLCG | AD | Only measuring FTS service availability currently
8 | 3 | 1 | 3 | MOK | Data Management (FTS + Rucio) Usage | Federal Services Report | Direct | Monthly | WLCG | AD
9 | 99% | 2% | 97.49% | MCT | CVMFS Availability | Federal Services Report | Direct | Monthly | WLCG | AD | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-CVMFS?start_date=2021-04-01&end_date=2021-06-30
10 |  |  | 44 | MOK | CVMFS Usage | Federal Services Report | Direct | Monthly | WLCG | AD | Measured as number of active repositories
11 | 95% | 5% | 96% | MOK | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | Security Quarterly Report | Direct | Quarterly | Security | DC | 1 CRITICAL advisory; 1 Tier-2 did not respond to request for information Site flagged for follow-up to understand situation (Note for metrics: with 16 production Tier-2s, 1 site not responding makes this amber, should we consider revising the bands for this one?)
12 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | Security Quarterly Report | Direct | Quarterly | Security | DC | n/a in this period
13 |  |  | 2 | MNO | No. of WLCG working groups participated in by GridPP Staff | Quartery Reports | Direct | Quarterly | WLCG | SS
Milestones
ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2021-04-01 | 2021-04-01 | 2021-04-01 | MSA | Review WLCG security policy and procedure set |  |  |  | Security | DK | Review available on request. Milestone now completed (July 2021). This was 3 months late because of conflict with other activities.
2 | 2022-04-01 | 2022-04-01 | 2022-04-01 | MSA | Review of WLCG site security operations (SOC) guidelines |  |  |  | Security | DC
3 | 2023-04-01 |  |  | MSU | Review WLCG security policy and procedure set |  |  |  | Security | DK
4 | 2024-04-01 |  |  | MSU | Review of WLCG site security operations (SOC) guidelines |  |  |  | Security | DC
5 | 2022-04-01 |  |  | MSU | Participation in EGI CSIRT Service Security Challenge |  |  |  | Security | DC
6 | 2024-04-01 |  |  | MSU | Participation in EGI CSIRT Service Security Challenge |  |  |  | Security | DC

## WP4
Workpackage |  |  | 4 | Title | Essential Development
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2 |  | 1 | MOK | No. of Reviews of DiRAC development and rollout to HEP Community |  |  | 6 monthly | Review | DC | Review of progress and deployment status made at GridPP Technical Meeting
2 | 2 |  | 1 | MOK | No. of Reviews of Rucio development and rollout to HEP Community |  |  | 6 monthly | Review | AD | Review of progress and deployment status made at GridPP Technical Meeting
3 | 2 |  | 2 | MOK | No. of Reviews of Tape Service Development |  |  | 6 monthly | Review | AD | Review of Progress made to PMB by Tier-1 Manager via email & PMB report
4 | 2 |  | 2 | MOK | No. of Reviews of Network Development |  |  | 6 monthly | Review | AD | Review of Progress made to PMB by Tier-1 Manager via email & PMB report
5 | 2 |  | 2 | MOK | No. of Reviews of Echo Development |  |  | 6 monthly | Review | AD | Needs to be reviewed 20Q3 to meet 6 month target
6 | 2 |  | 2 | mok | No. of Reviews of Data Lake Developments (DOMA & SWIFT-HEP) |  |  | 6 monthly | Review | AD | Needs to be reviewed 20Q3 to meet 6 month target
Milestones
1 | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2020-12-01 |  | 2020-04-01 | MSA | Procure New Tape Robot | Tender, procure and deploy into production a new Tape Robot |  |  | Tape Service | AD
2 | 2022-03-01 |  | 2021-12-01 | MSA | New Tape management System | CTA adopted as new tape system. Test systems in deployment. |  |  | Tape Service | AD
3 | 2022-06-01 | Yes |  | MOG | Migrate to LTO-9 Tape media | Procure and deploy, next generation of tape drives. |  |  | Tape Service | AD
4 | 2023-03-01 | Yes |  | MOG | Decomission old Tape system | Includes both the Oracle Tape Robot and Castor software. |  |  | Tape Service | AD
5 | 2021-12-01 | Yes |  | MOG | Tier-1 LHCONE integration | Awaits effort from STFC DI Group to become available |  |  | Network | AD
6 | 2021-04-01 | Yes | 2021-01-01 | MOG | Tier-1 Network Upgarde: Install HW |  |  |  | Network | DR
7 | 2020-10-01 |  | 2021-01-01 | MSA | Tier-1 Network Upgarde: 100Gb/s LHCOPN link | Ordered Jan-2020, delayed due to COVID lockdown (done now though) |  |  | Echo Development | AD
8 | 2021-06-01 |  | 2021-12-01 | MOD | Tier-1 Network Upgrade: Join LHCONE |  |  |  | Echo Development | AD
9 | 2021-10-01 | Yes |  | MOG | Tier-1 Network Upgarde: Migrate Services | Migrating |  |  | Echo Development | AD
10 | 2021-03-01 | Yes | 2020-06-01 | MSA | Core Object Store capability | Adding native object store support to Rucio |  |  | Data Lakes | AD
11 | 2021-12-01 | Yes |  | MOG | Rucio: FTS - S3 | Adding S3, WebDAV, HTTPS as endpoint protocols with required functionality (inc 3rd party copy) |  |  | Data Lakes | AD
12 | 2021-06-01 | Yes | 2021-04-01 | MOG | Cacheing for diskless T2s deployed | Support for diskless T2s which then require data form larger T2s. |  |  | Data Lakes | AD
13 | 2022-06-01 | Yes |  | MOG | WLCG "datalake" like federation | Region or national level federation of storage will be needed during GridP6. Awaits WLCG/HSF/DOMA timescales. |  |  | Data Lakes | AD
14 | 2024-03-01 | Yes |  | MOG | Participate in DOMA | DOMA (Data orgnisation, management, access) development and deployment |  |  | Data Lakes | AD
15 | 2021-03-01 |  | 2021-06-01 | MSA | Deployment of storage accounting | WLCG storage accounting to be deployed. DONE |  |  | Data Lakes | AD
| 2021-09-01 |  |  |  | Rucio: IAM integration | EGI
| 2021-12-01 |  |  |  | Rucio: FTS - S3 | GridPP/WLCG
| 2021-06-01 |  |  |  | Rucio: FTS/IAM integration | EGI
| 2022-01-01 |  |  |  | Rucio: WEBFTS | EGI

## WP5
Workpackage |  |  | 5 | Title | Management
Metrics
ID | Target | Margin | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 90% | 5% | 93% | MOK | % FTE in place across collaboration | Quarterly Reports, Project Allocations | Direct | Quarterly | Reporting
2 | 100% | 10% | 70% | MFL | % Quarterly reports received before deadline (2 months) | Quarterly Reports | Direct | Quarterly | Reporting |  | Delayed T1, Fed Services, NorthGrid, LHCb, Security reports due to staff scheduling
3 | 80% | 5% | 100% | MOK | % of Weekly PMB Meetings held | Meeting Minutes, Admin Support | Direct | Quarterly | Management
4 | 100% | 5% | 100% | MOK | % of Weekly Operations Meetings held | Meeting Minutes, Admin Support | Direct | Quarterly | Management
5 | 100% | 5% | 95% | MCT | % of Project Map updated by quarter end | Quarterly Reports, Project Map | Direct | Quarterly | Reporting
6 | 100% | 5% | 100% | MOK | % of Financial Model updated by quarter end | Finacial Model, STFC, Quarterly Reports | Direct | Quarterly | Reporting
7 | 2 | 0 | 2 | MOK | No. of Face to Face PMB Meetings held | Meeting Minutes, Admin Support | Direct | Yearly | Management
8 | 2 | 0 | 2 | mok | No. of Collaboration Meetings held | Meeting Minutes, Admin Support | Direct | Yearly | Management
9 | 4 | 0 | 4 | moK | No. of Tier-1 Resource Meetings held | Meeting Minutes, Admin Support | Direct | Yearly | Management
Milestones
ID | Target | Started | Current | Status | Description | Inputs | Type | Frequency | Category | Owner | Narrative
1 | 2020-04-01 | Yes | 2020-04-01 | MSA | Financial plan for GridPP6 established |  |  |  | Planning
2 | 2020-06-02 | Yes | 2020-05-01 | MSA | Draft ProjectMap for GridPP6. |  |  |  | Planning
3 | 2020-08-02 | Yes | 2020-08-01 | MSA | Final project map for GridPP6. |  |  |  | Planning
4 | 2020-08-01 | Yes | 2020-08-01 | MSA | Quarterly reporting system agreed for other areas |  |  |  | Planning
5 | 2020-04-01 | Yes | 2020-03-01 | MSA | T2 staff grants issued for GridPP6 |  |  |  | Planning
6 | 2021-09-01 | Yes | 2020-04-01 | MSA | Allocations for Tier-2 hardware grants |  |  |  | Planning
7 | 2021-10-01 | Yes | 2020-04-01 | MSA | Grants for Tier-2 hardware issued |  |  |  | Planning
8 | 2023-09-02 | Yes | 2021-12-01 | MSA | Allocations for Tier-2 hardware grants |  |  |  | Planning
9 | 2023-10-03 | Yes |  | MSU | Grants for Tier-2 hardware issued |  |  |  | Planning
10 | 2023-04-01 | Yes |  | MSU | Post-GridPP6 planning initiated |  |  |  | Planning
11 | Variable |  |  | MSU | OC papers submitted 2 weeks before meeting |  |  | Half Yearly | Review
12 | 2020-09-30 | Yes | 2020-09-01 | MSA | WLCG pledges updated |  |  | Yearly | Pledges
13 | 2020-12-31 | Yes | 2020-10-01 | MSA | Year 1 review of service to experiments |  |  | Yearly | Review
14 | 2021-09-30 | Yes | 2021-09-01 | MSA | WLCG pledges updated |  |  | Yearly | Pledges
15 | 2021-12-31 | Yes | 2021-12-01 | MSA | Year 2 review of service to experiments |  |  | Yearly | Review
16 | 2022-09-30 | Yes |  | MSU | WLCG pledges updated |  |  | Yearly | Pledges
17 | 2022-12-31 |  |  | MSU | Year 3 review of service to experiments |  |  | Yearly | Review
18 | 2023-09-30 |  |  | MSU | WLCG pledges updated |  |  | Yearly | Pledges
19 | 2023-12-31 |  |  | MSU | Year 4 review of service to experiments |  |  | Yearly | Review

## Index
Initials | Name | Role
AD | Alastair Dewhurst | Tier-1 Manager
AM | Andrew McNab | LHCB
DB | David Britton | Project Leader
DC | David Colling | CMS
DR | Duncan Rand | LondonGrid, Other Rep.
SS | Samuel Skipsey | Project Manager
MD | Matthew Doidge | NorthGrid
PG | Pete Gronbech | Resource Manager
RJ | Roger Jones | ATLAS

## Milestones&Deliverables
Milestones (including Deliverables) Table
No. |  | Work Package | Description | Baseline Date | Target |  | Completion Date | Status | Delay due to |  | Affects Critical Path? | See Note
[5 empty] | Date | Change |  |  | UK | Other
1a.1 | 1 | 1a | GridPP review of operation (biennial) | 2020-11-01 | 2020-11-01 | ↔ |  | on track
1a.2 | 2 | 1a | GridPP review of operation (biennial) | 2022-10-01 | 2022-10-01 | ↔ |  | on track
1a.3 | 3 | 1a | Produce the purchasing plan | 2020-06-01 | 2020-06-01 | ↔ | 2020-05-01 | completed
1a.4 | 4 | 1a | FY20 Capacity order placed | 2020-11-01 | 2020-11-01 | ↔ | 2020-07-01 | completed
1a.5 | 5 | 1a | FY20 Purchase in production | 2021-04-01 | 2021-04-01 | ↔ | 2021-06-01 | on track
1a.6 | 6 | 1a | Tier-1 WLCG MoU commitments met | 2021-05-01 | 2021-05-01 | ↔ | 2021-05-01 | on track
1a.7 | 7 | 1a | Produce the purchasing plan | 2021-06-01 | 2021-06-01 | ↔ | 2021-06-01 | on track
1a.8 | 8 | 1a | FY21 Capacity order placed | 2021-11-01 | 2021-11-01 | ↔ | 2021-08-01 | on track
1a.9 | 9 | 1a | FY21 Purchase in production | 2022-04-01 | 2022-04-01 | ↔ |  | on track
1a.10 | 10 | 1a | Tier-1 WLCG MoU commitments met | 2022-05-01 | 2022-05-01 | ↔ | 2022-04-01 | on track
1a.11 | 11 | 1a | Produce the purchasing plan | 2022-06-01 | 2022-06-01 | ↔ | 2022-04-01 | on track
1a.12 | 12 | 1a | FY22 Capacity order placed | 2022-11-01 | 2022-11-01 | ↔ |  | on track
1a.13 | 13 | 1a | FY22 Purchase in production | 2023-04-01 | 2023-04-01 | ↔ |  | on track
1a.14 | 14 | 1a | Tier-1 WLCG MoU commitments met | 2023-05-01 | 2023-05-01 | ↔ |  | on track
1a.15 | 15 | 1a | Produce the purchasing plan | 2023-06-01 | 2023-06-01 | ↔ |  | on track
1a.16 | 16 | 1a | FY23 Capacity order placed | 2023-11-01 | 2023-11-01 | ↔ |  | on track
1a.17 | 17 | 1a | FY23 Purchase in production | 2024-04-01 | 2024-04-01 | ↔ |  | on track
1a.18 | 18 | 1a | Tier-1 WLCG MoU commitments met | 2024-05-01 | 2024-05-01 | ↔ |  | on track
1b.1 | 1 | 1b | Allocate Tier-2 funds based on performance/utilisation | 2020-06-01 | 2020-06-01 | ↔ | 2020-04-01 | completed
1b.2 | 2 | 1b | FY21/22 Pocurements commence | 2021-10-01 | 2021-10-01 | ↔ | 2021-10-01 | on track
1b.3 | 3 | 1b | FY21/22 Procurements completed | 2022-04-01 | 2022-04-01 | ↔ | 2022-04-01 | on track
1b.4 | 4 | 1b | Allocate Tier-2 funds based on performance/utilisation | 2022-06-01 | 2022-06-01 | ↔ | 2021-12-01 | on track
1b.5 | 5 | 1b | FY22/23 Pocurements commence | 2022-10-01 | 2022-10-01 | ↔ |  | on track
1b.6 | 6 | 1b | FY22/23 Procurements completed | 2023-04-01 | 2023-04-01 | ↔ |  | on track
1b.7 | 7 | 1b | Review and set WLCG Pledges | 2020-08-01 | 2020-08-01 | ↔ | 2020-08-01 | on track
1b.8 | 8 | 1b | Review and set WLCG Pledges | 2021-08-01 | 2021-08-01 | ↔ | 2021-08-01 | on track
1b.9 | 9 | 1b | Review and set WLCG Pledges | 2022-08-01 | 2022-08-01 | ↔ |  | on track
1b.10 | 10 | 1b | Review and set WLCG Pledges | 2023-08-01 | 2023-08-01 | ↔ |  | on track
1c.1 | 1 | 1c | GridPP-wide security communication challenge | 2021-04-01 | 2021-04-01 | ↔ | 2020-07-01 | completed
1c.2 | 2 | 1c | GridPP-wide security communication challenge | 2022-04-01 | 2022-04-01 | ↔ | 2021-11-01 | on track
1c.3 | 3 | 1c | GridPP-wide security communication challenge | 2023-04-01 | 2023-04-01 | ↔ |  | on track
1c.4 | 4 | 1c | GridPP-wide security communication challenge | 2024-04-01 | 2024-04-01 | ↔ |  | on track
1c.5 | 5 | 1c | GridPP-wide security training event | 2022-04-01 | 2022-04-01 | ↔ | 2020-07-01 | on track
1c.6 | 6 | 1c | GridPP-wide security training event | 2024-04-01 | 2024-04-01 | ↔ |  | on track
1c.7 | 7 | 1c | Review of the role of the security team | 2022-04-01 | 2022-04-01 | ↔ |  | on track
2.1 | 1 | 2 | Report on delivery to ATLAS during year | 2020-12-01 | 2020-12-01 | ↔ | 2020-11-01 | on track
2.2 | 2 | 2 | Report on delivery to ATLAS during year | 2021-12-01 | 2021-12-01 | ↔ | 2021-11-01 | on track
2.3 | 3 | 2 | Report on delivery to ATLAS during year | 2022-12-01 | 2022-12-01 | ↔ |  | on track
2.4 | 4 | 2 | Report on delivery to ATLAS during year | 2023-12-01 | 2023-12-01 | ↔ |  | on track
2.5 | 5 | 2 | Report on delivery to CMS during year | 2020-12-01 | 2020-12-01 | ↔ | 2020-11-01 | on track
2.6 | 6 | 2 | Report on delivery to CMS during year | 2021-12-01 | 2021-12-01 | ↔ | 2020-11-01 | on track
2.7 | 7 | 2 | Report on delivery to CMS during year | 2022-12-01 | 2022-12-01 | ↔ |  | on track
2.8 | 8 | 2 | Report on delivery to CMS during year | 2023-12-01 | 2023-12-01 | ↔ |  | on track
2.9 | 9 | 2 | Report on delivery to LHCb during year | 2020-12-01 | 2020-12-01 | ↔ | 2020-11-01 | on track
2.10 | 10 | 2 | Report on delivery to LHCb during year | 2021-12-01 | 2021-12-01 | ↔ | 2020-11-01 | on track
2.11 | 11 | 2 | Report on delivery to LHCb during year | 2022-12-01 | 2022-12-01 | ↔ |  | on track
2.12 | 12 | 2 | Report on delivery to LHCb during year | 2023-12-01 | 2023-12-01 | ↔ |  | on track
2.13 | 13 | 2 | Report on delivery to Other during year | 2020-12-01 | 2020-12-01 | ↔ | 2020-11-01 | on track
2.14 | 14 | 2 | Report on delivery to Other during year | 2021-12-01 | 2021-12-01 | ↔ | 2020-11-01 | on track
2.15 | 15 | 2 | Report on delivery to Other during year | 2022-12-01 | 2022-12-01 | ↔ |  | on track
2.16 | 16 | 2 | Report on delivery to Other during year | 2023-12-01 | 2023-12-01 | ↔ |  | on track
2.17 | 17 | 2 | Review of CMS AAA Efficiency | 2020-10-01 | 2020-10-01 | ↔ | 2020-10-01 | on track
2.18 | 18 | 2 | Review of CMS AAA Efficiency | 2021-04-01 | 2021-04-01 | ↔ |  | suspended
2.19 | 19 | 2 | Review of CMS AAA Efficiency | 2021-10-01 | 2021-10-01 | ↔ |  | on track
2.20 | 20 | 2 | Review of CMS AAA Efficiency | 2022-04-01 | 2022-04-01 | ↔ |  | on track
2.21 | 21 | 2 | Review of CMS AAA Efficiency | 2022-10-01 | 2022-10-01 | ↔ |  | on track
2.22 | 22 | 2 | Review of CMS AAA Efficiency | 2023-04-01 | 2023-04-01 | ↔ |  | on track
2.23 | 23 | 2 | Review of CMS AAA Efficiency | 2023-10-01 | 2023-10-01 | ↔ |  | on track
2.24 | 24 | 2 | Review of CMS AAA Efficiency | 2024-04-01 | 2024-04-01 | ↔ |  | on track
3.1 | 1 | 3 | Review WLCG security policy and procedure set | 2021-04-01 | 2021-04-01 | ↔ | 2021-04-01 | on track
3.2 | 2 | 3 | Review of WLCG site security operations (SOC) guidelines | 2022-04-01 | 2022-04-01 | ↔ | 2022-04-01 | on track
3.3 | 3 | 3 | Review WLCG security policy and procedure set | 2023-04-01 | 2023-04-01 | ↔ |  | on track
3.4 | 4 | 3 | Review of WLCG site security operations (SOC) guidelines | 2024-04-01 | 2024-04-01 | ↔ |  | on track
3.5 | 5 | 3 | Participation in EGI CSIRT Service Security Challenge | 2022-04-01 | 2022-04-01 | ↔ |  | on track
3.6 | 6 | 3 | Participation in EGI CSIRT Service Security Challenge | 2024-04-01 | 2024-04-01 | ↔ |  | on track
4.1 | 1 | 4 | Procure New Tape Robot | 2020-12-01 | 2020-12-01 | ↔ | 2020-04-01 | completed
4.2 | 2 | 4 | New Tape management System | 2022-03-01 | 2022-03-01 | ↔ | 2021-12-01 | on track
4.3 | 3 | 4 | Migrate to LTO-9 Tape media | 2022-06-01 | 2022-06-01 | ↔ |  | on track
4.4 | 4 | 4 | Decomission old Tape system | 2023-03-01 | 2023-03-01 | ↔ |  | on track
4.5 | 5 | 4 | Tier-1 LHCONE integration | 2021-12-01 | 2021-12-01 | ↔ |  | on track
4.6 | 6 | 4 | Tier-1 Network Upgarde: Install HW | 2021-04-01 | 2021-04-01 | ↔ | 2021-01-01 | on track
4.7 | 7 | 4 | Tier-1 Network Upgarde: 100Gb/s LHCOPN link | 2020-10-01 | 2020-10-01 | ↔ | 2021-01-01 | completed
4.8 | 8 | 4 | Tier-1 Network Upgrade: Join LHCONE | 2021-06-01 | 2021-06-01 | ↔ | 2021-12-01 | on track
4.9 | 9 | 4 | Tier-1 Network Upgarde: Migrate Services | 2021-10-01 | 2021-10-01 | ↔ |  | on track
4.10 | 10 | 4 | Core Object Store capability | 2021-03-01 | 2021-03-01 | ↔ | 2020-06-01 | on track
4.11 | 11 | 4 | Rucio: FTS - S3 | 2021-12-01 | 2021-12-01 | ↔ |  | on track
4.12 | 12 | 4 | Cacheing for diskless T2s deployed | 2021-06-01 | 2021-06-01 | ↔ | 2021-04-01 | on track
4.13 | 13 | 4 | WLCG "datalake" like federation | 2022-06-01 | 2022-06-01 | ↔ |  | on track
4.14 | 14 | 4 | Participate in DOMA | 2024-03-01 | 2024-03-01 | ↔ |  | on track
4.15 | 15 | 4 | Deployment of storage accounting | 2021-03-01 | 2021-03-01 | ↔ |  | on track
5.1 | 1 | 5 | Financial plan for GridPP6 established | 2020-04-01 | 2020-04-01 | ↔ | 2020-04-01 | completed
5.2 | 2 | 5 | Draft ProjectMap for GridPP6. | 2020-06-02 | 2020-06-02 | ↔ | 2020-05-01 | completed
5.3 | 3 | 5 | Final project map for GridPP6. | 2020-08-02 | 2020-08-02 | ↔ | 2020-08-01 | on track
5.4 | 4 | 5 | Quarterly reporting system agreed for other areas | 2020-08-01 | 2020-08-01 | ↔ | 2020-08-01 | on track
5.5 | 5 | 5 | T2 staff grants issued for GridPP6 | 2020-04-01 | 2020-04-01 | ↔ | 2020-03-01 | completed
5.6 | 6 | 5 | Allocations for Tier-2 hardware grants | 2021-09-01 | 2021-09-01 | ↔ | 2020-04-01 | completed
5.7 | 7 | 5 | Grants for Tier-2 hardware issued | 2021-10-01 | 2021-10-01 | ↔ | 2020-04-01 | completed
5.8 | 8 | 5 | Allocations for Tier-2 hardware grants | 2023-09-02 | 2023-09-02 | ↔ | 2021-12-01 | on track
5.9 | 9 | 5 | Grants for Tier-2 hardware issued | 2023-10-03 | 2023-10-03 | ↔ |  | on track
5.10 | 10 | 5 | Post-GridPP6 planning initiated | 2023-04-01 | 2023-04-01 | ↔ |  | on track
5.11 | 11 | 5 | OC papers submitted 2 weeks before meeting | Variable | Variable | ↔ |  | on track
5.12 | 12 | 5 | WLCG pledges updated | 2020-09-30 | 2020-09-30 | ↔ | 2020-09-01 | on track
5.13 | 13 | 5 | Year 1 review of service to experiments | 2020-12-31 | 2020-12-31 | ↔ | 2020-10-01 | on track
5.14 | 14 | 5 | WLCG pledges updated | 2021-09-30 | 2021-09-30 | ↔ | 2021-09-01 | on track
5.15 | 15 | 5 | Year 2 review of service to experiments | 2021-12-31 | 2021-12-31 | ↔ | 2021-12-01 | on track
5.16 | 16 | 5 | WLCG pledges updated | 2022-09-30 | 2022-09-30 | ↔ |  | on track
5.17 | 17 | 5 | Year 3 review of service to experiments | 2022-12-31 | 2022-12-31 | ↔ |  | on track
5.18 | 18 | 5 | WLCG pledges updated | 2023-09-30 | 2023-09-30 | ↔ |  | on track
5.19 | 19 | 5 | Year 4 review of service to experiments | 2023-12-31 | 2023-12-31 | ↔ |  | on track